## Overview
SEGRO POAP Costings — Summary (all figures recalc live from the Control Panel)
Active scenario: effort = Likely · HCL = Include · platform = AKS · vendor = AzureOpenAI · sku = GPT-4o · obs = Azure · agents = Exclude/1 · mcp = 2 · rag = AISearch_Cosmos · envs = 4 · day rate £850 · contingency 15% · slip 0 wk · overlap 0 wk
HEADLINES
Build — POAP phases + loadings (one-off) | 830342.0708
Run — 5 years (indexed) | 1656842.3154
5-YEAR TCO (build + run) | 2487184.3862
TCO per employee (OrgSize input) | 3553.1206
Y1 cash (build + run Y1) | 1142415.895
CHART DATA (formula-driven — edit the Control Panel, not these cells)
Waterfall segment | Base (invisible) | Block (visible) | Delta (signed) | Cumulative | Short label | Reverse label | Base (invisible) | Block (visible) | Cumulative (reverse)
Design & Plan | 0 | 66625 | 66625 | 66625 | Plan | 5-yr TCO | 0 | 2487184.3862 | 2487184.3862
Build - SEGRO (Azure foundations, AKS, shared services) | 66625 | 221146.5833 | 221146.5833 | 287771.5833 | Build | Plan | 2420559.3862 | 66625 | 2420559.3862
Build - HCL (UnO + TX install, Unica+/CDP deploy) | 287771.5833 | 158250 | 158250 | 446021.5833 | Build | Build | 2199412.8029 | 221146.5833 | 2199412.8029
Testing (SIT, pen test, UAT, performance) | 446021.5833 | 89165 | 89165 | 535186.5833 | Testing | Build | 2041162.8029 | 158250 | 2041162.8029
Deploy (prod readiness, migration, go-live) | 535186.5833 | 66700 | 66700 | 601886.5833 | Deploy | Testing | 1951997.8029 | 89165 | 1951997.8029
Hypercare / PGLS + business readiness close-out | 601886.5833 | 120150 | 120150 | 722036.5833 | Maintenance | Deploy | 1885297.8029 | 66700 | 1885297.8029
Contingency | 722036.5833 | 108305.4875 | 108305.4875 | 830342.0708 | Contingency | Maintenance | 1765147.8029 | 120150 | 1765147.8029
Slip − Overlap | 830342.0708 | 0 | 0 | 830342.0708 | Slip/Overlap | Contingency | 1656842.3154 | 108305.4875 | 1656842.3154
Run (5yr) | 830342.0708 | 1656842.3154 | 1656842.3154 | 2487184.3862 | Run (5yr) | Slip/Overlap | 1656842.3154 | 0 | 1656842.3154
5-yr TCO | 0 | 2487184.3862 | 2487184.3862 | 2487184.3862 | 5-yr TCO | Run (5yr) | 0 | 1656842.3154 | 0
GO-LIVE (live — moves with slip)
Live go-live week (29 + slip) | 29 |  | Nominal 29 wk (Fri wk29 = 29 Jan 2027); slip extends go-live. Overlap is a cost saving (parallel HCL install), not a critical-path compression — matches the Gantt.
Live go-live date | 2027-01-29 |  | Anchored to the Gantt week-1 Monday (13 Jul 2026); Friday of the live go-live week.
GO-LIVE SCENARIOS (Green Book duration band) | Optimistic | Green Book lower | Green Book upper
Slip applied (weeks) | 0 | 3 | 16
Go-live week | 29 | 32 | 45
Go-live date | 2027-01-29 | 2027-02-19 | 2027-05-21
Weeks later than plan | 0 | 3 | 16
▪ Scenarios hold overlap at 0. +3 wk ≈ Green Book ICT duration optimism-bias lower bound (+10% of the 29-wk pre-go-live span); +16 wk ≈ upper bound (+54%). The live figures above respond to the actual Control Panel slip/overlap.
AGENT / MCP CALCULATOR (live — edit Control Panel)
AgentStack | Exclude | RagMemoryShape | AISearch_Cosmos
AgentCount (intensity) | 1 | McpServerCount (app plugs) | 2
Agent-stack run Y1 (MCP+RAG+memory; £0 when AgentStack=Exclude) | 0
Reference scenarios (proportional from live stack Y1; does not override Control Panel) | Agents | MCP servers | Est. stack Y1 £
Scenario 1 agents × 2 MCP | 1 | 2 | 0
Scenario 5 agents × 10 MCP | 5 | 10 | 0
Scenario 30 agents × 50 MCP | 30 | 50 | 0
▪ Named agents (which to build) live on the Agents tab and Gantt ASSUMPTION lanes. AgentCount scales intensity; McpServerCount scales application plugs.
Month (from contract) | Cumulative spend £ | Go-live marker
1 | 73868.3797 | #N/A
2 | 179906.9089 | #N/A
3 | 291834.5091 | #N/A
4 | 413646.102 | #N/A
5 | 541366.5442 | #N/A
6 | 648554.8614 | #N/A
7 | 744292.7328 | 744292.7328
8 | 857007.1349 | #N/A
9 | 890222.2869 | #N/A
10 | 916228.4389 | #N/A
11 | 942234.5909 | #N/A
12 | 968240.7429 | #N/A
13 | 994246.8949 | #N/A
14 | 1020253.047 | #N/A
15 | 1046259.199 | #N/A
16 | 1072265.351 | #N/A
Phase | SEGRO | HCL | Azure | ThirdParty
Design & Plan | 52375 | 14250 | 0 | 0
Build - SEGRO (Azure fou | 205445 | 0 | 15701.5833 | 0
Build - HCL (UnO + TX in | 15750 | 142500 | 0 | 0
Testing (SIT, pen test, | 55915 | 19000 | 0 | 14250
Deploy (prod readiness, | 47700 | 19000 | 0 | 0
Hypercare / PGLS + busin | 91650 | 28500 | 0 | 0
Run Y1 by side | £/yr
SEGRO | 255064.8
HCL | 0
Azure | 52259.0242
ThirdParty | 4750
▪ Benchmark provenance: all Benchmarks-tab rows are copied from org_it_benchmarks.json and programme_benchmarks.json (both adversarially verified, verdict APPROVE 17 Jul 2026) with their original status labels (VERIFIED / INDICATIVE / ASSUMPTION) carried unchanged; verifier MINORs
▪ Headcount: SEGRO's actual Group headcount is 463 (ARA 2025 p86; FY2025 average 454, of which 168 indirect/administration) versus the ~700 briefed — anchor OrgSize and all per-user maths to ~450-465, with the 168 'office' population available for knowledge-worker-only SKUs.
▪ INDICATIVE and list-price rows are vendor list / aggregator figures, not quotes: Microsoft GBP prices are paid-yearly annual-commitment ex-VAT list captured 16 Jul 2026 (a +5% monthly-billing premium applies, and 2026 M365 pricing/packaging updates are announced — re-verify at co
▪ HCL side is a FLOOR: HCL licence and subscription lines are RATE_MISSING (contract not shared) and are carried as clearly-labelled adjustable input cells defaulting to £0 — never presented as verified figures; totals on the HCL branch therefore understate true cost.
▪ Contingency framing: the workbook's ContingencyPct should be read against the HM Treasury Green Book optimism-bias band for ICT (10% floor at contract award with evidenced mitigation, 200% upper at outline-business-case stage) — a flat 10-20% default sits at the optimistic end of

## Gantt - POAP As Drawn (hidden)
Gantt - POAP As Drawn — technical step decomposition per major line of work
The POAP as drawn on slide 3 (16 Jul 2026 deck), decomposed into technical steps per major line of work. Window statuses: POAP-DRAWN = bar drawn on the slide; ASSUMPTION = no bar exists (the work is costed but absent from the plan). Step statuses: DERIVED = step text and position follow from slide sub-items, named documents (slides 5-10) or the verified cost model; ASSUMPTION = position is sequencing judgement, text still sourced. TASK bars dilate with SlipWeeks ONLY on time-driven work (people schedules + Azure commissioning + any people LANE); a pure fixed-fee TASK bar (a RATE_MISSING-licence fold or a third-party pen-test/red-team engagement) SHIFTS under slip but keeps its drawn duration, matching the slip-cost model. STEP bars render RELATIVE to their parent task's live window, so a fixed licence STEP inside a time-driven lane (e.g. the procurement track) rides the lane and may widen with it — the fixed-does-not-stretch rule is a TASK-row property, not a step-row one. Bars recalc live: SlipWeeks dilates TIME-DRIVEN windows (people + Azure commissioning) pro-rata — the same elongation the slip cost prices; FIXED-fee engagements (licences, third-party pen-test/red-team) shift but keep their duration; hypercare shifts whole. A ▶ in the Slip column flags any bar clipped at the grid edge under a large slip. Milestones: ▲ go-live (moves with slip) · ✕ Christmas · ! Bank holiday · ◆ drawn phase gate. Bar colours: SEGRO red · HCL dark blue · Azure mid blue · Third-party purple.
[10 empty] | Jul 26 |  |  | Aug 26 |  |  |  |  | Sep 26 |  |  |  | Oct 26 |  |  |  | Nov 26 |  |  |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27
Id | Major line of work / technical step | Side | Status | Findings | Depends on | Start wk | Wks | Live start | Live end | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | Slip | Basis / source | 29
| Milestones | [12 empty] | ◆ |  |  | ! | [12 empty] | ◆ |  |  | ✕ | ◆ |  |  |  | ▲
G-P1-L1 | Design & Plan (lane A) [P1-L1] | SEGRO | POAP-DRAWN | F16 |  | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | [57 empty] | Slide 3 lane A design bar is drawn: '5 weeks' bar x=1.98 w=2.54 = gantt_timeline P1 window weeks 1-5. Role/scope from spec_cost_model P1-L1: 'Solutions architect - workshop lead, HLD/LLD, target arch for EA, KDD papers (AKS v ARO, env count, cluster topology)', 1 FTE x 5 wk.
G-P1-L1-s1 | • Lead Arch Workshop Kick-off | SEGRO | DERIVED |  |  | 1 | 1 | 1 | 1 | 1 | [61 empty] | Slide 3 chip 'Arch Workshop Kick-off' (x=1.40) is the first workshop in the drawn left-to-right stagger of the lane-A chain - earliest position, so week 1 at parent start.
G-P1-L1-s2 | • Lead Arch Workshop Sizing | SEGRO | DERIVED |  | G-P1-L1-s1 | 2 | 1 | 2 | 2 |  | 1 | [60 empty] | Slide 3 chip 'Arch Workshop Sizing' (x=1.65) is drawn second in the workshop stagger, immediately right of kick-off - next week slot.
G-P1-L1-s3 | • Draft KDD papers (AKS v ARO, env count, cluster topology) feeding the lane-B KDD decisions | SEGRO | ASSUMPTION |  | G-P1-L1-s1 | 2 | 2 | 2 | 3 |  | 1 | 1 | [59 empty] | Text from spec_cost_model P1-L1 desc: 'KDD papers (AKS v ARO, env count, cluster topology)'. Position is judgement: drafting must follow the kick-off/sizing workshops and precede the lane-B 'KDDs documented / agreed' close-out - no drawn bar for the drafting itself.
G-P1-L1-s4 | • Produce High Level Design | SEGRO | ASSUMPTION |  | G-P1-L1-s2 | 3 | 2 | 3 | 4 |  |  | 1 | 1 | [58 empty] | Slide 5 named doc 'High Level Design'. Position is judgement: mid-phase, after the sizing and cyber workshops provide inputs; slide gives no per-document dates.
G-P1-L1-s5 | • Target Arch for EA (consuming platform engineer's physical infrastructure diagrams) | SEGRO | DERIVED |  | G-P1-L1-s4 | 4 | 1 | 4 | 4 |  |  |  | 1 | [58 empty] | Slide 3 chip 'Physical infrastructure diagrams and Target Arch for EA' (x=3.07) is drawn last in the lane-A stagger, late in the design bar - week 4 position follows from the drawn order.
G-P1-L1-s6 | • Finalise Low Level Design for Enterprise Arch; KDDs documented / agreed | SEGRO | ASSUMPTION |  | G-P1-L1-s3, G-P1-L1-s4 | 4 | 2 | 4 | 5 |  |  |  | 1 | 1 | [57 empty] | Slide 5 named docs 'Low Level Design for Enterprise Arch' and 'KDDs documented / agreed'. Position is judgement: closing deliverables in the final two weeks before the slide-3 'Design phase complete' marker; no per-document dates drawn.
G-P1-L2 | Design & Plan (lane A) [P1-L2] | SEGRO | POAP-DRAWN | F16, F14 |  | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | [57 empty] | Window = drawn slide 3 '5 weeks' design bar (x=1.98 w=2.54) = weeks 1-5. Role/scope from spec_cost_model P1-L2: 'Platform engineer - sizing workshop, physical infrastructure diagrams, physical sizing of infrastructure', 0.6 FTE.
G-P1-L2-s1 | • Attend Arch Workshop Kick-off; assemble estate sizing inputs | SEGRO | DERIVED |  |  | 1 | 1 | 1 | 1 | 1 | [61 empty] | Slide 3 chip 'Arch Workshop Kick-off' (x=1.40), first in the drawn stagger - week 1 at parent start; sizing-input scope from spec_cost_model P1-L2 desc 'sizing workshop'.
G-P1-L2-s2 | • Run Arch Workshop Sizing (the workshop the build phase is 'To be validated' against) | SEGRO | DERIVED |  | G-P1-L2-s1 | 2 | 1 | 2 | 2 |  | 1 | [60 empty] | Slide 3 chip 'Arch Workshop Sizing' (x=1.65), second in the drawn stagger. Slide 3 build annotation 'To be validated based on Arch workshop' (x=6.85) hangs on this workshop's output (F14).
G-P1-L2-s3 | • Physical sizing of infrastructure | SEGRO | ASSUMPTION |  | G-P1-L2-s2 | 3 | 2 | 3 | 4 |  |  | 1 | 1 | [58 empty] | Slide 5 named doc 'Physical sizing of infrastructure'. Position is judgement: follows the sizing workshop; no drawn bar for the document itself.
G-P1-L2-s4 | • Physical Low Level Technical Arch Diagrams / physical infrastructure diagrams | SEGRO | DERIVED |  | G-P1-L2-s3 | 4 | 2 | 4 | 5 |  |  |  | 1 | 1 | [57 empty] | Slide 5 named doc 'Physical Low Level Technical Arch Diagrams'; slide 3 chip 'Physical infrastructure diagrams and Target Arch for EA' (x=3.07) is drawn last in the lane-A stagger - late-phase position follows from the drawn order.
G-P1-L3 | Design & Plan (lane A) [P1-L3] | SEGRO | POAP-DRAWN | F16 |  | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | [57 empty] | Window = drawn slide 3 '5 weeks' design bar = weeks 1-5. Role/scope from spec_cost_model P1-L3: 'Cloud security - Cyber Sec Workshop, cyber security impact analysis + diagrams', 0.4 FTE; IAM workshop/design mapped here as the security-owning role.
G-P1-L3-s1 | • Prepare Cyber Sec Workshop inputs (SEGRO security principles, threat context) | SEGRO | ASSUMPTION |  |  | 1 | 1 | 1 | 1 | 1 | [61 empty] | Workshop named on slide 3 ('Cyber Sec Workshop'); preparation step and its week-1 position are judgement - only the workshop chip itself is drawn.
G-P1-L3-s2 | • Run Cyber Sec Workshop | SEGRO | DERIVED |  | G-P1-L3-s1 | 2 | 1 | 2 | 2 |  | 1 | [60 empty] | Slide 3 chip 'Cyber Sec Workshop' (x=1.90), third in the drawn left-to-right workshop stagger - early-mid phase position follows from the drawn order.
G-P1-L3-s3 | • Run Identity Access Mgmt Workshop | SEGRO | DERIVED |  | G-P1-L3-s2 | 3 | 1 | 3 | 3 |  |  | 1 | [59 empty] | Slide 3 chip 'Identity Access Mgmt Workshop' (x=2.01), fourth in the drawn stagger, right of the Cyber Sec Workshop chip.
G-P1-L3-s4 | • Cyber security impact analysis | SEGRO | ASSUMPTION |  | G-P1-L3-s2 | 3 | 2 | 3 | 4 |  |  | 1 | 1 | [58 empty] | Slide 5 named doc 'Cyber security impact analysis'. Position is judgement: follows the Cyber Sec Workshop; no drawn bar for the document.
G-P1-L3-s5 | • Cyber security diagrams | SEGRO | ASSUMPTION |  | G-P1-L3-s4 | 4 | 2 | 4 | 5 |  |  |  | 1 | 1 | [57 empty] | Slide 5 named doc 'Cyber security diagrams'. Position is judgement: diagrams follow the impact analysis in the phase tail.
G-P1-L3-s6 | • Identity & access management design | SEGRO | ASSUMPTION |  | G-P1-L3-s3 | 4 | 2 | 4 | 5 |  |  |  | 1 | 1 | [57 empty] | Slide 5 named doc 'Identity & access management design'. Position is judgement: follows the IAM workshop; closes with the phase.
G-P1-L4 | Design & Plan (lane A) [P1-L4] | SEGRO | POAP-DRAWN | F16 |  | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | [57 empty] | Window = drawn slide 3 '5 weeks' design bar = weeks 1-5. Role/scope from spec_cost_model P1-L4: 'Data engineer - Data Mgmt Workshop, data flow design, data governance principles input', 0.4 FTE.
G-P1-L4-s1 | • Prepare Data Mgmt Workshop inputs (data landscape, governance principles) | SEGRO | ASSUMPTION |  |  | 1 | 2 | 1 | 2 | 1 | 1 | [60 empty] | Text from spec_cost_model P1-L4 desc 'data governance principles input' and the slide-3 workshop name; preparation step and its position are judgement - only the workshop chip is drawn.
G-P1-L4-s2 | • Run Data Mgmt Workshop | SEGRO | DERIVED |  | G-P1-L4-s1 | 3 | 1 | 3 | 3 |  |  | 1 | [59 empty] | Slide 3 chip 'Data Mgmt Workshop' (x=2.31), fifth and last workshop in the drawn left-to-right stagger - mid-phase position follows from the drawn order.
G-P1-L4-s3 | • Data flow design | SEGRO | ASSUMPTION |  | G-P1-L4-s2 | 4 | 2 | 4 | 5 |  |  |  | 1 | 1 | [57 empty] | Slide 5 named doc 'Data flow design'. Position is judgement: follows the Data Mgmt Workshop; no drawn bar for the document.
G-P1-L4-s4 | • Data governance principles input handed to the build-phase Data Mgmt & Governance workstream | SEGRO | ASSUMPTION |  | G-P1-L4-s2 | 4 | 2 | 4 | 5 |  |  |  | 1 | 1 | [57 empty] | Text from spec_cost_model P1-L4 desc 'data governance principles input' (the downstream stream is slide 3 build item 6 'Data Mgmt and Governance Principles'). Handover position at phase tail is judgement.
G-P1-L5 | Design & Plan (lane A) [P1-L5] | SEGRO | POAP-DRAWN | F16 |  | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | [57 empty] | Window = drawn slide 3 '5 weeks' design bar = weeks 1-5. Role/scope from spec_cost_model P1-L5: 'Business analyst - Use case scope for Release 1 Agreed, KDD documentation, DRG/ARG approval pack', 0.4 FTE.
G-P1-L5-s1 | • Use case scoping for Release 1, closing with 'Use case scope for Release 1 Agreed' | SEGRO | DERIVED |  |  | 1 | 2 | 1 | 2 | 1 | 1 | [60 empty] | Slide 3 chip 'Use case scope for Release 1 Agreed' (x=1.95) is drawn at the very start of the design bar (bar starts x=1.98) - early position follows from the drawing.
G-P1-L5-s2 | • Business context input to the workshop chain (sizing, cyber, IAM, data) | SEGRO | ASSUMPTION |  | G-P1-L5-s1 | 2 | 2 | 2 | 3 |  | 1 | 1 | [59 empty] | Workshops named on slide 3 ('Arch Workshop Sizing', 'Cyber Sec Workshop', 'Identity Access Mgmt Workshop', 'Data Mgmt Workshop'); BA attendance and its weeks-2-3 position are judgement.
G-P1-L5-s3 | • KDD documentation | SEGRO | ASSUMPTION |  | G-P1-L5-s2 | 3 | 2 | 3 | 4 |  |  | 1 | 1 | [58 empty] | Text from spec_cost_model P1-L5 desc 'KDD documentation' and slide 5 named doc 'KDDs documented / agreed'. Position is judgement: follows the workshop chain, precedes DRG close-out.
G-P1-L5-s4 | • DRG approval doc / DRG-ARG approval pack | SEGRO | ASSUMPTION |  | G-P1-L5-s3 | 4 | 2 | 4 | 5 |  |  |  | 1 | 1 | [57 empty] | Slide 5 named doc 'DRG approval doc'; slide 3 lane-B item 'Arch decisions for DRG / ARG'. Position is judgement: approval pack lands at the phase tail; no drawn date for the document.
G-P1-L6 | Design & Plan (lane A) [P1-L6] | SEGRO | POAP-DRAWN | F16 |  | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | [57 empty] | Window = drawn slide 3 '5 weeks' design bar = weeks 1-5. Role/scope from spec_cost_model P1-L6: 'Project manager - mobilisation, delivery plan, procurement specification and coordination', 1 FTE.
G-P1-L6-s1 | • Architecture Plan & Mobilisations | SEGRO | DERIVED |  |  | 1 | 1 | 1 | 1 | 1 | [61 empty] | Slide 3 item 'Architecture Plan & Mobilisations' (x=0.70, numbered 1) is drawn at the head of lane A - week 1 at parent start.
G-P1-L6-s2 | • Coordinate workshop chain and track KDD decisions | SEGRO | ASSUMPTION |  | G-P1-L6-s1 | 2 | 3 | 2 | 4 |  | 1 | 1 | 1 | [58 empty] | Coordination scope from spec_cost_model P1-L6 desc 'procurement specification and coordination' across the slide-3 workshop chips (drawn weeks 1-3 stagger); the coordinating activity itself has no drawn bar - position is judgement.
G-P1-L6-s3 | • Procurement specification (feeds the lane-B 'Procurement of desired tech stack' bar) | SEGRO | ASSUMPTION |  | G-P1-L6-s2 | 3 | 3 | 3 | 5 |  |  | 1 | 1 | 1 | [57 empty] | Slide 5 named doc 'Procurement specification'; the lane-B bar 'Procurement of desired tech stack' is drawn from x=3.10 (~week 3 of the design bar), so the spec is placed alongside it - exact position is judgement.
G-P1-L6-s4 | • Delivery plan | SEGRO | ASSUMPTION |  | G-P1-L6-s2 | 4 | 2 | 4 | 5 |  |  |  | 1 | 1 | [57 empty] | Slide 5 named doc 'Delivery plan'. Position is judgement: consolidates workshop/KDD outcomes at the phase tail before 'Design phase complete'.
G-P1-L7 | Design & Plan (lane A) [P1-L7] | HCL | POAP-DRAWN | F14 |  | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | [57 empty] | Window = drawn slide 3 '5 weeks' design bar = weeks 1-5. Role/scope from spec_cost_model P1-L7: 'HCL architecture/product SME input to design workshops (UnO/TX/Unica/CDP sizing and prerequisites)', 0.6 FTE, side HCL.
G-P1-L7-s1 | • HCL SME attendance at Arch Workshop Kick-off | HCL | DERIVED |  |  | 1 | 1 | 1 | 1 | 1 | [61 empty] | Slide 3 chip 'Arch Workshop Kick-off' (x=1.40), first in the drawn stagger; HCL input scope from spec_cost_model P1-L7 desc 'input to design workshops'.
G-P1-L7-s2 | • UnO/TX/Unica/CDP sizing and prerequisites input to Arch Workshop Sizing | HCL | DERIVED |  | G-P1-L7-s1 | 2 | 1 | 2 | 2 |  | 1 | [60 empty] | Slide 3 chip 'Arch Workshop Sizing' (x=1.65), second in the drawn stagger; product scope quoted from spec_cost_model P1-L7 desc 'UnO/TX/Unica/CDP sizing and prerequisites'. The build phase is 'To be validated based on Arch workshop' (F14) - this input is what the validation hangs on.
G-P1-L7-s3 | • HCL product input to Cyber Sec / Identity Access Mgmt / Data Mgmt workshops | HCL | DERIVED |  | G-P1-L7-s2 | 3 | 1 | 3 | 3 |  |  | 1 | [59 empty] | Slide 3 chips 'Cyber Sec Workshop' (x=1.90), 'Identity Access Mgmt Workshop' (x=2.01), 'Data Mgmt Workshop' (x=2.31) - drawn mid-stagger after the sizing workshop.
G-P1-L7-s4 | • Product prerequisite validation input to physical sizing and KDD papers | HCL | ASSUMPTION |  | G-P1-L7-s2 | 4 | 2 | 4 | 5 |  |  |  | 1 | 1 | [57 empty] | Scope from spec_cost_model P1-L7 desc ('sizing and prerequisites') supporting the slide-5 docs 'Physical sizing of infrastructure' and 'KDDs documented / agreed'; tail-of-phase position is judgement - no drawn bar for HCL input.
G-P1-PROC | Decisions & procurement (lane B) | SEGRO | POAP-DRAWN | F10 |  | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 1 | 1 | [57 empty] | Slide 3 lane B 'Decisions & procurement' (label x=0.67) is drawn inside the P1 window: four KDD chips stacked at the lane start (x=1.37-1.40) plus 'Arch decisions for DRG / ARG' (x=0.53), then the 'Procurement of desired tech stack' bar drawn x=3.10 w=1.31 - per F10 geometry 'roughly a 2.5-2.7 week allowance', ending at the phase boundary. Window = weeks 1-5 in gantt_timeline week numbers; the drawn procurement portion is the final ~2.5 wk. F10 (MAJOR): architect 18 Jul 2026 - 'Procurrent of commercial components would take longer than 2 weeks' - and the licence items P1-L8/P1-L9 are absent from the drawn lane.
G-P1-PROC-s1 | • Agree KDD: TCO AKS v ARO | SEGRO | DERIVED |  |  | 1 | 3 | 1 | 3 | 1 | 1 | 1 | [59 empty] | Slide 3 lane-B chip 'KDD: TCO AKS v ARO' (x=1.40, numbered 1) drawn at the lane start - decision window runs from week 1 ahead of the procurement bar (drawn from x=3.10).
G-P1-PROC-s2 | • Agree KDD: Vol of Environments | SEGRO | DERIVED |  |  | 1 | 3 | 1 | 3 | 1 | 1 | 1 | [59 empty] | Slide 3 lane-B chip 'KDD: Vol of Environments' (x=1.39, numbered 2) drawn stacked at the lane start alongside the other KDD chips - same drawn decision window.
G-P1-PROC-s3 | • Agree KDD: Hybrid Tech Stack | SEGRO | DERIVED |  |  | 1 | 3 | 1 | 3 | 1 | 1 | 1 | [59 empty] | Slide 3 lane-B chip 'KDD: Hybrid Tech Stack' (x=1.39, numbered 3) drawn stacked at the lane start - same drawn decision window.
G-P1-PROC-s4 | • Agree Single Cluster vs Multi Cluster deployment | SEGRO | DERIVED |  |  | 1 | 3 | 1 | 3 | 1 | 1 | 1 | [59 empty] | Slide 3 lane-B chip 'Single Cluster Vs Multi Cluster deployment' (x=1.37, numbered 4) drawn stacked at the lane start - same drawn decision window.
G-P1-PROC-s5 | • Take architecture decisions through DRG / ARG | SEGRO | DERIVED |  |  | 1 | 3 | 1 | 3 | 1 | 1 | 1 | [59 empty] | Slide 3 lane-B item 'Arch decisions for DRG / ARG' (x=0.53) drawn at the head of the lane spanning the KDD chain; governance runs with the KDD decisions ahead of procurement.
G-P1-PROC-s6 | • Procurement of desired tech stack | SEGRO | DERIVED |  | G-P1-PROC-s1, G-P1-PROC-s3, G-P1-PROC-s4 | 3 | 3 | 3 | 5 |  |  | 1 | 1 | 1 | [57 empty] | Slide 3 lane-B bar 'Procurement of desired tech stack' drawn x=3.10 w=1.31 - per F10 'roughly a 2.5-2.7 week allowance', starting ~week 3 of the design bar and running to the phase boundary (clamped to the parent weeks 1-5 window). F10: architect says procurement of commercial components 'would take longer than 2 weeks'.
G-P1-PROC-s7 | • P1-L8: procure Oracle 19 licence (mandatory for Unica+ MaxAI CDM) - folded into the drawn procurement window | SEGRO | ASSUMPTION |  | G-P1-PROC-s6 | 3 | 3 | 3 | 5 |  |  | 1 | 1 | 1 | [57 empty] | P1-L8 in spec_cost_model: 'Oracle 19 licence (mandatory for Unica+ MaxAI CDM) - procurement item, price not shared', RATE_MISSING at GBP 0; its basis notes it is 'absent from POAP Decisions & procurement lane (F10)'. Not drawn anywhere on slide 3, so its position inside the ~2.5 wk drawn procurement window is judgement.
G-P1-PROC-s8 | • P1-L9: procure Aerospike edition/licence (CDP caching, V6.3.0.35 disclosed, edition/licence unstated) - folded into the drawn procurement window | SEGRO | ASSUMPTION |  | G-P1-PROC-s6 | 3 | 3 | 3 | 5 |  |  | 1 | 1 | 1 | [57 empty] | P1-L9 in spec_cost_model: 'Aerospike edition/licence (CDP caching, V6.3.0.35 disclosed, edition/licence unstated) - procurement item', RATE_MISSING at GBP 0; its basis notes 'absent from POAP procurement lane (F10)'. Not drawn on slide 3, so its position inside the drawn procurement window is judgement.
G-P2-L1 | Azure foundations [P2-L1] | SEGRO | POAP-DRAWN |  |  | 6 | 5 | 6 | 10 | [5 empty] | 1 | 1 | 1 | 1 | 1 | [52 empty] | Slide 3 build item 1 bar x=4.55 w=2.22: 'Provision Azure Foundations ¦ Env Segregation ¦ Networking ¦ Subscriptions ¦ Private DNS ¦ VPN Tunnel Connectivity & workspaces'. Drawn from phase start; width 2.22 of the 4.31 full-phase bar = ~5.2 wk -> weeks 6-10 (F17 evidence corroborates: item 1 'drawn completing in roughly the first half of the build'). Cost line P2-L1 (2 FTE squad-shape ASSUMPTION).
G-P2-L1-s1 | • Stand up subscriptions and environment segregation (landing zones per env) | SEGRO | DERIVED |  |  | 6 | 1 | 6 | 6 | [5 empty] | 1 | [56 empty] | P2-L1 desc sub-items 'env segregation' + 'subscriptions' (slide 3 item 1: 'Env Segregation ... Subscriptions'); slide 7 'Environment Configuration Document ¦ Defines core Azure foundation'. First step: every other P2 resource deploys into these subscriptions.
G-P2-L1-s2 | • Networking build - VNets, subnets, peering across the segregated environments | SEGRO | DERIVED |  | G-P2-L1-s1 | 7 | 2 | 7 | 8 | [6 empty] | 1 | 1 | [54 empty] | P2-L1 desc sub-item 'networking' (slide 3 item 1 'Networking'). Positioned after subscriptions exist; note F17 tension - network segmentation decisions sit in the cyber design (item 4) drawn in parallel, so layout rework risk is live.
G-P2-L1-s3 | • Private DNS zones and workspaces provisioning | SEGRO | DERIVED |  | G-P2-L1-s2 | 9 | 1 | 9 | 9 | [8 empty] | 1 | [53 empty] | P2-L1 desc sub-items 'Private DNS' + 'workspaces' (slide 3 item 1 'Private DNS ... & workspaces'). Positioned after core networking - privatelink DNS zones bind to the VNet layout.
G-P2-L1-s4 | • VPN tunnel connectivity established; write up Environment build specification | SEGRO | DERIVED |  | G-P2-L1-s3 | 10 | 1 | 10 | 10 | [9 empty] | 1 | [52 empty] | P2-L1 desc sub-item 'VPN tunnel connectivity' (slide 3 item 1 'VPN Tunnel Connectivity'); slide 6 build doc 'Environment build specification' closes out the foundations bar (drawn ending ~week 10).
G-P2-L2 | AKS platform build & harden [P2-L2] | SEGRO | POAP-DRAWN |  | G-P2-L1 | 8 | 5 | 8 | 12 | [7 empty] | 1 | 1 | 1 | 1 | 1 | [50 empty] | Slide 3 build item 2 bar x=5.52 w=2.33: 'Build and harden AKS platform ¦ AKS cluster operational processes ¦ node pools ¦ RBAC ¦ Entra ID integration ¦ backup strategy'. Offset (5.52-4.55)=0.97 in = ~2.25 wk after phase start -> starts week 8; width 2.33 = ~5.4 wk -> weeks 8-12. Cost line P2-L2 (1 FTE ASSUMPTION). Sequencing: foundations (P2-L1) before AKS.
G-P2-L2-s1 | • Provision AKS cluster and node pools into the foundations networking | SEGRO | DERIVED |  |  | 8 | 1 | 8 | 8 | [7 empty] | 1 | [54 empty] | P2-L2 desc sub-item 'node pools' (slide 3 item 2 'node pools'); slide 7 'Kubernetes Cluster Configuration Document ¦ Define platform hosting setup'. Starts at the drawn item-2 bar start (x=5.52), once subscriptions/networking exist.
G-P2-L2-s2 | • RBAC and Entra ID integration onto the cluster | SEGRO | DERIVED |  | G-P2-L2-s1 | 9 | 1 | 9 | 9 | [8 empty] | 1 | [53 empty] | P2-L2 desc sub-items 'RBAC ¦ Entra ID integration' (slide 3 item 2 same phrases); slide 7 'Identity & Authentication Configuration Document ¦ Secures user & system access'. Identity wiring follows cluster existence.
G-P2-L2-s3 | • Harden cluster and stand up AKS cluster operational processes | SEGRO | DERIVED |  | G-P2-L2-s2 | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | P2-L2 desc sub-item 'AKS cluster operational processes' + bar title 'Build and harden AKS platform' (slide 3 item 2); slide 6 build doc 'Operational Runbook'. Hardening/ops maturity is the bulk of the bar after provisioning.
G-P2-L2-s4 | • Implement and document cluster backup strategy | SEGRO | DERIVED |  | G-P2-L2-s3 | 12 | 1 | 12 | 12 | [11 empty] | 1 | [50 empty] | P2-L2 desc sub-item 'backup strategy' (slide 3 item 2 'backup strategy'); slide 6 build doc 'Backup & Disaster Recovery Design'. Closes the drawn item-2 bar (~week 12).
G-P2-L3 | Shared platform services [P2-L3] | SEGRO | POAP-DRAWN |  | G-P2-L2 | 10 | 6 | 10 | 15 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | Slide 3 build item 3 bar x=6.48 w=2.39: 'Deploy shared platform services ¦ PostgreSQL ¦ SQL Server ¦ MongoDB/Cosmos ¦ Kafka ¦ Redis ¦ monitoring stack ¦ ingress controllers and cert management'. Offset (6.48-4.55)=1.93 in = ~4.5 wk -> starts week 10; width 2.39 = ~5.5 wk -> weeks 10-15 (clipped at phase end). Cost line P2-L3 (1.5 FTE ASSUMPTION, 8 named services). Sequencing: AKS (P2-L2) before shared services.
G-P2-L3-s1 | • Deploy database services - PostgreSQL, SQL Server, MongoDB/Cosmos | SEGRO | DERIVED |  |  | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | P2-L3 desc sub-items 'PostgreSQL ¦ SQL Server ¦ MongoDB/Cosmos' (slide 3 item 3 same phrases). Data stores first - downstream services and the HCL install both consume them.
G-P2-L3-s2 | • Deploy messaging and cache - Kafka, Redis | SEGRO | DERIVED |  | G-P2-L3-s1 | 12 | 1 | 12 | 12 | [11 empty] | 1 | [50 empty] | P2-L3 desc sub-items 'Kafka ¦ Redis' (slide 3 item 3 same phrases). Note P2-L17 basis: HCL's own matrix marks Event Hubs = N for UnO/CDP/Unica+ - the Kafka endpoint may be forced self-hosted on the cluster.
G-P2-L3-s3 | • Ingress controllers and certificate management | SEGRO | DERIVED |  | G-P2-L3-s2 | 13 | 1 | 13 | 13 | [12 empty] | 1 | [49 empty] | P2-L3 desc sub-item 'ingress controllers and cert management' (slide 3 item 3 same phrase); slide 6 build doc 'Secrets & certificate register'.
G-P2-L3-s4 | • Deploy monitoring stack across the shared services | SEGRO | DERIVED |  | G-P2-L3-s3 | 14 | 1 | 14 | 14 | [13 empty] | 1 | [48 empty] | P2-L3 desc sub-item 'monitoring stack' (slide 3 item 3 'monitoring stack'); slide 6 build doc 'Monitoring & Logging Design'. Late-bar position: monitoring wraps the services already deployed.
G-P2-L3-s5 | • Service integration wiring and configuration documentation | SEGRO | DERIVED |  | G-P2-L3-s4 | 15 | 1 | 15 | 15 | [14 empty] | 1 | [47 empty] | Slide 6 build docs 'Integration specification' + 'Configuration document*'; slide 7 'Integration Configuration Document ¦ Enables connectivity'. Closes the item-3 bar at phase end, ready for the HCL install (which follows sequentially, F2).
G-P2-L4 | Cyber security design [P2-L4] | SEGRO | POAP-DRAWN | F17 |  | 6 | 10 | 6 | 15 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | Slide 3 build item 4 bar x=4.55 w=4.32: 'Complete Cyber Security design ¦ Managed identities ¦ Key Vault integration ¦ secrets management ¦ network segmentation ¦ WAF ¦ API security ¦ privileged access controls' - drawn across the FULL 10-week build (same extent as the 'SEGRO 10 weeks' bar w=4.31) -> weeks 6-15. F17: architect view is this design should substantially PRECEDE foundations/networking ('c4 needs doing before ... c1,2,3, to avoid rework on the network layout'); the drawn geometry does the opposite. Cost line P2-L4 (0.5 FTE ASSUMPTION).
G-P2-L4-s1 | • Network segmentation design | SEGRO | DERIVED |  |  | 6 | 2 | 6 | 7 | [5 empty] | 1 | 1 | [55 empty] | P2-L4 desc sub-item 'network segmentation' (slide 3 item 4 'network segmentation'). Placed first within the drawn full-span bar because it feeds the foundations networking build (weeks 7-8) - the F17 rework risk is smallest if this lands earliest.
G-P2-L4-s2 | • Managed identities and privileged access controls design | SEGRO | DERIVED |  | G-P2-L4-s1 | 8 | 2 | 8 | 9 | [7 empty] | 1 | 1 | [53 empty] | P2-L4 desc sub-items 'managed identities' + 'privileged access controls' (slide 3 item 4 'Managed identities ... privileged access controls'); slide 7 'Identity & Authentication Configuration Document ¦ Secures user & system access'. Aligned with the AKS RBAC/Entra ID step (week 9).
G-P2-L4-s3 | • Key Vault integration and secrets management design | SEGRO | DERIVED |  | G-P2-L4-s2 | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | P2-L4 desc sub-items 'Key Vault integration' + 'secrets management' (slide 3 item 4 same phrases); slide 7 'Secrets Management Configuration Document ¦ Enables connectivity to systems' and 'Operational Support Configuration Document ¦ Protects credentials & certificates'; slide 6 'Secrets & certificate register'.
G-P2-L4-s4 | • WAF and API security design | SEGRO | DERIVED |  | G-P2-L4-s3 | 12 | 2 | 12 | 13 | [11 empty] | 1 | 1 | [49 empty] | P2-L4 desc sub-items 'WAF' + 'API security' (slide 3 item 4 'WAF ¦ API security'). Aligned with gateway commissioning; SEGRO principle - all integration via APIM with OAuth (P2-L21 basis).
G-P2-L4-s5 | • Consolidate and sign off the Security & access design document | SEGRO | DERIVED |  | G-P2-L4-s4 | 14 | 2 | 14 | 15 | [13 empty] | 1 | 1 | [47 empty] | Slide 6 build doc 'Security & access design'; bar title 'Complete Cyber Security design' (slide 3 item 4) - completion lands at the drawn bar end (week 15).
G-P2-L5 | Data mgmt & governance principles [P2-L5] | SEGRO | POAP-DRAWN |  |  | 6 | 10 | 6 | 15 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | Slide 3 build item 6 bar x=4.55 w=6.23: 'Data Mgmt and Governance Principles: Data classification ¦ Data ownership ¦ Data retention policies ¦ Data lineage ¦ Master data requirements ¦ Information architecture'. Drawn from phase start and OVERHANGING the SEGRO 10-wk bar (w=6.23 vs 4.31 - it extends ~4.5 wk into the HCL build window); clipped here to the P2 window weeks 6-15 owned by cost line P2-L5 (0.5 FTE ASSUMPTION). The overhang belongs to the P3 fragment if carried.
G-P2-L5-s1 | • Data classification scheme | SEGRO | DERIVED |  |  | 6 | 2 | 6 | 7 | [5 empty] | 1 | 1 | [55 empty] | P2-L5 desc sub-item 'classification' (slide 3 item 6 'Data classification'). First in the governance chain - classification drives retention and ownership decisions.
G-P2-L5-s2 | • Data ownership model | SEGRO | DERIVED |  | G-P2-L5-s1 | 8 | 2 | 8 | 9 | [7 empty] | 1 | 1 | [53 empty] | P2-L5 desc sub-item 'ownership' (slide 3 item 6 'Data ownership').
G-P2-L5-s3 | • Data retention policies | SEGRO | DERIVED |  | G-P2-L5-s2 | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | P2-L5 desc sub-item 'retention' (slide 3 item 6 'Data retention policies'). Follows classification/ownership; informs the database services being deployed weeks 10-11 (G-P2-L3-s1).
G-P2-L5-s4 | • Data lineage and master data requirements | SEGRO | DERIVED |  | G-P2-L5-s3 | 12 | 2 | 12 | 13 | [11 empty] | 1 | 1 | [49 empty] | P2-L5 desc sub-items 'lineage' + 'master data' (slide 3 item 6 'Data lineage ¦ Master data requirements').
G-P2-L5-s5 | • Information architecture consolidation; feed the Updated Systems matrix | SEGRO | DERIVED |  | G-P2-L5-s4 | 14 | 2 | 14 | 15 | [13 empty] | 1 | 1 | [47 empty] | P2-L5 desc sub-item 'information architecture' (slide 3 item 6 'Information architecture'); slide 6 build docs 'Updated Systems matrix' + 'Updated app landscape' are the natural landing artifacts. Closes the P2-owned portion of the drawn bar.
G-P2-L6 | Agent eval harness & observability (FND-4) [P2-L6] | SEGRO | ASSUMPTION | F13 |  | 7 | 9 | 7 | 15 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | NOT drawn anywhere on the POAP - F13: 'No agent evaluation harness / AI observability workstream anywhere in the POAP' (the HCL bar's generic 'observability integration' is the only adjacent text). Window is the cost model's implied shape: platform.json FND-4 = 20 pd over 9 wk (0.44 FTE), placed weeks 7-15 so the harness completes with the build and gates the first pilots. Quantity source itself labels the task ASSUMPTION.
G-P2-L6-s1 | • Define golden sets for agent output evaluation | SEGRO | ASSUMPTION |  |  | 7 | 2 | 7 | 8 | [6 empty] | 1 | 1 | [54 empty] | P2-L6 desc sub-item 'golden sets' (spec_cost_model: 'golden sets, scored promotion gates, run-trace logging, eval dashboard (absent from POAP, F13)'). Design-first step, no infra dependency.
G-P2-L6-s2 | • Build scored promotion gates | SEGRO | ASSUMPTION |  | G-P2-L6-s1 | 9 | 2 | 9 | 10 | [8 empty] | 1 | 1 | [52 empty] | P2-L6 desc sub-item 'scored promotion gates' (spec_cost_model P2-L6). F13: SEGRO's counter-proposal makes the eval-harness baseline 'a promotion gate for the first pilot'.
G-P2-L6-s3 | • Integrate run-trace logging into the platform observability stack | SEGRO | ASSUMPTION |  | G-P2-L6-s2 | 11 | 2 | 11 | 12 | [10 empty] | 1 | 1 | [50 empty] | P2-L6 desc sub-item 'run-trace logging' (spec_cost_model P2-L6); positioned after the monitoring stack starts landing (G-P2-L3) - the only drawn adjacency is the HCL bar's 'observability integration' (F13 evidence).
G-P2-L6-s4 | • Stand up eval dashboard and run baseline evaluations | SEGRO | ASSUMPTION |  | G-P2-L6-s3 | 13 | 3 | 13 | 15 | [12 empty] | 1 | 1 | 1 | [47 empty] | P2-L6 desc sub-item 'eval dashboard' (spec_cost_model P2-L6). Completes at week 15 so the baseline exists before the HCL install/test phases consume it.
G-P2-L7 | Project/delivery management [P2-L7] | SEGRO | POAP-DRAWN |  |  | 6 | 10 | 6 | 15 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | Spans the drawn 'SEGRO 10 weeks' bar (slide 3, x=4.55 w=4.31) end-to-end - the PM allocation itself is the cost model's ASSUMPTION ('1 PM on a 6-workstream build phase', P2-L7); the window is the drawn phase bar. The bar carries the annotation 'To be validated based on Arch workshop' (F14 context).
G-P2-L7-s1 | • Mobilise the build squad and baseline the 10-week plan | SEGRO | DERIVED |  |  | 6 | 1 | 6 | 6 | [5 empty] | 1 | [56 empty] | Slide 3 'SEGRO 10 weeks' bar start + annotation 'To be validated based on Arch workshop' (x=6.85) - the plan enters the build unvalidated, so baselining is the first PM act.
G-P2-L7-s2 | • Coordinate build workstreams 1-6 and track build-document production | SEGRO | DERIVED |  | G-P2-L7-s1 | 7 | 4 | 7 | 10 | [6 empty] | 1 | 1 | 1 | 1 | [52 empty] | Slide 3 numbered build items 1-6 within lane C; slide 6 build docs list ('Environment build specification ... Operational Runbook') is the deliverable register the PM tracks.
G-P2-L7-s3 | • Progress/RAID management through the back half of the build; prepare HCL install handover | SEGRO | DERIVED |  | G-P2-L7-s2 | 11 | 4 | 11 | 14 | [10 empty] | 1 | 1 | 1 | 1 | [48 empty] | Slide 3: 'HCL 6 weeks' bar (x=8.91) starts immediately after the SEGRO bar ends (x=8.86) - drawn strictly sequential (F2 evidence), so handover readiness is the PM focus in the closing weeks.
G-P2-L7-s4 | • Close the SEGRO build phase and hand over to the HCL install | SEGRO | DERIVED |  | G-P2-L7-s3 | 15 | 1 | 15 | 15 | [14 empty] | 1 | [47 empty] | End of the drawn 'SEGRO 10 weeks' bar; slide 6 build doc 'Service transition pack' (listed twice on slide 6) is the closing handover artifact.
G-P2-L8 | Pen-test booking & remediation window [P2-L8] | SEGRO | ASSUMPTION | F7 |  | 13 | 3 | 13 | 15 | [12 empty] | 1 | 1 | 1 | [47 empty] | NOT drawn on the POAP - F7: booking 'is not shown'; P2-L8 basis: "F7 recommendation: add a 'book pen test' task in October; POAP shows none". Window ASSUMPTION per F7 recommendation ('Add a book pen test task in October'): October 2026 = weeks 13-16 (gantt_timeline month_headers), placed weeks 13-15 inside P2. 2 days procurement admin (cost model); F7: CREST firms quote 4-8 wk booking lead times and the drawn 'Pen Testing' sits early Dec (x=11.30).
G-P2-L8-s1 | • Scope the CREST pen test (cloud platform scope) and issue RFQ | SEGRO | ASSUMPTION |  |  | 13 | 1 | 13 | 13 | [12 empty] | 1 | [49 empty] | F7: 'Pen testing is inside the 4-week December window' and slide 9 requires a 'Penetration Test Report' - scope must be fixed before booking. Early-October start per F7 'bookable only if procurement of the pen test starts by ~October'.
G-P2-L8-s2 | • Confirm the booking for the December test window | SEGRO | ASSUMPTION |  | G-P2-L8-s1 | 14 | 1 | 14 | 14 | [13 empty] | 1 | [48 empty] | F7: 'CREST-accredited test firms commonly quote multi-week booking lead times (4-8 weeks as a planning assumption)' - booking mid-October + 4-8 wk lead lands the engagement in the drawn early-Dec 'Pen Testing' slot (x=11.30, P4 weeks 22-25).
G-P2-L8-s3 | • Reserve a named remediation + retest window in early January before go/no-go | SEGRO | ASSUMPTION |  | G-P2-L8-s2 | 15 | 1 | 15 | 15 | [14 empty] | 1 | [47 empty] | F7 recommendation: 'hold a named remediation window in early Jan before go/no-go' ('Go / No Go decision' drawn x=13.99, mid-Jan). Scheduling only - execution is P5-L4 in the deploy fragment.
G-P2-L27 | DevSecOps automation [P2-L27] | SEGRO | ASSUMPTION | F19 |  | 6 | 10 | 6 | 15 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | NO drawn bar - that absence IS F19: 'No DevSecOps automation workstream exists anywhere in the POAP'; slide 7 names a 'CI/CD Configuration Document ¦ Automates build & deploy' but 'no build task produces the pipeline that document would describe'. Window is the cost model's implied shape (judgement): P2-L27 = 0.6 FTE x 10 wk = 30 pd across the full build -> weeks 6-15, starting with foundations so IaC codifies them from day one. Trigger: senior architect review 18 Jul 2026.
G-P2-L27-s1 | • IaC pipelines for the Azure foundations | SEGRO | ASSUMPTION |  |  | 6 | 2 | 6 | 7 | [5 empty] | 1 | 1 | [55 empty] | P2-L27 desc sub-item 'IaC pipelines' (spec_cost_model: 'IaC pipelines, policy-as-code, image scanning, CI/CD for infra + agent deployment'). Placed alongside G-P2-L1 so foundations are provisioned as code rather than hand-built (F19: 'hand-built environments and manual deploys plausibly move cost, quality and go-live risk materially').
G-P2-L27-s2 | • Policy-as-code guardrails across subscriptions and the cluster | SEGRO | ASSUMPTION |  | G-P2-L27-s1 | 8 | 2 | 8 | 9 | [7 empty] | 1 | 1 | [53 empty] | P2-L27 desc sub-item 'policy-as-code' (spec_cost_model P2-L27). Follows the IaC baseline; aligned with the AKS build start (week 8).
G-P2-L27-s3 | • Image scanning and container registry hygiene | SEGRO | ASSUMPTION |  | G-P2-L27-s2 | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | P2-L27 desc sub-item 'image scanning' (spec_cost_model P2-L27). Positioned as workloads start landing on the cluster (shared services deploy from week 10).
G-P2-L27-s4 | • CI/CD pipelines for infra and agent deployment | SEGRO | ASSUMPTION |  | G-P2-L27-s3 | 12 | 2 | 12 | 13 | [11 empty] | 1 | 1 | [49 empty] | P2-L27 desc sub-item 'CI/CD for infra + agent deployment' (spec_cost_model P2-L27); slide 7 'CI/CD Configuration Document ¦ Automates build & deploy' is the deliverable this pipeline work substantiates. Boundary note per P2-L27 basis: this BUILDS the pipelines; P5-L2 executes the deploy-phase cutover.
G-P2-L27-s5 | • Author the CI/CD Configuration Document and hand pipelines to the run team | SEGRO | ASSUMPTION |  | G-P2-L27-s4 | 14 | 2 | 14 | 15 | [13 empty] | 1 | 1 | [47 empty] | Slide 7 configuration doc: 'CI/CD Configuration Document ¦ Automates build & deploy' - the only CI/CD reference in the whole deck (F19 evidence); the document is written last, describing the pipelines built in s1-s4.
G-P2-AZURE | Azure services commissioning window [P2-L9..P2-L26] | Azure | ASSUMPTION |  |  | 6 | 10 | 6 | 15 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | Grouped commissioning window for the 18 Azure SKU cost lines P2-L9..P2-L26. The SKUs are named on drawn slide-3 build items 1-4 (Private DNS/VPN in item 1; node pools in item 2; PostgreSQL/SQL Server/MongoDB/Cosmos/Kafka/Redis/monitoring in item 3; Key Vault/WAF in item 4), but no consumption bar is drawn - the window and its '50% ramp' ('envs commissioned progressively', P2-L9 basis) are the cost model's ASSUMPTION. Task shows the P2 portion (weeks 6-15) of the longer ~22-wk commissioning ramp; step positions are grouped SKU-family tiles, a sequencing simplification of the progressive ramp.
G-P2-AZURE-s1 | • AKS cluster + node pools commissioned (AKS mgmt fee, D4s_v5 worker pools; ARO branch: D4ds_v5 workers, OpenShift licence uplift, 3x D8s_v5 masters) | Azure | ASSUMPTION |  |  | 6 | 2 | 6 | 7 | [5 empty] | 1 | 1 | [55 empty] | Covers P2-L9 'AKS cluster management fee (Standard tier)', P2-L10 'AKS worker node pools - D4s_v5 class (M)', P2-L10b 'ARO worker node pools - D4ds_v5 class', P2-L11 'ARO OpenShift worker licence uplift', P2-L12 'ARO control-plane nodes - 3x D8s_v5'. Slide 3 item 2 names 'node pools'. Positioned first: cluster meters start with the foundations so the platform exists before the drawn AKS-hardening bar begins (week 8); ARO lines price the open 'KDD: TCO AKS v ARO' branch (F3 context in P2-L11 basis).
G-P2-AZURE-s2 | • Data services commissioned - PostgreSQL Flexible Server, PostgreSQL storage, Azure SQL Database, Cosmos DB serverless | Azure | ASSUMPTION |  | G-P2-AZURE-s1 | 8 | 2 | 8 | 9 | [7 empty] | 1 | 1 | [53 empty] | Covers P2-L13 'PostgreSQL Flexible Server GP 4-vCore', P2-L14 'PostgreSQL provisioned storage', P2-L15 'Azure SQL Database GP 4-vCore', P2-L16 'Cosmos DB serverless (MongoDB-API workloads)'. Slide 3 item 3 names 'PostgreSQL ¦ SQL Server ¦ MongoDB/Cosmos'. Positioned ahead of the shared-services deploy bar (weeks 10-15) that configures them.
G-P2-AZURE-s3 | • Messaging + cache commissioned - Event Hubs Standard (Kafka endpoint), Azure Cache for Redis | Azure | ASSUMPTION |  | G-P2-AZURE-s2 | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | Covers P2-L17 'Event Hubs Standard (Kafka endpoint)', P2-L18 'Azure Cache for Redis Standard C1'. Slide 3 item 3 names 'Kafka ¦ Redis'. Aligned with the drawn shared-services bar start (week 10). P2-L17 is the INDICATIVE Azure-native branch - 'HCL's own matrix marks Event Hubs = N for UnO/CDP/Unica+'. Status ASSUMPTION: the SKU list (text) is sourced from the cost-model line descs, but the commissioning position within the P2 window is a grouped SKU-family sequencing judgement (no consumption bar is drawn).
G-P2-AZURE-s4 | • Gateway + network commissioned - App Gateway WAF_v2 (gateways + capacity units), APIM Standard, VPN Gateway VpnGw1, Private DNS zones | Azure | ASSUMPTION |  | G-P2-AZURE-s3 | 12 | 2 | 12 | 13 | [11 empty] | 1 | 1 | [49 empty] | Covers P2-L19 'Application Gateway WAF_v2 - fixed gateway fee', P2-L20 'Application Gateway WAF_v2 - capacity units', P2-L21 'API Management Standard unit', P2-L22 'VPN Gateway VpnGw1', P2-L23 'Azure Private DNS zones'. Slide 3 item 1 names 'Private DNS ¦ VPN Tunnel Connectivity' (drawn weeks 6-10) and item 4 names 'WAF ¦ API security' - grouped here as one SKU-family tile aligned with the WAF/API security design step (weeks 12-13); DNS/VPN meters in practice start earlier with foundations.
G-P2-AZURE-s5 | • Observability + security commissioned - Log Analytics ingestion, Key Vault operations, Defender for Cloud | Azure | ASSUMPTION |  | G-P2-AZURE-s4 | 14 | 2 | 14 | 15 | [13 empty] | 1 | 1 | [47 empty] | Covers P2-L24 'Log Analytics ingestion during build (monitoring stack commissioning)', P2-L25 'Key Vault operations', P2-L26 'Microsoft Defender for Cloud workload protection'. Slide 3 item 3 names 'monitoring stack'; item 4 names 'Key Vault integration'. Positioned with the monitoring-stack deploy step (week 14). P2-L26 is RATE_MISSING at GBP 0 until priced (cost model).
G-P3-L1 | Build - HCL [P3-L1] | HCL | POAP-DRAWN | F2 |  | 16 | 6 | 16 | 21 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [41 empty] | Slide 3 'HCL 6 weeks' bar (x=8.91 w=1.87) with text block 'HCL install and configure base ¦ UnO ¦ platform and TX components (DX and Foundry) onto AKS, including: ¦ platform validation, ¦ connectivity and ¦ observability integration' (x=8.91 y=2.35). Drawn strictly sequential after the 'SEGRO 10 weeks' bar (x=4.55 w=4.31, ends x=8.86) - no overlap drawn (F2). Window = P3 weeks 16-21 per gantt_timeline.
G-P3-L1-s1 | • Install and configure base UnO platform onto AKS | HCL | ASSUMPTION |  |  | 16 | 2 | 16 | 17 | [15 empty] | 1 | 1 | [45 empty] | Slide 3: 'HCL install and configure base ¦ UnO ¦ platform and TX components (DX and Foundry) onto AKS'. Base platform install is the first listed item, so placed at the window start; the POAP draws one undifferentiated 6-wk bar with no task breakdown (F20), so internal sequencing is derived from the listed order. Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L1-s2 | • Install TX components (DX and Foundry) onto AKS | HCL | ASSUMPTION |  | G-P3-L1-s1 | 18 | 1 | 18 | 18 | [17 empty] | 1 | [44 empty] | Slide 3: 'platform and TX components (DX and Foundry) onto AKS' - second listed install item, so positioned after the base UnO install within the drawn bar. Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L1-s3 | • Platform validation of the installed UnO/TX stack | HCL | ASSUMPTION |  | G-P3-L1-s2 | 19 | 1 | 19 | 19 | [18 empty] | 1 | [43 empty] | Slide 3: 'including: ¦ platform validation' - validation can only follow the install, so positioned after s1/s2 in the drawn window. Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L1-s4 | • Connectivity configuration to SEGRO platform services | HCL | ASSUMPTION |  | G-P3-L1-s3 | 20 | 1 | 20 | 20 | [19 empty] | 1 | [42 empty] | Slide 3: 'connectivity' - listed after platform validation in the bar text, so positioned late in the window. Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L1-s5 | • Observability integration into the SEGRO monitoring stack | HCL | ASSUMPTION |  | G-P3-L1-s4 | 21 | 1 | 21 | 21 | [20 empty] | 1 | [41 empty] | Slide 3: 'observability integration' - final listed item in the HCL install text, so closes the drawn window at week 21 ('Build phase complete' milestone x=10.89). Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L2 | Build - HCL [P3-L2] | HCL | POAP-DRAWN |  |  | 16 | 6 | 16 | 21 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [41 empty] | Slide 3 second HCL text block inside the drawn 'HCL 6 weeks' bar: 'HCL deploy Unica+ & CDP services, configure: ¦ routing, ¦ application gateways, ¦ certificates' (x=8.91 y=3.45, same x-extent as the bar). Cost line P3-L2. Window = P3 weeks 16-21 per gantt_timeline.
G-P3-L2-s1 | • Deploy Unica+ services | HCL | ASSUMPTION |  |  | 16 | 2 | 16 | 17 | [15 empty] | 1 | 1 | [45 empty] | Slide 3: 'HCL deploy Unica+ & CDP services' - Unica+ named first; deployment of the services precedes their configuration items, so placed at the window start. The bar itself has no task breakdown (F20). Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L2-s2 | • Deploy CDP services | HCL | ASSUMPTION |  | G-P3-L2-s1 | 18 | 1 | 18 | 18 | [17 empty] | 1 | [44 empty] | Slide 3: 'HCL deploy Unica+ & CDP services' - CDP named second in the deploy pair; positioned after the Unica+ deploy within the drawn window. Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L2-s3 | • Configure routing | HCL | ASSUMPTION |  | G-P3-L2-s2 | 19 | 1 | 19 | 19 | [18 empty] | 1 | [43 empty] | Slide 3: 'configure: ¦ routing' - first listed configure item, so follows the service deploys. Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L2-s4 | • Configure application gateways | HCL | ASSUMPTION |  | G-P3-L2-s3 | 20 | 1 | 20 | 20 | [19 empty] | 1 | [42 empty] | Slide 3: 'configure: ... ¦ application gateways' - second listed configure item in the drawn text. Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L2-s5 | • Configure certificates and confirm end-to-end service exposure | HCL | ASSUMPTION |  | G-P3-L2-s4 | 21 | 1 | 21 | 21 | [20 empty] | 1 | [41 empty] | Slide 3: 'configure: ... ¦ certificates' - final listed configure item, closing the drawn window at week 21. Status ASSUMPTION: the step ORDER follows the slide-3 sub-item sequence, but the week boundaries are a judgement split of a single undifferentiated drawn HCL bar (no per-sub-item durations are drawn).
G-P3-L3 | Build - HCL [P3-L3] | SEGRO | ASSUMPTION |  |  | 16 | 6 | 16 | 21 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [41 empty] | Cost line P3-L3: 'SEGRO platform/security engineers supporting HCL install (access, networking, reviews)' - support is co-extensive with the drawn 'HCL 6 weeks' bar (slide 3 x=8.91 w=1.87), a vendor install on a SEGRO-run cluster (cost-line basis: 'vendor installs on a SEGRO-run cluster always consume platform-team time (RBAC, network paths, secrets)'). Window = the drawn P3 weeks 16-21. Status ASSUMPTION: this SEGRO support line has NO bar of its own on the POAP - it is placed co-extensive with the drawn HCL/Testing bar by judgement (the support is real and costed, but its window is inferred, not drawn).
G-P3-L3-s1 | • Grant HCL access - RBAC, identities, secrets paths | SEGRO | ASSUMPTION |  |  | 16 | 1 | 16 | 16 | [15 empty] | 1 | [46 empty] | Cost line P3-L3 '(access, ...)' and its basis 'RBAC, network paths, secrets'; slide 3 SEGRO build item 2 built 'RBAC ¦ Entra ID integration'. Access must exist before HCL can install, so placed at the window start. Status ASSUMPTION: step position is a judgement split within the inferred support window (no per-step boundary is drawn).
G-P3-L3-s2 | • Open network paths and firewall rules for the HCL install | SEGRO | ASSUMPTION |  | G-P3-L3-s1 | 17 | 1 | 17 | 17 | [16 empty] | 1 | [45 empty] | Cost line P3-L3 '(... networking ...)' and basis 'network paths'; positioned early because the slide-3 install text needs 'connectivity' to SEGRO services. Status ASSUMPTION: step position is a judgement split within the inferred support window (no per-step boundary is drawn).
G-P3-L3-s3 | • Ongoing platform support during the UnO/TX and Unica+/CDP installs | SEGRO | ASSUMPTION |  | G-P3-L3-s2 | 18 | 2 | 18 | 19 | [17 empty] | 1 | 1 | [43 empty] | Cost line P3-L3 desc 'SEGRO platform/security engineers supporting HCL install' - continuous support through the middle of the drawn HCL bar while both install blocks run. Status ASSUMPTION: step position is a judgement split within the inferred support window (no per-step boundary is drawn).
G-P3-L3-s4 | • Security and configuration reviews of HCL deployments | SEGRO | ASSUMPTION |  | G-P3-L3-s3 | 20 | 1 | 20 | 20 | [19 empty] | 1 | [42 empty] | Cost line P3-L3 '(... reviews)' - reviews follow the deployed components, so positioned late in the window. Status ASSUMPTION: step position is a judgement split within the inferred support window (no per-step boundary is drawn).
G-P3-L3-s5 | • Validate observability integration into the SEGRO monitoring stack at handover to test | SEGRO | ASSUMPTION |  | G-P3-L3-s4 | 21 | 1 | 21 | 21 | [20 empty] | 1 | [41 empty] | Slide 3 HCL install text ends 'observability integration'; slide 3 SEGRO build item 3 deployed the 'monitoring stack' - SEGRO-side validation closes the window at 'Build phase complete' (x=10.89). Status ASSUMPTION: step position is a judgement split within the inferred support window (no per-step boundary is drawn).
G-P3-LIC | Build - HCL (licences & procurement) | HCL | ASSUMPTION | F10 |  | 16 | 6 | 16 | 21 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [41 empty] | Folds the one-off/licence cost lines P3-L4..P3-L8 (HCL UnO / Unica+ / CDP / DX licences, all RATE_MISSING at GBP 0 'until contract shared', plus the MinIO EOL remediation package). None of these is drawn on the POAP - licence/procurement items are absent from the Decisions & procurement lane (F10) - so the window is an ASSUMPTION aligned to the P3 phase (weeks 16-21) whose install these licences must precede or accompany. Steps are tiled nominally; in practice the commercial actions run in parallel.
G-P3-LIC-s1 | • Execute HCL UnO platform licence/subscription - initial year (P3-L4) | HCL | ASSUMPTION |  |  | 16 | 1 | 16 | 16 | [15 empty] | 1 | [46 empty] | P3-L4: 'HCL UnO platform licence/subscription - initial year', RATE_MISSING - 'HCL contract pricing not shared with SEGRO'. Placed at the window start because the UnO licence gates the base UnO install (G-P3-L1-s1); no procurement bar is drawn for it (F10). Position is judgement.
G-P3-LIC-s2 | • Execute HCL Unica+ licence/subscription - initial year (P3-L5) | HCL | ASSUMPTION |  |  | 17 | 1 | 17 | 17 | [16 empty] | 1 | [45 empty] | P3-L5: 'HCL Unica+ licence/subscription - initial year', RATE_MISSING ('As P3-L4'). Must precede the Unica+ deploy (G-P3-L2); not drawn anywhere on the POAP (F10). Position is judgement.
G-P3-LIC-s3 | • Execute HCL CDP licence/subscription - initial year (P3-L6) | HCL | ASSUMPTION |  |  | 18 | 1 | 18 | 18 | [17 empty] | 1 | [44 empty] | P3-L6: 'HCL CDP licence/subscription - initial year', RATE_MISSING; its basis notes 'AKS x CDP = N in HCL's own matrix - CDP scope interacts with the Platform toggle (F3)'. Must precede the CDP deploy (G-P3-L2-s2); not drawn (F10). Position is judgement.
G-P3-LIC-s4 | • Execute HCL DX licence/subscription - initial year (P3-L7) | HCL | ASSUMPTION |  |  | 19 | 1 | 19 | 19 | [18 empty] | 1 | [43 empty] | P3-L7: 'HCL DX licence/subscription - initial year', RATE_MISSING ('As P3-L4'). Must precede/accompany the TX components (DX and Foundry) install (G-P3-L1-s2); not drawn (F10). Position is judgement.
G-P3-LIC-s5 | • MinIO EOL remediation - technical remediation of the CDP-mandated MinIO v5.0.15 dependency (P3-L8) | HCL | ASSUMPTION |  | G-P3-LIC-s3 | 20 | 2 | 20 | 21 | [19 empty] | 1 | 1 | [41 empty] | P3-L8: 'MinIO EOL remediation (community edition EOL Apr 2026; HCL: ‘Do not assume replaceable’)' - its basis: 'CDP mandates MinIO v5.0.15, community edition EOL upstream Apr 2026, Azure First tab walks back Blob substitution. Absent from POAP procurement lane (F10)'. A real technical remediation step, not just a commercial line - placed at the tail of the window after the CDP deploy exists to remediate against. Position and duration are judgement.
G-P4-L1 | Testing [P4-L1] | SEGRO | POAP-DRAWN | F1 |  | 22 | 4 | 22 | 25 | [21 empty] | 1 | 1 | 1 | 1 | [37 empty] | Slide 3: 'System Integration Testing (SIT)' x=11.30 w=1.63 - ends x=12.93, i.e. the full Testing bar (x=11.19-12.9) = weeks 22-25. Cost line P4-L1 'System Integration Testing - test engineers'. Straddles Christmas weeks 24-25 (Christmas marker x=12.91; F1 peak-leave compression).
G-P4-L1-s1 | • SIT test-case preparation and environment shakedown | SEGRO | DERIVED |  |  | 22 | 1 | 22 | 22 | [21 empty] | 1 | [40 empty] | Slide 9: '* Each report should document test cases, evidence, results, & any resolutions made' - test cases must exist before execution, so preparation opens the drawn SIT item (x=11.30, start of the Testing bar).
G-P4-L1-s2 | • Execute SIT across the integrated UnO/TX/Unica+/CDP + Azure stack | SEGRO | DERIVED |  | G-P4-L1-s1 | 23 | 1 | 23 | 23 | [22 empty] | 1 | [39 empty] | Slide 9 names an 'SIT report*' deliverable; execution follows preparation within the drawn weeks-22-25 SIT item.
G-P4-L1-s3 | • Regression testing - falls in Christmas week | SEGRO | DERIVED |  | G-P4-L1-s2 | 24 | 1 | 24 | 24 | [23 empty] | 1 | [38 empty] | Slide 9 names a 'Regression test report*' deliverable; as drawn this lands in week 24 (Christmas marker x=12.91 sits at the tail of the Testing bar - F1 peak-leave compression, preserved as drawn).
G-P4-L1-s4 | • Compile SIT report and regression test report with test cases, evidence, results and resolutions | SEGRO | DERIVED |  | G-P4-L1-s3 | 25 | 1 | 25 | 25 | [24 empty] | 1 | [37 empty] | Slide 9: 'Regression test report*' + 'SIT report*' + '* Each report should document test cases, evidence, results, & any resolutions made' - reporting closes the drawn window at 'Test phase complete' (x=12.68).
G-P4-L2 | Testing [P4-L2] | SEGRO | POAP-DRAWN | F1 |  | 22 | 4 | 22 | 25 | [21 empty] | 1 | 1 | 1 | 1 | [37 empty] | Cost line P4-L2 'Test management - plan, defect register, release readiness' - co-extensive with the drawn Testing bar (x=11.19-12.9, weeks 22-25); its deliverables are named on slide 9 ('Defect register & resolution log', 'UAT plan & sign off*', 'Production readiness assessment'). Straddles Christmas weeks 24-25 (F1).
G-P4-L2-s1 | • Issue UAT plan and test-phase plan | SEGRO | DERIVED |  |  | 22 | 1 | 22 | 22 | [21 empty] | 1 | [40 empty] | Slide 9: 'UAT plan & sign off*' - the plan half must precede UAT execution (drawn from week 23), so it opens the window.
G-P4-L2-s2 | • Stand up and run the defect register | SEGRO | DERIVED |  | G-P4-L2-s1 | 23 | 1 | 23 | 23 | [22 empty] | 1 | [39 empty] | Slide 9: 'Defect register & resolution log' - the register operates once SIT execution produces defects (G-P4-L1-s2, week 23).
G-P4-L2-s3 | • Defect triage and resolution-log maintenance across the Christmas weeks | SEGRO | DERIVED |  | G-P4-L2-s2 | 24 | 1 | 24 | 24 | [23 empty] | 1 | [38 empty] | Slide 9: '... & resolution log'; as drawn this triage load sits in week 24 with the Christmas marker (x=12.91) at the bar tail - F1 compression, preserved as drawn.
G-P4-L2-s4 | • Production readiness assessment input and release-readiness close-out | SEGRO | DERIVED |  | G-P4-L2-s3 | 25 | 1 | 25 | 25 | [24 empty] | 1 | [37 empty] | Slide 9: 'Production readiness assessment' + 'Go-Live Readiness / Go-No Go Approval' - readiness outputs close the phase at 'Test phase complete' (x=12.68).
G-P4-L3 | Testing [P4-L3] | ThirdParty | POAP-DRAWN | F7, F1 |  | 22 | 3 | 22 | 24 | [21 empty] | 1 | 1 | 1 | [38 empty] | Slide 3: 'Pen Testing' x=11.30 w=1.16 - ends x=12.46, i.e. weeks 22-24 at the 0.4275 in/week Testing-bar scale. Cost line P4-L3 'CREST penetration test engagement (cloud platform scope)' (~10 tester-days INDICATIVE). F7: CREST firms quote 4-8 wk booking lead times and remediation + retest must land before the January go/no-go - no booking task or remediation window is drawn. Tail of the drawn item touches Christmas week 24 (F1).
G-P4-L3-s1 | • Scoping and rules of engagement with the CREST firm | ThirdParty | DERIVED |  |  | 22 | 1 | 22 | 22 | [21 empty] | 1 | [40 empty] | P4-L3 desc 'CREST penetration test engagement (cloud platform scope)' - scoping opens the engagement at the start of the drawn 'Pen Testing' item (x=11.30). F7 notes the booking itself needed procurement 'by ~October' (carried as P2-L8, outside this fragment).
G-P4-L3-s2 | • Penetration test execution against the cloud platform | ThirdParty | DERIVED |  | G-P4-L3-s1 | 23 | 1 | 23 | 23 | [22 empty] | 1 | [39 empty] | Slide 3: 'Pen Testing' (x=11.30 w=1.16) - the ~10-tester-day execution sits in the middle of the drawn item.
G-P4-L3-s3 | • Penetration Test Report delivery | ThirdParty | DERIVED |  | G-P4-L3-s2 | 24 | 1 | 24 | 24 | [23 empty] | 1 | [38 empty] | Slide 9 names a 'Penetration Test Report' deliverable - reporting closes the drawn pen-test item in week 24. F7: remediation + retest before the Jan go/no-go has no drawn window (remediation costed at P5-L4, outside this fragment).
G-P4-L4 | Testing [P4-L4] | SEGRO | POAP-DRAWN | F1 |  | 23 | 3 | 23 | 25 | [22 empty] | 1 | 1 | 1 | [37 empty] | Slide 3: 'UAT & release readiness' x=11.90 w=1.07 - starts ~1.7 weeks into the Testing bar and runs to its tail, i.e. weeks 23-25. Cost line P4-L4 'UAT coordination & business-readiness liaison (BA)' (business-user UAT time itself is NOT costed, per the cost-line basis). Straddles Christmas weeks 24-25 (F1) - UAT lands exactly on peak leave.
G-P4-L4-s1 | • UAT coordination - business scenarios, user scheduling, entry criteria | SEGRO | DERIVED |  |  | 23 | 1 | 23 | 23 | [22 empty] | 1 | [39 empty] | Slide 3: 'UAT & release readiness' (x=11.90) + P4-L4 desc 'UAT coordination & business-readiness liaison (BA)' - coordination opens the drawn item; the UAT plan comes from G-P4-L2-s1.
G-P4-L4-s2 | • UAT execution support - Christmas week | SEGRO | DERIVED |  | G-P4-L4-s1 | 24 | 1 | 24 | 24 | [23 empty] | 1 | [38 empty] | Slide 3 draws UAT running through the bar tail where the 'Christmas' marker sits (x=12.91) - business-user execution falls in week 24, peak leave (F1), preserved as drawn.
G-P4-L4-s3 | • UAT sign off and release-readiness confirmation | SEGRO | DERIVED |  | G-P4-L4-s2 | 25 | 1 | 25 | 25 | [24 empty] | 1 | [37 empty] | Slide 9: 'UAT plan & sign off*' - the sign-off half closes the drawn item at 'Test phase complete' (x=12.68, adjacent to the Christmas marker x=12.91).
G-P4-L5 | Testing [P4-L5] | SEGRO | POAP-DRAWN | F1 |  | 23 | 3 | 23 | 25 | [22 empty] | 1 | 1 | 1 | [37 empty] | Slide 3: 'Performance testing' x=11.88 w=1.07 - starts ~1.6 weeks into the Testing bar and runs to its tail, i.e. weeks 23-25. Cost line P4-L5 'Performance & resilience testing (incl. DR test execution - DR Test Report is a named deliverable)'. Straddles Christmas weeks 24-25 (F1).
G-P4-L5-s1 | • Performance test execution against the integrated platform | SEGRO | DERIVED |  |  | 23 | 1 | 23 | 23 | [22 empty] | 1 | [39 empty] | Slide 3: 'Performance testing' (x=11.88) - execution opens the drawn item once SIT is under way.
G-P4-L5-s2 | • Resilience testing and report drafting | SEGRO | DERIVED |  | G-P4-L5-s1 | 24 | 1 | 24 | 24 | [23 empty] | 1 | [38 empty] | Slide 9: 'Performance resilience test report*' - the resilience half of the named deliverable; as drawn it lands in Christmas week 24 (F1), preserved as drawn.
G-P4-L5-s3 | • DR test execution and Disaster Recovery Test Report | SEGRO | DERIVED |  | G-P4-L5-s2 | 25 | 1 | 25 | 25 | [24 empty] | 1 | [37 empty] | Slide 9: 'Disaster Recovery Test Report' is a named testing deliverable; P4-L5 basis costs its execution while noting 'DR infrastructure itself remains uncosted' - the report closes the drawn window.
G-P4-L6 | Testing [P4-L6] | HCL | ASSUMPTION | F23, F1 |  | 22 | 4 | 22 | 25 | [21 empty] | 1 | 1 | 1 | 1 | [37 empty] | Cost line P4-L6 'HCL defect-fix & SIT/UAT support (their stack, their fixes)'. No defect-fix window is drawn anywhere: F23 - 'the plan draws SIT, pen test, UAT and performance testing back-to-back with no fix-and-retest loop before Test phase complete'; architect: 'There does not seem to any fix time for iusses from HCL'. Window is an ASSUMPTION co-extensive with the drawn Testing bar (weeks 22-25) because vendor-stack defects arise across all four drawn test items. Also F23: 'green field and brown field would need to tested' - no greenfield/brownfield split is drawn in the test scope. Spans Christmas weeks 24-25 (F1).
G-P4-L6-s1 | • HCL support to SIT on the vendor stack | HCL | ASSUMPTION |  |  | 22 | 1 | 22 | 22 | [21 empty] | 1 | [40 empty] | P4-L6 desc 'HCL defect-fix & SIT/UAT support (their stack, their fixes)' - support starts when SIT starts (drawn x=11.30, week 22). No HCL support bar is drawn; position is judgement.
G-P4-L6-s2 | • HCL defect fixing on UnO/TX/Unica+/CDP components | HCL | ASSUMPTION |  | G-P4-L6-s1 | 23 | 1 | 23 | 23 | [22 empty] | 1 | [39 empty] | P4-L6 basis: 'vendor stack defects during SIT need vendor fixes'. F23 evidence (architect): 'There does not seem to any fix time for iusses from HCL' - the fixing this step represents has no drawn elapsed time; positioned where SIT defects first accumulate. Judgement.
G-P4-L6-s3 | • Fix-and-retest loop (undrawn) ahead of UAT sign-off | HCL | ASSUMPTION |  | G-P4-L6-s2 | 24 | 1 | 24 | 24 | [23 empty] | 1 | [38 empty] | F23: 'no fix-and-retest loop before ‘Test phase complete’ at the Christmas marker' - this step names the loop the POAP omits between HCL defect-fixing (P4-L6) and UAT (P4-L4); the drawn geometry leaves it zero elapsed weeks, so its placement in Christmas week 24 is judgement recording the gap, not a drawn window.
G-P4-L6-s4 | • UAT defect support and resolution-log closure - no greenfield/brownfield split in scope | HCL | ASSUMPTION |  | G-P4-L6-s3 | 25 | 1 | 25 | 25 | [24 empty] | 1 | [37 empty] | P4-L6 desc '... & SIT/UAT support'; resolutions feed the slide 9 'Defect register & resolution log'. F23 evidence (architect): 'In E, green field and brown field would need to tested' - the drawn test scope shows no greenfield/brownfield coverage split. Position is judgement (closing week of the phase).
G-P4-L7 | Testing [P4-L7] | SEGRO | ASSUMPTION | F1 |  | 22 | 4 | 22 | 25 | [21 empty] | 1 | 1 | 1 | 1 | [37 empty] | Cost line P4-L7 'SEGRO platform team support during test phase (env fixes, redeploys)' - co-extensive with the drawn Testing bar (x=11.19-12.9, weeks 22-25); its basis calls it 'standard test-phase platform support'. Straddles Christmas weeks 24-25 (F1). Status ASSUMPTION: this SEGRO support line has NO bar of its own on the POAP - it is placed co-extensive with the drawn HCL/Testing bar by judgement (the support is real and costed, but its window is inferred, not drawn).
G-P4-L7-s1 | • Environment fixes and configuration support for SIT start-up | SEGRO | ASSUMPTION |  |  | 22 | 1 | 22 | 22 | [21 empty] | 1 | [40 empty] | P4-L7 desc '(env fixes, redeploys)' - environment support is heaviest when SIT opens the drawn Testing bar (week 22). Status ASSUMPTION: step position is a judgement split within the inferred support window (no per-step boundary is drawn).
G-P4-L7-s2 | • Redeploys behind defect fixes | SEGRO | ASSUMPTION |  | G-P4-L7-s1 | 23 | 1 | 23 | 23 | [22 empty] | 1 | [39 empty] | P4-L7 desc '... redeploys' - redeploys follow the first SIT defect cycle (G-P4-L1-s2, week 23). Status ASSUMPTION: step position is a judgement split within the inferred support window (no per-step boundary is drawn).
G-P4-L7-s3 | • Platform support cover through the Christmas weeks to Test phase complete | SEGRO | ASSUMPTION |  | G-P4-L7-s2 | 24 | 2 | 24 | 25 | [23 empty] | 1 | 1 | [37 empty] | P4-L7 desc 'SEGRO platform team support during test phase' - the drawn Testing bar runs to x=12.9 with 'Test phase complete' at x=12.68 and the 'Christmas' marker at x=12.91, so as drawn the cover spans weeks 24-25, the peak-leave window (F1), preserved as drawn. Status ASSUMPTION: step position is a judgement split within the inferred support window (no per-step boundary is drawn).
G-P4-L8 | Testing [P4-L8] | ThirdParty | ASSUMPTION | F26 |  | 22 | 3 | 22 | 24 | [21 empty] | 1 | 1 | 1 | [38 empty] | Cost line P4-L8 'AI red-team exercise + audit dry-run before go-live - prompt injection, tool-abuse/data-exfiltration, jailbreak testing on agent surfaces (absent from POAP, F26)'. NO bar is drawn for this anywhere - F26: 'No AI red-teaming or audit dry-run appears anywhere in the plan'; architect: 'Red Teaming or Audit Dry runs for AI not in plan'. Window weeks 22-24 is a judgement placement inside the P4 test phase so findings can inform the January go/no-go (F26 recommendation: 'named go/no-go inputs').
G-P4-L8-s1 | • Scope AI red-team - agent surfaces, prompt injection, tool-abuse/data-exfiltration and jailbreak test plan | ThirdParty | ASSUMPTION |  |  | 22 | 1 | 22 | 22 | [21 empty] | 1 | [40 empty] | P4-L8 desc: 'prompt injection, tool-abuse/data-exfiltration, jailbreak testing on agent surfaces'. Nothing is drawn (F26), so scoping is placed at the start of the assumed window, alongside pen-test scoping. Judgement.
G-P4-L8-s2 | • Red-team execution (3-8 tester-days) against agent behaviour | ThirdParty | ASSUMPTION |  | G-P4-L8-s1 | 23 | 1 | 23 | 23 | [22 empty] | 1 | [39 empty] | P4-L8 qty_model: 'ASSUMPTION-range fixed engagement: 3-8 tester-days' at the INDICATIVE CREST-proxy rate. Execution follows scoping; placed before the Christmas weeks to protect specialist availability. Judgement.
G-P4-L8-s3 | • Audit dry-run and red-team findings packaged as go/no-go inputs | ThirdParty | ASSUMPTION |  | G-P4-L8-s2 | 24 | 1 | 24 | 24 | [23 empty] | 1 | [38 empty] | P4-L8 desc '... + audit dry-run before go-live'; F26 recommendation: 'Add a pre-go-live AI red-team exercise and audit dry-run as named go/no-go inputs'. Closes the assumed window ahead of the January go/no-go (drawn x=13.99). Judgement.
G-P5-L1 | Deploy (P5) [P5-L1] | SEGRO | POAP-DRAWN |  |  | 26 | 4 | 26 | 29 | [25 empty] | 1 | 1 | 1 | 1 | [33 empty] | Slide 3 Deploy bar x=13.23-14.9 (weeks 26-29) with five staggered items: 'Production readiness review ¦ Smoke test / Stage gates ¦ Go / No Go decision ¦ Migration execution ¦ Go live'. Cost line P5-L1: 'Production readiness, smoke tests, stage gates, migration execution, go-live' - 2 FTE platform engineers x 4 wk.
G-P5-L1-s1 | • Production readiness review | SEGRO | DERIVED |  |  | 26 | 1 | 26 | 26 | [25 empty] | 1 | [36 empty] | Slide 3 deploy item 1 'Production readiness review' drawn x=13.54 - first staggered item, offset 0.74 wk into the Deploy bar = week 26. Slide 9 names the 'Production readiness assessment' deliverable it produces.
G-P5-L1-s2 | • Smoke test / stage gates in production, smoke test report produced | SEGRO | DERIVED |  | G-P5-L1-s1 | 27 | 1 | 27 | 27 | [26 empty] | 1 | [35 empty] | Slide 3 deploy item 2 'Smoke test / Stage gates' drawn x=13.71 - offset 1.15 wk = week 27. Slide 10 deploy doc 'Smoke test report' is the evidenced output.
G-P5-L1-s3 | • Rollback plan validation and cutover rehearsal ahead of migration | SEGRO | ASSUMPTION |  | G-P5-L1-s1 | 27 | 1 | 27 | 27 | [26 empty] | 1 | [35 empty] | Text sourced from slide 10 deploy docs 'Rollback plan' and 'Migration & cutover plan' - both must be exercised before the week-28 migration; positioned week 27 alongside stage gates (position is our allocation, no drawn item).
G-P5-L1-s4 | • Migration execution per the migration & cutover plan | SEGRO | DERIVED |  | G-P5-L1-s2, G-P5-L1-s3 | 28 | 1 | 28 | 28 | [27 empty] | 1 | [34 empty] | Slide 3 deploy item 4 'Migration execution' drawn x=14.28 - offset 2.51 wk = week 28; executes the slide 10 'Migration & cutover plan'.
G-P5-L1-s5 | • Go live | SEGRO | DERIVED |  | G-P5-L1-s4 | 29 | 1 | 29 | 29 | [28 empty] | 1 | [33 empty] | Slide 3 deploy item 5 'Go live' drawn x=14.57 - offset 3.21 wk = week 29; matches the 'Go Live' milestone marker x=14.60 = end of week 29 (gantt_timeline).
G-P5-L2 | Deploy (P5) [P5-L2] | SEGRO | POAP-DRAWN |  |  | 26 | 4 | 26 | 29 | [25 empty] | 1 | 1 | 1 | 1 | [33 empty] | Cost line P5-L2: 'CI/CD cutover, release automation, operational handover pack' - 1 FTE DevOps x 4 wk inside the drawn Deploy bar (weeks 26-29). Spec boundary: P2-L27 BUILDS the pipelines in P2; this line EXECUTES the CI/CD cutover and release automation at deploy.
G-P5-L2-s1 | • Release plan finalised and release automation configured for production | SEGRO | ASSUMPTION |  |  | 26 | 1 | 26 | 26 | [25 empty] | 1 | [36 empty] | Text sourced from slide 10 deploy doc 'Release plan' + P5-L2 desc 'release automation'; positioned week 26 to precede stage gates (position is our allocation).
G-P5-L2-s2 | • CI/CD cutover to production pipelines | SEGRO | ASSUMPTION |  | G-P5-L2-s1 | 27 | 1 | 27 | 27 | [26 empty] | 1 | [35 empty] | Text sourced from P5-L2 desc 'CI/CD cutover' + slide 7 'CI/CD Configuration Document ¦ Automates build & deploy'; positioned week 27 alongside smoke/stage gates so production deploys run through the pipeline before migration.
G-P5-L2-s3 | • Deployment-automation support through migration execution | SEGRO | ASSUMPTION |  | G-P5-L2-s2 | 28 | 1 | 28 | 28 | [27 empty] | 1 | [34 empty] | Positioned against the drawn 'Migration execution' item (x=14.28, week 28) - the DevOps FTE supports the cutover it automated; allocation ours.
G-P5-L2-s4 | • Operational handover pack compiled and handed to the run team | SEGRO | ASSUMPTION |  | G-P5-L2-s3 | 29 | 1 | 29 | 29 | [28 empty] | 1 | [33 empty] | Text sourced from slide 10 deploy doc 'Operational handover pack' (P5-L2 basis names it); positioned week 29 at go-live so the run team receives it as hypercare starts.
G-P5-L3 | Deploy (P5) [P5-L3] | SEGRO | POAP-DRAWN |  |  | 26 | 4 | 26 | 29 | [25 empty] | 1 | 1 | 1 | 1 | [33 empty] | Cost line P5-L3: 'Release/project management - go/no-go pack, cutover comms' - 1 FTE PM x 4 wk; anchored on the drawn 'Go / No Go decision' milestone (slide 3, x=13.99).
G-P5-L3-s1 | • Go/no-go checklist and approval pack assembled | SEGRO | ASSUMPTION |  |  | 26 | 2 | 26 | 27 | [25 empty] | 1 | 1 | [35 empty] | Text sourced from slide 10 deploy doc 'Go / no go checklist & approval'; positioned weeks 26-27 to complete before the drawn decision point (allocation ours).
G-P5-L3-s2 | • Go / No Go decision | SEGRO | DERIVED |  | G-P5-L3-s1 | 27 | 1 | 27 | 27 | [26 empty] | 1 | [35 empty] | Slide 3 deploy item 3 'Go / No Go decision' drawn x=13.99 - offset 1.82 wk into the Deploy bar = late week 27, ahead of week-28 migration execution.
G-P5-L3-s3 | • Cutover comms and go-live coordination | SEGRO | ASSUMPTION |  | G-P5-L3-s2 | 28 | 2 | 28 | 29 | [27 empty] | 1 | 1 | [33 empty] | Text sourced from P5-L3 desc 'cutover comms'; positioned weeks 28-29 spanning the drawn 'Migration execution' (wk 28) and 'Go live' (wk 29) items.
G-P5-L4 | Deploy (P5) [P5-L4] | SEGRO | ASSUMPTION | F7 |  | 26 | 4 | 26 | 29 | [25 empty] | 1 | 1 | 1 | 1 | [33 empty] | Cost line P5-L4: 'Pen-test remediation + retest sign-off before go/no-go (F7)' - 0.5 FTE cloud security x 4 wk. The POAP itself draws no remediation window (F7: 'remediation + retest must land before the January go/no-go; POAP holds no named window') - the task window is the drawn Deploy bar; the internal steps are the F7-recommended sequence. Status ASSUMPTION: the POAP draws NO remediation window (F7) - this window is placed inside the drawn Deploy bar by judgement.
G-P5-L4-s1 | • Triage pen-test findings and agree remediation plan | SEGRO | ASSUMPTION |  |  | 26 | 1 | 26 | 26 | [25 empty] | 1 | [36 empty] | Text sourced from P5-L4 basis (F7: 'hold a named remediation window in early Jan before go/no-go'); pen test runs in the P4 window ending week 25, so triage positioned week 26 (allocation ours).
G-P5-L4-s2 | • Remediate pen-test findings | SEGRO | ASSUMPTION |  | G-P5-L4-s1 | 26 | 2 | 26 | 27 | [25 empty] | 1 | 1 | [35 empty] | Text sourced from P5-L4 desc 'Pen-test remediation'; positioned weeks 26-27 so remediation completes before the drawn Go/No Go decision (x=13.99, late wk 27). P5-L4 basis: 'High band = material findings'.
G-P5-L4-s3 | • Retest and security sign-off input to the go/no-go decision | SEGRO | ASSUMPTION |  | G-P5-L4-s2 | 27 | 1 | 27 | 27 | [26 empty] | 1 | [35 empty] | Text sourced from P5-L4 desc 'retest sign-off before go/no-go'; positioned week 27 to land at the drawn decision point (allocation ours).
G-P5-L5 | Deploy (P5) [P5-L5] | HCL | POAP-DRAWN |  |  | 26 | 4 | 26 | 29 | [25 empty] | 1 | 1 | 1 | 1 | [33 empty] | Cost line P5-L5: 'HCL go-live support (their components through cutover)' - 1 FTE x 4 wk across the drawn Deploy bar (weeks 26-29). Rate VERIFIED (HCL card); allocation ASSUMPTION per spec.
G-P5-L5-s1 | • HCL support at production readiness review and smoke tests of HCL components (UnO/TX, Unica+, CDP) | HCL | ASSUMPTION |  |  | 26 | 2 | 26 | 27 | [25 empty] | 1 | 1 | [35 empty] | Text sourced from P5-L5 desc 'their components through cutover' + slide 3 deploy items 'Production readiness review' (wk 26) and 'Smoke test / Stage gates' (wk 27); vendor components need vendor presence at both gates (allocation ours).
G-P5-L5-s2 | • HCL support during migration execution | HCL | ASSUMPTION |  | G-P5-L5-s1 | 28 | 1 | 28 | 28 | [27 empty] | 1 | [34 empty] | Positioned against the drawn 'Migration execution' item (x=14.28, week 28); HCL-installed services migrate under vendor support (allocation ours).
G-P5-L5-s3 | • HCL standby and cutover support at go-live | HCL | ASSUMPTION |  | G-P5-L5-s2 | 29 | 1 | 29 | 29 | [28 empty] | 1 | [33 empty] | Positioned against the drawn 'Go live' item (x=14.57, week 29); text sourced from P5-L5 desc 'go-live support' (allocation ours).
G-P6-L1 | Hypercare / PGLS (P6) [P6-L1] | SEGRO | POAP-DRAWN | F24 | G-P5-L1 | 30 | 6 | 30 | 35 | [29 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [27 empty] | Slide 3 'PGLS + Hypercare' bar drawn from go-live (x=15.41). Duration 6 wk is the cost model's ASSUMPTION (P6 poap_ref: '4-8 wk hypercare norm... short fixed-end-date, criteria-based exit'). Cost line P6-L1: 'Hypercare squad - declining coverage, average 1.5 FTE across 6 weeks'.
G-P6-L1-s1 | • Hypercare full coverage - stabilisation and incident triage per the hypercare plan | SEGRO | ASSUMPTION |  |  | 30 | 2 | 30 | 31 | [29 empty] | 1 | 1 | [31 empty] | Text sourced from slide 10 deploy doc 'Hypercare plan' + slide 3 'PGLS + Hypercare' (bar start = go-live); front-loaded full coverage implements P6-L1's 'declining coverage' profile (split ours).
G-P6-L1-s2 | • Hypercare reduced coverage as incident volumes fall | SEGRO | ASSUMPTION |  | G-P6-L1-s1 | 32 | 2 | 32 | 33 | [31 empty] | 1 | 1 | [29 empty] | Text sourced from P6-L1 desc 'declining coverage, average 1.5 FTE across 6 weeks' - middle tranche of the declining profile (split ours).
G-P6-L1-s3 | • Criteria-based hypercare exit assessment and handover to run team | SEGRO | ASSUMPTION |  | G-P6-L1-s2 | 34 | 2 | 34 | 35 | [33 empty] | 1 | 1 | [27 empty] | Text sourced from P6 poap_ref 'short fixed-end-date, criteria-based exit' (programme_benchmarks hypercare norm via spec). F24 context: after this exit the POAP shows no iterative delivery - post-go-live items are only 'PGLS + Hypercare' and 'Planning & scope for R2'.
G-P6-L2 | Hypercare / PGLS (P6) [P6-L2] | HCL | POAP-DRAWN |  | G-P5-L5 | 30 | 6 | 30 | 35 | [29 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [27 empty] | Slide 3 'PGLS + Hypercare' bar from go-live (x=15.41). Cost line P6-L2: 'HCL PGLS / hypercare support on HCL components' - 1 FTE x 6 wk; spec basis: 'If PGLS is inside a fixed-price contract this double-counts - flexes to 0 via qty or HCL_Toggle'.
G-P6-L2-s1 | • PGLS defect-fix and stabilisation on HCL components | HCL | ASSUMPTION |  |  | 30 | 3 | 30 | 32 | [29 empty] | 1 | 1 | 1 | [30 empty] | Slide 3 'PGLS + Hypercare' drawn starting x=15.41 = week 30 (immediately after the go-live marker x=14.60); heaviest vendor defect-fix load lands in the first weeks post-cutover. Status ASSUMPTION: front-load position on the single drawn PGLS+Hypercare bar is judgement (matching the analogous SEGRO hypercare step G-P6-L1-s1).
G-P6-L2-s2 | • Tapering HCL support - ticket-driven fixes and knowledge transfer | HCL | ASSUMPTION |  | G-P6-L2-s1 | 33 | 2 | 33 | 34 | [32 empty] | 1 | 1 | [28 empty] | Text sourced from P6-L2 desc 'HCL PGLS / hypercare support on HCL components'; taper mirrors the SEGRO-side declining-coverage profile (split ours).
G-P6-L2-s3 | • PGLS exit - HCL components transition to steady-state AMS/support contract | HCL | ASSUMPTION |  | G-P6-L2-s2 | 35 | 1 | 35 | 35 | [34 empty] | 1 | [27 empty] | Text sourced from P6-L2 basis 'If PGLS is inside a fixed-price contract this double-counts - flexes to 0'; exit at the end of the 6-wk window hands to the run-model AMS line (R-L24, RATE_MISSING).
G-P6-L3 | Hypercare / PGLS (P6) [P6-L3] | SEGRO | POAP-DRAWN |  |  | 6 | 30 | 6 | 35 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [27 empty] | Cost line P6-L3: 'Change management, comms, training delivery & business readiness (spread P2-P6, booked here)' - drawn as the lane D bars (Change Management x=4.65, Stakeholder engagement & Comms x=4.60, Training x=6.74) spanning weeks ~6-26, with delivery and close-out running into P6; windowed weeks 6-35 to match the drawn spread while the cost books in P6. Sized from the VERIFIED Prosci benchmark: '10% of project budget' (spec basis).
G-P6-L3-s1 | • Change management and stakeholder engagement across build and test | SEGRO | DERIVED |  |  | 6 | 21 | 6 | 26 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [36 empty] | Slide 3 lane D bars 'Change Management' (x=4.65 w=6.98 = weeks 6-22) and 'Stakeholder engagement & Comms' (x=4.60 w=8.62 = weeks 6-26) at the 2.388 wk/in calibration; window = the wider of the two drawn extents. Slide 8 doc: 'Comms plan'.
G-P6-L3-s2 | • Training strategy and materials development | SEGRO | DERIVED |  |  | 11 | 15 | 11 | 25 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [37 empty] | Slide 3 lane D bar 'Training' drawn x=6.74 w=5.96 = weeks 11-25 at the calibration; slide 8 doc 'Training strategy & materials'.
G-P6-L3-s3 | • Business Readiness Assessment and process updates ahead of go-live | SEGRO | ASSUMPTION |  | G-P6-L3-s1 | 22 | 6 | 22 | 27 | [21 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [35 empty] | Text sourced from slide 8 docs 'Business Readiness Assessment' and 'Process Updates'; positioned weeks 22-27 (test phase into the go/no-go) so readiness evidence feeds the drawn 'Go / No Go decision' - position is our allocation, no drawn item.
G-P6-L3-s4 | • Go-live comms and end-user training delivery through deploy | SEGRO | ASSUMPTION |  | G-P6-L3-s2, G-P6-L3-s3 | 26 | 4 | 26 | 29 | [25 empty] | 1 | 1 | 1 | 1 | [33 empty] | Text sourced from P6-L3 desc 'comms, training delivery'; positioned across the drawn Deploy bar (weeks 26-29) so users are trained and informed at cutover (allocation ours).
G-P6-L3-s5 | • Post-go-live adoption support and business-readiness close-out (booked here) | SEGRO | ASSUMPTION |  | G-P6-L3-s4 | 30 | 6 | 30 | 35 | [29 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [27 empty] | Text sourced from P6-L3 desc '(spread P2-P6, booked here)' - the P6 booking window itself (weeks 30-35), covering adoption support and embedding of slide 8 'Process Updates' during hypercare.
G-P6-L4 | Hypercare / PGLS (P6) [P6-L4] | SEGRO | ASSUMPTION |  | G-P6-L3 | 30 | 6 | 30 | 35 | [29 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [27 empty] | Cost line P6-L4: 'End-user training materials/licence cost per employee (per-rollout unit cost unpublished)' - RATE_MISSING at GBP 0; 'Headcount VERIFIED (SEGRO ARA25: 463)'. No drawn POAP item carries this - the lane D 'Training' bar covers strategy/materials (D4); this per-employee rollout unit-cost line is windowed to the P6 booking (weeks 30-35) as an ASSUMPTION. Spec: 'Trainer delivery days already inside P6-L3'.
G-P6-L4-s1 | • Confirm per-employee training materials/licence procurement (unit rate GBP 0 until published) | SEGRO | ASSUMPTION |  |  | 30 | 1 | 30 | 30 | [29 empty] | 1 | [32 empty] | Text sourced from P6-L4 basis 'Per-rollout training unit cost is RATE_MISSING in people_rates... GBP 0 adjustable'; positioned at the start of the P6 booking window (allocation ours).
G-P6-L4-s2 | • Materials/licence rollout to 463 employees during hypercare | SEGRO | ASSUMPTION |  | G-P6-L4-s1 | 31 | 4 | 31 | 34 | [30 empty] | 1 | 1 | 1 | 1 | [28 empty] | Text sourced from P6-L4 qty_model '463 employees x per-rollout rate GBP 0' (headcount VERIFIED, SEGRO ARA25); positioned weeks 31-34 inside the hypercare window (allocation ours).
G-P6-L4-s3 | • Completion tracking and training records close-out | SEGRO | ASSUMPTION |  | G-P6-L4-s2 | 35 | 1 | 35 | 35 | [34 empty] | 1 | [27 empty] | Close-out of the rollout at the end of the P6 window; supports the slide 8 'Business Readiness Assessment' evidence trail (position is our allocation, no drawn item).
G-P6-L5 | Hypercare / PGLS (P6) [P6-L5] | SEGRO | POAP-DRAWN |  | G-P5-L2 | 30 | 6 | 30 | 35 | [29 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [27 empty] | Cost line P6-L5: 'Service transition & application support model into ITIL/ServiceNow (transition pack, RACI, ownership matrix)' - 0.5 FTE PM x 6 wk. The preparatory work is the drawn lane D item 1 'Service transition & application support model' (x=5.83 w=6.83, weeks 9-25, carried in G-D-BIZ); this task is the P6-booked close-out into BAU. Spec basis: 'SEGRO principle - ITIL/ServiceNow service transition for everything'.
G-P6-L5-s1 | • Finalise Support RACI and Service ownership matrix from the transition pack | SEGRO | ASSUMPTION |  |  | 30 | 2 | 30 | 31 | [29 empty] | 1 | 1 | [31 empty] | Text sourced from slide 8 docs 'Support RACI' and 'Service ownership matrix' + P6-L5 desc '(transition pack, RACI, ownership matrix)'; positioned at the start of the P6 window using the P5-L2 operational handover pack as input (allocation ours).
G-P6-L5-s2 | • ServiceNow onboarding - service catalogue, support groups, knowledge articles | SEGRO | ASSUMPTION |  | G-P6-L5-s1 | 32 | 2 | 32 | 33 | [31 empty] | 1 | 1 | [29 empty] | Text sourced from P6-L5 desc 'into ITIL/ServiceNow' + spec basis 'SEGRO principle - ITIL/ServiceNow service transition for everything'; positioned mid-window after RACI/ownership agreed (allocation ours).
G-P6-L5-s3 | • Formal service acceptance into BAU at hypercare exit | SEGRO | ASSUMPTION |  | G-P6-L5-s2 | 34 | 2 | 34 | 35 | [33 empty] | 1 | 1 | [27 empty] | Positioned to coincide with the criteria-based hypercare exit (G-P6-L1-s3, weeks 34-35) so the support model is live when hypercare ends; text sourced from P6-L5 desc 'Service transition & application support model' (allocation ours).
G-D-BIZ | Business readiness (lane D) | SEGRO | POAP-DRAWN | F22, F4, F24 |  | 6 | 25 | 6 | 30 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [32 empty] | Slide 3 lane D 'Business readiness' (label x=4.59): six drawn items D1-D6 staggered from mid-build (starts x=4.60-6.83), read at the 2.388 wk/in calibration (build-bar start x=4.55 = start wk 6; Go Live x=14.60 = end wk 29). Per-item extents span weeks 6-30 - a refinement of the timeline fact's approximate [8,25] lane envelope (which defers per-item reads to this fragment); D5 is drawn past the go-live marker. Costed via cost line P6-L3 (booked in P6, spread P2-P6). F22: D1-D4 imply an op-model change with no stated IT-governance alignment ('Has IT Governance Capability been aligned to this, and can it support the op model changes and the change management for AI?'). F4: comms/readiness must handle slides 13/14 showing use cases 'Live' in Q3/Q4 2026 - before this platform's Feb 2027 go-live. F24: the lane is one-pass bars ending at/near go-live - no iterative agent-delivery or learning-to-rules loop follows ('agents will require more agility that this with a feedback loop and many iterations').
G-D-BIZ-s1 | • Service transition & application support model (D1) | SEGRO | DERIVED |  |  | 9 | 17 | 9 | 25 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [37 empty] | Slide 3 lane D item 1 'Service transition & application support model' drawn x=5.83 w=6.83 = weeks 9-25 at the 2.388 wk/in calibration; P6-booked close-out carried in G-P6-L5.
G-D-BIZ-s2 | • IT Operating Model (ITOM) (D2) | SEGRO | DERIVED |  |  | 9 | 17 | 9 | 25 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [37 empty] | Slide 3 lane D item 2 'IT Operating Model (ITOM)' drawn x=5.83 w=6.83 = weeks 9-25 - same drawn extent as D1. F22 bites here: the op-model change has no stated IT-governance owner.
G-D-BIZ-s3 | • Change Management (D3) | SEGRO | DERIVED |  |  | 6 | 17 | 6 | 22 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [40 empty] | Slide 3 lane D item 3 'Change Management' drawn x=4.65 w=6.98 = weeks 6-22 at the calibration - starts with the build phase.
G-D-BIZ-s4 | • Training (D4) | SEGRO | DERIVED |  |  | 11 | 15 | 11 | 25 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [37 empty] | Slide 3 lane D item 4 'Training' drawn x=6.74 w=5.96 = weeks 11-25 at the calibration; slide 8 doc 'Training strategy & materials'.
G-D-BIZ-s5 | • Planning & scope for R2 (D5) | SEGRO | DERIVED |  |  | 11 | 20 | 11 | 30 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [32 empty] | Slide 3 lane D item 5 'Planning & scope for R2' drawn x=6.83 w=8.19 = weeks 11-30 at the calibration - the widest lane D bar, drawn past the go-live marker (x end 15.02 vs Go Live x=14.60). F5: this is the only Release-item in the plan - 'no Release 1 use-case build/test/deploy appears anywhere after platform go-live; the only R-item is Planning & scope for R2'. Slide 8 docs: 'Release 2 scope document', 'Roadmap'.
G-D-BIZ-s6 | • Stakeholder engagement & Comms (D6) | SEGRO | DERIVED |  |  | 6 | 21 | 6 | 26 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [36 empty] | Slide 3 lane D item 6 'Stakeholder engagement & Comms' drawn x=4.60 w=8.62 = weeks 6-26 at the calibration - the earliest-starting lane D bar, running into the deploy window. Slide 8 docs: 'Stakeholder impact assessment', 'Comms plan'. F4 bites here: comms must reconcile slides 13/14 'Customer P1 (Live)' / 'Sustainability UL 360 (Live)' / 'Content Agent (Live)' in Q3 2026 against this plan's Feb 2027 go-live.
G-P2-L28 | Data integration (scope gap) [P2-L28] | SEGRO | ASSUMPTION | F15 |  | 6 | 10 | 6 | 15 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | NO drawn bar — the absence IS finding F15: the POAP costs the platform but no integration to MRI (the critical backbone), SAMA or Anaplan. Agents with no data path to the systems of record cannot deliver business value. Visible £0 on the cost tab (P2-L28, RATE_MISSING). Window is the implied shape (a delivery-prerequisite lane that would run across the build); judgement, not drawn geometry. [td_override=true: this is a people/delivery LANE — its elapsed effort dilates with slip even though the cost line is RATE_MISSING £0, so the bar must stretch like other people lanes, not sit fixed.]
G-P2-L28-s1 | • Integration design to MRI / SAMA / Anaplan via APIM + staging layer | SEGRO | ASSUMPTION |  |  | 6 | 3 | 6 | 8 | [5 empty] | 1 | 1 | 1 | [54 empty] | Absent from the POAP (F15); the SEGRO architecture mandates APIM + staging-layer integration to systems of record. £0 un-costed.
G-P2-L28-s2 | • Build + test data pipelines to the operational backbones | SEGRO | ASSUMPTION |  |  | 9 | 4 | 9 | 12 | [8 empty] | 1 | 1 | 1 | 1 | [50 empty] | No integration build lane exists in the POAP (F15). Prerequisite for any business-facing use case.
G-P2-L28-s3 | • Reconciliation + cutover of the integration layer | SEGRO | ASSUMPTION |  |  | 13 | 3 | 13 | 15 | [12 empty] | 1 | 1 | 1 | [47 empty] | Implied tail of an integration workstream the POAP omits (F15).
G-P4-L9 | Eval golden-set labelling (scope gap) [P4-L9] | SEGRO | ASSUMPTION | F13 |  | 22 | 4 | 22 | 25 | [21 empty] | 1 | 1 | 1 | 1 | [37 empty] | NO drawn bar — the absence IS finding F13: FND-4 costs the eval-harness MACHINERY but nobody has costed the business-SME weeks that label the golden sets it scores against. Without labelled goldens the promotion gates are hollow. Visible £0 on the cost tab (P4-L9). Window aligns to the test phase where the eval harness runs. [td_override=true: this is a people/delivery LANE — its elapsed effort dilates with slip even though the cost line is RATE_MISSING £0, so the bar must stretch like other people lanes, not sit fixed.]
G-P4-L9-s1 | • SMEs assemble representative golden-set inputs per use case | SEGRO | ASSUMPTION |  |  | 22 | 2 | 22 | 23 | [21 empty] | 1 | 1 | [39 empty] | Business SME effort absent from the POAP (F13); needed before the eval harness can score anything.
G-P4-L9-s2 | • SMEs label expected outputs + edge cases; sign-off | SEGRO | ASSUMPTION |  |  | 24 | 2 | 24 | 25 | [23 empty] | 1 | 1 | [37 empty] | Labelling effort un-costed (F13). The promotion gates depend on it.
G-P5-L9 | R1 use-case delivery lane (scope gap) [P5-L9] | SEGRO | ASSUMPTION | F5 |  | 22 | 8 | 22 | 29 | [21 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [33 empty] | NO drawn bar — the absence IS finding F5: A101 concedes £830k buys a platform with zero business-facing capability at go-live. There is no R1 use-case delivery lane in the POAP. Visible £0 on the cost tab (P5-L9); the £37k supervised September pilot (R1 Pilot tab) is the costed alternative. Window would run from build into deploy. [td_override=true: this is a people/delivery LANE — its elapsed effort dilates with slip even though the cost line is RATE_MISSING £0, so the bar must stretch like other people lanes, not sit fixed.]
G-P5-L9-s1 | • Build the first business-facing use cases against the platform | SEGRO | ASSUMPTION |  |  | 22 | 4 | 22 | 25 | [21 empty] | 1 | 1 | 1 | 1 | [37 empty] | No R1 delivery lane in the POAP (F5); the platform delivers no capability without it.
G-P5-L9-s2 | • Supervised pilot + iterate to promotion | SEGRO | ASSUMPTION |  |  | 26 | 4 | 26 | 29 | [25 empty] | 1 | 1 | 1 | 1 | [33 empty] | The costed alternative is the R1 September pilot (out-of-total). Absent from the POAP (F5).
G-P2-L30-ALT | Llama GPU-quota procurement (ALTERNATIVE branch) [P2-L30] | Azure | ASSUMPTION |  |  | 6 | 4 | 6 | 9 | [5 empty] | 1 | 1 | 1 | 1 | [53 empty] | ALTERNATIVE branch only (ModelChoice=Llama). GPU capacity needs a quota request / reserved-capacity commitment — a SCHEDULE RISK (lead time to grant) as well as a cost (P2-L30, RATE_MISSING £0). It PRECEDES commissioning (you cannot spin up GPU nodes before quota is granted), which is why the commissioning bar G-P2-L29-ALT starts after this one completes. Shown as an ASSUMPTION row so the procurement lead-time is visible on the schedule under the self-host branch; toggle-gated off otherwise.
G-P2-L30-ALT-s1 | • Raise Azure GPU quota increase request | Azure | ASSUMPTION |  |  | 6 | 2 | 6 | 7 | [5 empty] | 1 | 1 | [55 empty] | Llama-branch procurement (P2-L30); grant lead time is a schedule risk. Gates commissioning.
G-P2-L30-ALT-s2 | • Grant + negotiate reserved-capacity / capacity-reservation commitment | Azure | ASSUMPTION |  |  | 8 | 2 | 8 | 9 | [7 empty] | 1 | 1 | [53 empty] | Llama-branch procurement (P2-L30); RATE_MISSING until quoted. Grant at end of wk 9 unblocks commissioning.
G-P2-L29-ALT | Llama GPU commissioning (ALTERNATIVE branch) [P2-L29] | Azure | ASSUMPTION |  | G-P2-L30-ALT | 10 | 6 | 10 | 15 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | ALTERNATIVE branch only — this bar exists ONLY under ModelChoice=Llama (self-hosting), which is NOT the POAP as drawn (the POAP assumes hosted Azure OpenAI). Starts in week 10, AFTER the GPU-quota grant (G-P2-L30-ALT completes wk 9) — you cannot commission GPU nodes before quota is granted (the source flags quota as a prerequisite / schedule risk). Shown as an ASSUMPTION row so the self-host build cost is visible on the schedule when that branch is chosen; toggle-gated £0 otherwise. Bounded GPU commissioning/eval window during P2 bring-up (cost line P2-L29).
G-P2-L29-ALT-s1 | • Provision GPU node pool + drivers/CUDA for model bring-up (post quota grant) | Azure | ASSUMPTION |  |  | 10 | 3 | 10 | 12 | [9 empty] | 1 | 1 | 1 | [50 empty] | Llama-branch build work (P2-L29); only if self-hosting is chosen. Follows the quota grant.
G-P2-L29-ALT-s2 | • Quantise + throughput-tune + eval the served model | Azure | ASSUMPTION |  |  | 13 | 3 | 13 | 15 | [12 empty] | 1 | 1 | 1 | [47 empty] | Llama-branch commissioning (P2-L29); bounded window, not 24/7 serving.
G-P2-MODEL | Azure model endpoint bring-up (Foundry/AOAI) [P2-L29..P2-L29] | SEGRO | ASSUMPTION |  |  | 6 | 4 | 6 | 9 | [5 empty] | 1 | 1 | 1 | 1 | [53 empty] | Platform model serving path (v3). Llama GPU ALT remains G-P2-L29-ALT. [td_override=true: people/platform lane dilates with slip.]
G-P2-MODEL-s1 | • Scaffold Azure OpenAI / Foundry deployments | SEGRO | ASSUMPTION |  |  | 6 | 2 | 6 | 7 | [5 empty] | 1 | 1 | [55 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-MODEL-s2 | • Wire SKU endpoint + quota | SEGRO | ASSUMPTION |  |  | 8 | 1 | 8 | 8 | [7 empty] | 1 | [54 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-MODEL-s3 | • Smoke eval harness calls | SEGRO | ASSUMPTION |  |  | 9 | 1 | 9 | 9 | [8 empty] | 1 | [53 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-MCP | MCP estate on Container Apps (McpServerCount servers) [R-L40..R-L42] | SEGRO | ASSUMPTION | F5 |  | 7 | 8 | 7 | 14 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [48 empty] | MCP estate scales with McpServerCount calculator. [td_override=true: people/platform lane dilates with slip.]
G-P2-MCP-s1 | • Scaffold MCP servers on ACA | SEGRO | ASSUMPTION |  |  | 7 | 3 | 7 | 9 | [6 empty] | 1 | 1 | 1 | [53 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-MCP-s2 | • APIM products + OAuth for each MCP | SEGRO | ASSUMPTION |  |  | 10 | 3 | 10 | 12 | [9 empty] | 1 | 1 | 1 | [50 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-MCP-s3 | • Contract tests per application plug | SEGRO | ASSUMPTION |  |  | 13 | 2 | 13 | 14 | [12 empty] | 1 | 1 | [48 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-RAG | RAG index (AI Search or Cosmos vectors) [R-L43..R-L44] | SEGRO | ASSUMPTION | F13 |  | 8 | 6 | 8 | 13 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [49 empty] | Shape from RagMemoryShape toggle. [td_override=true: people/platform lane dilates with slip.]
G-P2-RAG-s1 | • Choose RagMemoryShape path | SEGRO | ASSUMPTION |  |  | 8 | 2 | 8 | 9 | [7 empty] | 1 | 1 | [53 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-RAG-s2 | • Index / vector store bring-up | SEGRO | ASSUMPTION |  |  | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-RAG-s3 | • Retrieval eval smoke | SEGRO | ASSUMPTION |  |  | 12 | 2 | 12 | 13 | [11 empty] | 1 | 1 | [49 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-MEM | Cosmos Mongo agent memory store [R-L45..R-L45] | SEGRO | ASSUMPTION |  |  | 8 | 5 | 8 | 12 | [7 empty] | 1 | 1 | 1 | 1 | 1 | [50 empty] | Shared memory platform for all catalogue agents. [td_override=true: people/platform lane dilates with slip.]
G-P2-MEM-s1 | • Provision Cosmos Mongo | SEGRO | ASSUMPTION |  |  | 8 | 2 | 8 | 9 | [7 empty] | 1 | 1 | [53 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-MEM-s2 | • Memory schema + retention | SEGRO | ASSUMPTION |  |  | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-MEM-s3 | • Per-agent memory wiring pattern | SEGRO | ASSUMPTION |  |  | 12 | 1 | 12 | 12 | [11 empty] | 1 | [50 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-FABRIC | Agent hosting / orchestration fabric [R-L40..R-L45] | SEGRO | ASSUMPTION | F5 |  | 10 | 6 | 10 | 15 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [47 empty] | Ties named agents to platform stack. [td_override=true: people/platform lane dilates with slip.]
G-P2-FABRIC-s1 | • Host agent runtimes | SEGRO | ASSUMPTION |  |  | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-FABRIC-s2 | • Bind MCP + RAG + memory | SEGRO | ASSUMPTION |  |  | 12 | 2 | 12 | 13 | [11 empty] | 1 | 1 | [49 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-P2-FABRIC-s3 | • Supervisor / orchestration hooks | SEGRO | ASSUMPTION |  |  | 14 | 2 | 14 | 15 | [13 empty] | 1 | 1 | [47 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-OPEX | Agent: OpEx categorisation agent [R-L40..R-L45] | SEGRO | ASSUMPTION | F5 | G-P2-FABRIC | 12 | 10 | 12 | 21 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [41 empty] | NAMED AGENT (which to build). Absent from HCL POAP (F5). Apps=['MRI']; rag_required=True. Agents tab Include flag. [td_override=true]
G-AGT-OPEX-s1 | • Scope OpEx categorisation agent + eval golden-set hooks | SEGRO | ASSUMPTION |  |  | 12 | 2 | 12 | 13 | [11 empty] | 1 | 1 | [49 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-OPEX-s2 | • MCP tools via APIM into MRI + Entra NHI | SEGRO | ASSUMPTION |  |  | 14 | 2 | 14 | 15 | [13 empty] | 1 | 1 | [47 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-OPEX-s3 | • RAG grounding corpus for OpEx categorisation agent | SEGRO | ASSUMPTION |  |  | 16 | 2 | 16 | 17 | [15 empty] | 1 | 1 | [45 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-OPEX-s4 | • Cosmos Mongo memory wiring for OpEx categorisation agent | SEGRO | ASSUMPTION |  |  | 18 | 2 | 18 | 19 | [17 empty] | 1 | 1 | [43 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-OPEX-s5 | • Pilot → hypercare gate for OpEx categorisation agent | SEGRO | ASSUMPTION |  |  | 20 | 2 | 20 | 21 | [19 empty] | 1 | 1 | [41 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-CAPEX | Agent: CapEx assist agent [R-L40..R-L45] | SEGRO | ASSUMPTION | F5 | G-P2-FABRIC | 13 | 10 | 13 | 22 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [40 empty] | NAMED AGENT (which to build). Absent from HCL POAP (F5). Apps=['MRI', 'Anaplan']; rag_required=True. Agents tab Include flag. [td_override=true]
G-AGT-CAPEX-s1 | • Scope CapEx assist agent + eval golden-set hooks | SEGRO | ASSUMPTION |  |  | 13 | 2 | 13 | 14 | [12 empty] | 1 | 1 | [48 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-CAPEX-s2 | • MCP tools via APIM into MRI, Anaplan + Entra NHI | SEGRO | ASSUMPTION |  |  | 15 | 2 | 15 | 16 | [14 empty] | 1 | 1 | [46 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-CAPEX-s3 | • RAG grounding corpus for CapEx assist agent | SEGRO | ASSUMPTION |  |  | 17 | 2 | 17 | 18 | [16 empty] | 1 | 1 | [44 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-CAPEX-s4 | • Cosmos Mongo memory wiring for CapEx assist agent | SEGRO | ASSUMPTION |  |  | 19 | 2 | 19 | 20 | [18 empty] | 1 | 1 | [42 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-CAPEX-s5 | • Pilot → hypercare gate for CapEx assist agent | SEGRO | ASSUMPTION |  |  | 21 | 2 | 21 | 22 | [20 empty] | 1 | 1 | [40 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-GROWTH | Agent: Growth / Research Pack agent [R-L40..R-L45] | SEGRO | ASSUMPTION | F5 | G-P2-FABRIC | 14 | 10 | 14 | 23 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [39 empty] | NAMED AGENT (which to build). Absent from HCL POAP (F5). Apps=['SAMA']; rag_required=True. Agents tab Include flag. [td_override=true]
G-AGT-GROWTH-s1 | • Scope Growth / Research Pack agent + eval golden-set hooks | SEGRO | ASSUMPTION |  |  | 14 | 2 | 14 | 15 | [13 empty] | 1 | 1 | [47 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-GROWTH-s2 | • MCP tools via APIM into SAMA + Entra NHI | SEGRO | ASSUMPTION |  |  | 16 | 2 | 16 | 17 | [15 empty] | 1 | 1 | [45 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-GROWTH-s3 | • RAG grounding corpus for Growth / Research Pack agent | SEGRO | ASSUMPTION |  |  | 18 | 2 | 18 | 19 | [17 empty] | 1 | 1 | [43 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-GROWTH-s4 | • Cosmos Mongo memory wiring for Growth / Research Pack agent | SEGRO | ASSUMPTION |  |  | 20 | 2 | 20 | 21 | [19 empty] | 1 | 1 | [41 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-GROWTH-s5 | • Pilot → hypercare gate for Growth / Research Pack agent | SEGRO | ASSUMPTION |  |  | 22 | 2 | 22 | 23 | [21 empty] | 1 | 1 | [39 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-METER | Agent: Meter exception agent [R-L40..R-L45] | SEGRO | ASSUMPTION | F5 | G-P2-FABRIC | 15 | 10 | 15 | 24 | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [38 empty] | NAMED AGENT (which to build). Absent from HCL POAP (F5). Apps=['UL360']; rag_required=False. Agents tab Include flag. [td_override=true]
G-AGT-METER-s1 | • Scope Meter exception agent + eval golden-set hooks | SEGRO | ASSUMPTION |  |  | 15 | 2 | 15 | 16 | [14 empty] | 1 | 1 | [46 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-METER-s2 | • MCP tools via APIM into UL360 + Entra NHI | SEGRO | ASSUMPTION |  |  | 17 | 2 | 17 | 18 | [16 empty] | 1 | 1 | [44 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-METER-s3 | • Confirm tool-only path (RAG not required) | SEGRO | ASSUMPTION |  |  | 19 | 2 | 19 | 20 | [18 empty] | 1 | 1 | [42 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-METER-s4 | • Cosmos Mongo memory wiring for Meter exception agent | SEGRO | ASSUMPTION |  |  | 21 | 2 | 21 | 22 | [20 empty] | 1 | 1 | [40 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-METER-s5 | • Pilot → hypercare gate for Meter exception agent | SEGRO | ASSUMPTION |  |  | 23 | 2 | 23 | 24 | [22 empty] | 1 | 1 | [38 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-RECON | Agent: Recon discrepancy agent [R-L40..R-L45] | SEGRO | ASSUMPTION | F5 | G-P2-FABRIC | 16 | 10 | 16 | 25 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [37 empty] | NAMED AGENT (which to build). Absent from HCL POAP (F5). Apps=['MRI', 'UL360']; rag_required=False. Agents tab Include flag. [td_override=true]
G-AGT-RECON-s1 | • Scope Recon discrepancy agent + eval golden-set hooks | SEGRO | ASSUMPTION |  |  | 16 | 2 | 16 | 17 | [15 empty] | 1 | 1 | [45 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-RECON-s2 | • MCP tools via APIM into MRI, UL360 + Entra NHI | SEGRO | ASSUMPTION |  |  | 18 | 2 | 18 | 19 | [17 empty] | 1 | 1 | [43 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-RECON-s3 | • Confirm tool-only path (RAG not required) | SEGRO | ASSUMPTION |  |  | 20 | 2 | 20 | 21 | [19 empty] | 1 | 1 | [41 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-RECON-s4 | • Cosmos Mongo memory wiring for Recon discrepancy agent | SEGRO | ASSUMPTION |  |  | 22 | 2 | 22 | 23 | [21 empty] | 1 | 1 | [39 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-RECON-s5 | • Pilot → hypercare gate for Recon discrepancy agent | SEGRO | ASSUMPTION |  |  | 24 | 2 | 24 | 25 | [23 empty] | 1 | 1 | [37 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-R1 | Agent: R1 Content Agent (supervised pilot) [R-L40..R-L45] | SEGRO | ASSUMPTION | F5 | G-P2-FABRIC | 10 | 8 | 10 | 17 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [45 empty] | NAMED AGENT (which to build). Absent from HCL POAP (F5). Apps=[]; rag_required=False. Agents tab Include flag. [td_override=true]
G-AGT-R1-s1 | • Scope R1 Content Agent (supervised pilot) + eval golden-set hooks | SEGRO | ASSUMPTION |  |  | 10 | 2 | 10 | 11 | [9 empty] | 1 | 1 | [51 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-R1-s2 | • MCP tools via APIM into platform tools only + Entra NHI | SEGRO | ASSUMPTION |  |  | 12 | 2 | 12 | 13 | [11 empty] | 1 | 1 | [49 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-R1-s3 | • Confirm tool-only path (RAG not required) | SEGRO | ASSUMPTION |  |  | 14 | 2 | 14 | 15 | [13 empty] | 1 | 1 | [47 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-R1-s4 | • Cosmos Mongo memory wiring for R1 Content Agent (supervised pilot) | SEGRO | ASSUMPTION |  |  | 16 | 1 | 16 | 16 | [15 empty] | 1 | [46 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-R1-s5 | • Pilot → hypercare gate for R1 Content Agent (supervised pilot) | SEGRO | ASSUMPTION |  |  | 17 | 1 | 17 | 17 | [16 empty] | 1 | [45 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-ORCH | Agent: Platform orchestrator / supervisor agent [R-L40..R-L45] | SEGRO | ASSUMPTION | F5 | G-P2-FABRIC | 18 | 8 | 18 | 25 | [17 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [37 empty] | NAMED AGENT (which to build). Absent from HCL POAP (F5). Apps=[]; rag_required=False. Agents tab Include flag. [td_override=true]
G-AGT-ORCH-s1 | • Scope Platform orchestrator / supervisor agent + eval golden-set hooks | SEGRO | ASSUMPTION |  |  | 18 | 2 | 18 | 19 | [17 empty] | 1 | 1 | [43 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-ORCH-s2 | • MCP tools via APIM into platform tools only + Entra NHI | SEGRO | ASSUMPTION |  |  | 20 | 2 | 20 | 21 | [19 empty] | 1 | 1 | [41 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-ORCH-s3 | • Confirm tool-only path (RAG not required) | SEGRO | ASSUMPTION |  |  | 22 | 2 | 22 | 23 | [21 empty] | 1 | 1 | [39 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-ORCH-s4 | • Cosmos Mongo memory wiring for Platform orchestrator / supervisor agent | SEGRO | ASSUMPTION |  |  | 24 | 1 | 24 | 24 | [23 empty] | 1 | [38 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.
G-AGT-ORCH-s5 | • Pilot → hypercare gate for Platform orchestrator / supervisor agent | SEGRO | ASSUMPTION |  |  | 25 | 1 | 25 | 25 | [24 empty] | 1 | [37 empty] | Agent-stack build step (v3). Judgement split of parent window; not drawn on HCL POAP.

## Gantt - Revised
Gantt - Corrected — technical step decomposition per major line of work
The corrected sequence implementing review findings (F1/F2/F10/F16/F17/F19/F23/F26). Every window is RECOMMENDED — a proposed re-draw, not a committed plan. Cost totals are unchanged: windows move, quantities do not. The F1 re-anchor moves nominal go-live to week 31 (range weeks 29-33); the sheet renders BOTH the nominal marker and the range band, not a single committed date. Bars recalc live: SlipWeeks dilates TIME-DRIVEN windows (people + Azure commissioning) pro-rata — the same elongation the slip cost prices; FIXED-fee engagements (licences, third-party pen-test/red-team) shift but keep their duration; hypercare shifts whole. A ▶ in the Slip column flags any bar clipped at the grid edge under a large slip. Milestones: ▲ nominal go-live · ◁▷ F1 range band · ✕ Christmas · ! Bank holiday · ◆ drawn phase gate. Bar colours: SEGRO red · HCL dark blue · Azure mid blue · Third-party purple · corrected bars green (proposed, not committed).
[11 empty] | Jul 26 |  |  | Aug 26 |  |  |  |  | Sep 26 |  |  |  | Oct 26 |  |  |  | Nov 26 |  |  |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27
Id | Major line of work / technical step | Side | Status | Findings | Depends on | Start wk | Wks | Live start | Live end | Change vs as-drawn (per finding) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | Slip | Basis / source | 31 | 29 | 33
| Go-live range (F1) | [13 empty] | ◆ |  |  | ! | [12 empty] | ◆ |  |  | ✕ | ◆ |  |  |  | ◁ | · | ▲ | · | ▷
G-P2-L4-R | Build - SEGRO (pulled forward into Design) [P2-L4] | SEGRO | RECOMMENDED | F17 |  | 3 | 6 | 3 | 8 | Pulled forward from the full P2 span (weeks 6-15) to weeks 3-8 so security design completes before network build-out completes, not weeks after it. |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [54 empty] | F17: 'Front-load the security-design decisions that constrain network layout (segmentation model, WAF placement, private endpoints, API security) into the design phase or build weeks 1-2; keep only implementation hardening in the parallel bar' - the corrected bar starts week 3 in P1, alongside the Cyber Sec Workshop in the P1 workshop chain, and completes end of week 8 (first 3 weeks of P2), BEFORE the as-drawn network build-out (item 1, first ~half of the 10-week build) completes - avoiding rework of an already-provisioned network layout. Implementation hardening only remains in the parallel build bar per the recommendation. Quantity unchanged (25 pd likely, P2-L4).
G-P2-L4-R-s1 | • Security-design decisions that constrain network layout - segmentation model, WAF placement, private endpoints, API security - taken in the design phase alongside the Cyber Sec Workshop | SEGRO | RECOMMENDED |  |  | 3 | 3 | 3 | 5 |  |  |  | 1 | 1 | 1 | [57 empty] | F17: 'Front-load the security-design decisions that constrain network layout (segmentation model, WAF placement, private endpoints, API security) into the design phase or build weeks 1-2' - taken in P1 weeks 3-5 so they are settled before any network provisioning starts in P2.
G-P2-L4-R-s2 | • Complete remaining cyber security design - managed identities, Key Vault, secrets management, PAM - in build weeks 1-3, before network build-out completes | SEGRO | RECOMMENDED |  | G-P2-L4-R-s1 | 6 | 3 | 6 | 8 | [6 empty] | 1 | 1 | 1 | [54 empty] | F17: 'keep only implementation hardening in the parallel bar' - the design content completes by week 8, ahead of the network build-out finishing; only implementation hardening continues alongside the rest of the build.
G-P1-REV-R | Design & Plan | SEGRO | RECOMMENDED | F16 |  | 2 | 6 | 2 | 7 | New TAD/HLD/LLD review-and-revision track inside P1 extending 2 weeks into early P2; no as-drawn counterpart exists - the as-drawn plan has no review or revision cycle at all. |  | 1 | 1 | 1 | 1 | 1 | 1 | [55 empty] | F16: 'Publish a review/approval schedule per gating document (owner, turnaround SLA, revision allowance) and hold at least one built-in revision cycle before the build-start gate' - NEW explicit TAD/HLD/LLD review + revision track covering the 14 slide-5 design documents. One full revision loop for 14 documents does not fit inside the 5-week P1 window on top of authoring, so the track runs weeks 2-7, extending 2 weeks into early P2. Build-start impact, stated honestly: SEGRO build tasks gated on an approved TAD/HLD/LLD/DRG pack carry up to a 2-week start risk against the week-6 build start; this risk is absorbed in the go-live range shown in G-TEST-REANCHOR-R. No cost change - review effort sits inside the existing P1 role lines (P1-L1 to P1-L7), which is why no single cost_line is cited.
G-P1-REV-R-s1 | • Publish the review/approval schedule per gating document - owner, turnaround SLA, revision allowance - for all 14 slide-5 design documents (TAD, HLD, LLD, DRG pack and the rest) | SEGRO | RECOMMENDED |  |  | 2 | 1 | 2 | 2 |  |  | 1 | [60 empty] | F16: 'Publish a review/approval schedule per gating document (owner, turnaround SLA, revision allowance)' - schedule issued in week 2 so reviews can start as documents land.
G-P1-REV-R-s2 | • First-pass reviews of the 14 slide-5 design documents as they land through the P1 workshop chain | SEGRO | RECOMMENDED |  | G-P1-REV-R-s1 | 3 | 3 | 3 | 5 |  |  |  | 1 | 1 | 1 | [57 empty] | F16: reviews executed against the published schedule's 'turnaround SLA' during weeks 3-5, while the documents are being authored - not deferred past 'Design phase complete'.
G-P1-REV-R-s3 | • Built-in revision cycle: revise, re-review and approve the gating documents (TAD, HLD, LLD, DRG approval) before the build-start gate | SEGRO | RECOMMENDED |  | G-P1-REV-R-s2 | 6 | 2 | 6 | 7 | [6 empty] | 1 | 1 | [55 empty] | F16: 'hold at least one built-in revision cycle before the build-start gate' - the revision loop runs weeks 6-7 (early P2); build tasks gated on approved designs carry up to a 2-week start risk, noted in the parent basis.
G-P1-PROC-R | Decisions & procurement | SEGRO | RECOMMENDED | F10 |  | 1 | 5 | 1 | 5 | Procurement starts week 1 and runs 5 weeks with named owners and latest-order dates, replacing the drawn ~2.5-week allowance that starts mid-P1. | 1 | 1 | 1 | 1 | 1 | [57 empty] | F10: 'Add named procurement tasks with owners and latest-order dates back-planned from the HCL install start' - the corrected procurement track starts week 1 and runs the full 5-week P1 window (>=4 weeks), covering the Oracle 19 and Aerospike licence lead times (P1-L8, P1-L9) plus the MinIO EOL remediation scoping (P3-L8) and the ARO subscription branch if KDD-1 selects ARO. F10's evidence: the drawn bar is roughly a 2.5-2.7 week allowance starting mid-P1, which the senior architect independently challenged ('Procurrent of commercial components would take longer than 2 weeks'). Quantities unchanged - the licence lines remain RATE_MISSING at GBP 0 until quoted. cost_line is null (this track spans P1-L8/P1-L9 plus the P3-L8 MinIO remediation scoping and the conditional ARO subscription - no single cost-model id represents it); the covered lines are listed in 'covers'.
G-P1-PROC-R-s1 | • Name the procurement tasks with owners; back-plan latest-order dates from the corrected HCL install start (week 13) for Oracle 19, Aerospike, MinIO successor and the conditional ARO subscription | SEGRO | RECOMMENDED |  |  | 1 | 1 | 1 | 1 |  | 1 | [61 empty] | F10: 'Add named procurement tasks with owners and latest-order dates back-planned from the HCL install start' - done in week 1 so lead times run from the earliest possible date.
G-P1-PROC-R-s2 | • Issue quotes/orders for the long-lead commercial components: Oracle 19 (mandatory for Unica+ MaxAI CDM, P1-L8) and Aerospike edition/licence (P1-L9) | SEGRO | RECOMMENDED |  | G-P1-PROC-R-s1 | 2 | 2 | 2 | 3 |  |  | 1 | 1 | [59 empty] | F10: these items 'can gate the HCL install bar' per the finding - orders issued weeks 2-3 against the week-1 latest-order dates.
G-P1-PROC-R-s3 | • Track lead times and confirm delivery/entitlement against the latest-order dates before the Design phase complete gate | SEGRO | RECOMMENDED |  | G-P1-PROC-R-s2 | 4 | 2 | 4 | 5 |  |  |  |  | 1 | 1 | [57 empty] | F10: confirmation weeks 4-5 keeps the 'latest-order dates back-planned from the HCL install start' honest - any slip is visible ~8 weeks before the corrected HCL install start (week 13).
G-P2-L27-R | Build - SEGRO [P2-L27] | SEGRO | RECOMMENDED | F19 |  | 6 | 3 | 6 | 8 | Concentrated into the first 3 weeks of P2 (weeks 6-8) so pipelines and policy gates exist before workloads deploy, instead of running across the full 10-week build. | [5 empty] | 1 | 1 | 1 | [54 empty] | F19: 'Add a named DevSecOps workstream (IaC for foundations, policy-as-code, image scanning, CI/CD for platform and agent deployment) to the build phase; the workbook carries it as P2-L27' - placed in the FIRST 3 weeks of P2 (weeks 6-8) so pipelines and policy gates exist before workloads deploy onto the platform, rather than being spread across the full 10-week build where later workstreams would deploy without gates. Quantity unchanged (30 pd likely, P2-L27) - the same effort concentrated into a shorter elapsed window. PLANNING NOTE: 30 pd across 3 weeks implies ~2.0 DevSecOps FTE vs the P2-L27 profile of 0.6 FTE over 10 weeks - a resourcing assumption, not a cost change (pd constant); if 2.0 FTE is infeasible in the first 3 build weeks, spread to weeks 6-10 while still landing the pipelines before the bulk of workloads deploy, which is all F19 requires.
G-P2-L27-R-s1 | • IaC pipelines for foundations stood up first - before foundations provisioning scales | SEGRO | RECOMMENDED |  |  | 6 | 1 | 6 | 6 | [6 empty] | 1 | [56 empty] | F19: 'IaC for foundations' is the first named element of the recommended workstream - it must exist in week 6 so build item 1 provisions through pipelines, not by hand.
G-P2-L27-R-s2 | • Policy-as-code gates and image scanning wired into the pipelines | SEGRO | RECOMMENDED |  | G-P2-L27-R-s1 | 7 | 1 | 7 | 7 | [7 empty] | 1 | [55 empty] | F19: 'policy-as-code, image scanning' - gates live in week 7, ahead of shared-services and AKS workload deployments.
G-P2-L27-R-s3 | • CI/CD for platform and agent deployment operational; all subsequent P2/P3 deployments flow through the gated pipelines | SEGRO | RECOMMENDED |  | G-P2-L27-R-s2 | 8 | 1 | 8 | 8 | [8 empty] | 1 | [54 empty] | F19: 'CI/CD for platform and agent deployment' complete by end week 8 - the pipelines the slide-7 'CI/CD Configuration Document' describes now exist before the workloads they deploy.
G-P3-L1-R | Build - HCL [P3-L1] | HCL | RECOMMENDED | F2 | G-P1-PROC-R, G-P2-L27-R | 13 | 6 | 13 | 18 | Starts week 13 (once AKS hardening completes at end of SEGRO build week 7), overlapping the SEGRO build tail by 3 weeks instead of running strictly sequential from week 16. | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [44 empty] | F2: 'Re-plan the HCL install to start once the AKS platform is hardened (end of SEGRO week 6-7) rather than after the full SEGRO bar; validate the overlap window with HCL' - corrected start week 13 = end of SEGRO build week 7 (grid week 12), giving a 3-week overlap with the SEGRO build tail (weeks 13-15), inside F2's 2-4 week planning assumption. Later HCL scope (connectivity, routing, observability integration) is sequenced after the wider SEGRO stack completes at week 15. Priced via the model's OverlapWeeks lever: 'Priced via the OverlapWeeks input (Azure double-running saving only - person-days are not reduced by parallel working)' - the 90 pd likely quantity is unchanged; only elapsed double-running shortens. The install remains gated on KDD-1 closure per F3.
G-P3-L1-R-s1 | • HCL install base UnO platform onto the hardened AKS platform, overlapping the SEGRO build tail | HCL | RECOMMENDED |  |  | 13 | 2 | 13 | 14 | [13 empty] | 1 | 1 | [48 empty] | F2: 'start once the AKS platform is hardened (end of SEGRO week 6-7)' - the base install needs only the hardened AKS platform (SEGRO item 2), not the full stack, so it starts week 13 in parallel with the remaining SEGRO build.
G-P3-L1-R-s2 | • Install TX components (DX, Foundry) and run platform validation | HCL | RECOMMENDED |  | G-P3-L1-R-s1 | 15 | 2 | 15 | 16 | [15 empty] | 1 | 1 | [46 empty] | F2: overlap sequencing - component installs proceed while the SEGRO build completes (week 15); 'validate the overlap window with HCL' applies to this boundary.
G-P3-L1-R-s3 | • Connectivity, routing and observability integration against the completed SEGRO stack | HCL | RECOMMENDED |  | G-P3-L1-R-s2 | 17 | 2 | 17 | 18 | [17 empty] | 1 | 1 | [44 empty] | F2: the finding notes 'later HCL scope (connectivity, routing, gateways, certificates) depends on the wider stack' - so this step runs weeks 17-18, after the SEGRO build ends (week 15).
G-TEST-REANCHOR-R | Testing & Deploy (re-anchored) | SEGRO | RECOMMENDED | F1, F14, F23 | G-P3-L1-R | 19 | 13 | 19 | 31 | New re-anchoring task: SIT pulled left to mid-Nov (week 19), explicit Christmas freeze gap weeks 24-25, UAT in January weeks 26-27; go-live moves from end of week 29 to an honest week 29-33 range (ASSUMPTION-within-RECOMMENDED). | [18 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [31 empty] | F1: 'Pull testing left (start mid-Nov) or extend to 6 weeks crossing Christmas with an explicit freeze gap; do not book UAT sign-off or go/no-go inputs in the week of 21 Dec' - the corrected sequence does both: SIT/pen test start week 19 (w/c 16 Nov 2026 = mid-Nov, enabled by the F2 overlap ending the HCL install at week 18), an explicit freeze gap holds weeks 24-25 (Christmas), and UAT sign-off runs weeks 26-27, clear of w/c 21 Dec. Resulting go-live movement, stated HONESTLY as a range and labelled ASSUMPTION-within-RECOMMENDED: nominal go-live end of week 31 vs the as-drawn end of week 29, presented as a week 29-33 range (late Jan to late Feb 2027) - NOT a new committed date - because F14 says 'Present go-live as a range' until the Arch workshop confirms durations, and the range must absorb the F16 review-cycle build-start risk (up to 2 weeks). The week 29-33 band shown here is the mechanical Christmas-freeze + F16 floor; F14's own recommendation cites the wider Green Book ICT optimism-bias band (+3 to +16 wk, i.e. potentially into Q2 2027), which the SlipWeeks lever on the As-Drawn sheet prices beyond this floor - so the true upper bound is SlipWeeks-driven, not capped at week 33. No cost change: the P4/P5 quantities are unchanged; this task only re-anchors their windows (spans cost lines P4-L1 to P5-L5, so no single cost_line is cited).
G-TEST-REANCHOR-R-s1 | • SIT + pen test execution, pulled left to start mid-November | SEGRO | RECOMMENDED |  |  | 19 | 3 | 19 | 21 | [19 empty] | 1 | 1 | 1 | [41 empty] | F1: 'Pull testing left (start mid-Nov)' - week 19 is w/c 16 Nov 2026; possible because the overlapped HCL install (G-P3-L1-R) completes at week 18. The F7-booked pen test lands here, well clear of December.
G-TEST-REANCHOR-R-s2 | • HCL fix-and-retest window between the SIT defect surge and UAT (detail carried in G-P4-FIX-R - same window, not double-counted) | SEGRO | RECOMMENDED |  | G-TEST-REANCHOR-R-s1 | 22 | 2 | 22 | 23 | [22 empty] | 1 | 1 | [39 empty] | F23: 'Add an explicit fix-and-retest loop with an HCL turnaround SLA inside (or immediately after) the test window' - this step reserves the elapsed weeks in the re-anchored sequence; the task-level detail is G-P4-FIX-R.
G-TEST-REANCHOR-R-s3 | • Explicit Christmas freeze gap - no UAT sign-off, no go/no-go inputs, no cutover activity booked | SEGRO | RECOMMENDED |  | G-TEST-REANCHOR-R-s2 | 24 | 2 | 24 | 25 | [24 empty] | 1 | 1 | [37 empty] | F1: 'extend to 6 weeks crossing Christmas with an explicit freeze gap; do not book UAT sign-off or go/no-go inputs in the week of 21 Dec' - weeks 24-25 (w/c 21 Dec and 28 Dec) are held as a named freeze, not silently worked through.
G-TEST-REANCHOR-R-s4 | • UAT execution and sign-off, clear of the freeze | SEGRO | RECOMMENDED |  | G-TEST-REANCHOR-R-s3 | 26 | 2 | 26 | 27 | [26 empty] | 1 | 1 | [35 empty] | F1: 'do not book UAT sign-off or go/no-go inputs in the week of 21 Dec' - UAT runs weeks 26-27 (w/c 4 and 11 Jan 2027), after the freeze, with the fix-and-retest loop already complete.
G-TEST-REANCHOR-R-s5 | • Deploy: production readiness, go/no-go, migration execution, go-live within the stated range | SEGRO | RECOMMENDED |  | G-TEST-REANCHOR-R-s4 | 28 | 4 | 28 | 31 | [28 empty] | 1 | 1 | 1 | 1 | [31 empty] | F14: 'Present go-live as a range' - deploy runs weeks 28-31 with nominal go-live end of week 31; the movement vs the as-drawn week-29 go-live is labelled ASSUMPTION-within-RECOMMENDED and shown as a week 29-33 range, not a new committed date. The go/no-go gate (~week 30) takes the G-P4-L8-R red-team/audit outputs as named inputs.
G-P4-FIX-R | Testing [P4-L6] | HCL | RECOMMENDED | F23 | G-P3-L1-R | 22 | 2 | 22 | 23 | New 2-week explicit HCL fix-and-retest window inserted between SIT and UAT, with greenfield and brownfield retest coverage; no as-drawn counterpart exists. | [21 empty] | 1 | 1 | [39 empty] | F23: 'Add an explicit fix-and-retest loop with an HCL turnaround SLA inside (or immediately after) the test window, and state greenfield/brownfield coverage in the test scope; P4-L6 carries the HCL-side cost but the elapsed time must be planned' - NEW ~2-week window at weeks 22-23, between the SIT defect surge (weeks 19-21) and UAT (weeks 26-27) in the re-anchored sequence, so material HCL defects no longer slip the go/no-go directly. Cost unchanged: P4-L6 (20 pd likely) already carries the HCL-side effort; this task plans the elapsed time the as-drawn plan omitted.
G-P4-FIX-R-s1 | • HCL defect triage and fix under a stated turnaround SLA, on defects raised by SIT against HCL-installed components | HCL | RECOMMENDED |  |  | 22 | 1 | 22 | 22 | [22 empty] | 1 | [40 empty] | F23: 'an explicit fix-and-retest loop with an HCL turnaround SLA' - week 22 is the fix half of the loop; the SLA makes HCL turnaround a managed commitment rather than untimed goodwill.
G-P4-FIX-R-s2 | • Retest with explicit greenfield coverage (clean-install paths) AND brownfield coverage (integration with the existing estate) before UAT entry | HCL | RECOMMENDED |  | G-P4-FIX-R-s1 | 23 | 1 | 23 | 23 | [23 empty] | 1 | [39 empty] | F23: 'state greenfield/brownfield coverage in the test scope' - the architect flagged both scenarios need testing; the retest week exercises fixed components on both paths so UAT starts on a known-good baseline.
G-P4-L8-R | Testing [P4-L8] | ThirdParty | RECOMMENDED | F26 |  | 26 | 3 | 26 | 28 | Moved from inside the December test window to weeks 26-28 as a named go/no-go input completing immediately before the gate, clear of the Christmas freeze. | [25 empty] | 1 | 1 | 1 | [34 empty] | F26: 'Add a pre-go-live AI red-team exercise and audit dry-run as named go/no-go inputs (carried as P4-L8), plus a recurring cadence as agent surfaces and edge cases grow (R-L31)' - placed at weeks 26-28, late in the re-anchored test window running into the deploy start, completing BEFORE the go/no-go gate (~week 30 in G-TEST-REANCHOR-R-s5) so its findings are genuine gate inputs. It cannot sit earlier without landing in the Christmas freeze (weeks 24-25), which F1 rules out for go/no-go inputs. Cost unchanged: fixed engagement of 3-8 tester-days (P4-L8); the recurring cadence is already carried as R-L31 in the run model.
G-P4-L8-R-s1 | • AI red-team exercise on agent surfaces - prompt injection, tool-abuse/data-exfiltration, jailbreak testing | ThirdParty | RECOMMENDED |  |  | 26 | 1 | 26 | 26 | [26 empty] | 1 | [36 empty] | F26: 'Add a pre-go-live AI red-team exercise' - scope drawn from the finding's own list (prompt injection, data exfiltration via tools, jailbreaks); runs week 26 in parallel with UAT on the same environments.
G-P4-L8-R-s2 | • Audit dry-run against the platform's operational and governance evidence | ThirdParty | RECOMMENDED |  | G-P4-L8-R-s1 | 27 | 1 | 27 | 27 | [27 empty] | 1 | [35 empty] | F26: 'and audit dry-run' - the finding notes 'no audit dry-run precedes go-live on a platform whose product is agent behaviour'; week 27 closes that gap before the gate.
G-P4-L8-R-s3 | • Findings triage and red-team/audit report issued as named go/no-go inputs | ThirdParty | RECOMMENDED |  | G-P4-L8-R-s2 | 28 | 1 | 28 | 28 | [28 empty] | 1 | [34 empty] | F26: 'as named go/no-go inputs (carried as P4-L8)' - the report lands week 28, ahead of the go/no-go gate in the re-anchored deploy step (G-TEST-REANCHOR-R-s5).

## Control Panel>>>
SEGRO POAP Costings — Control Panel (all scenarios drive live)
Amber cells are editable inputs — change a toggle and every tab, total and chart recalculates live. Status labels: VERIFIED (grounded to source) / VERIFIED-ESTIMATE / INDICATIVE (list price, editable) / DERIVED (formula) / ASSUMPTION (stated basis, editable) / RATE_MISSING (no source rate — £0 until entered).
SCENARIO SWITCHES & LOADINGS
Include HCL delivery & licence lines | Include | ASSUMPTION | Includes/excludes all people_hcl rate lines and HCL RATE_MISSING licence/AMS input cells from build and run totals
Effort estimate basis | Likely | ASSUMPTION | Selects the effort column (low/likely/high person-days) used for all people cost lines
Container platform | AKS | ASSUMPTION | AKS: aks_standard_mgmt_hr flat per cluster. ARO: adds aro_openshift_licence_vcpu_hr per worker vCPU plus 3 control-plane node VMs. Note HCL's own matrix marks AKS x CDP = N
Number of environments | 4 | ASSUMPTION | Multiplies per-environment infrastructure lines (dev/test/preprod/prod)
Cluster topology | Single | ASSUMPTION | Open KDD (F3; CDP AKS incompatibility may force a split). Dual doubles cluster-level fees only (AKS mgmt fee, ARO control planes) - total worker-node count is workload-driven and does not double when the same workload is split across two clusters.
Node pool sizing | M | ASSUMPTION | Maps node pool SKU: S/M -> vm_d4s_v5_node_hr, L -> vm_d8s_v5_node_hr (S = fewer nodes of D4s_v5)
Blended day rate (GBP) - adjustable placeholder, RATE_MISSING in sources | 850 | ASSUMPTION | Overrides blended_day_rate for lines costed on the blended basis (role-specific lines keep their own VERIFIED medians)
Contingency % on build (HM Treasury ICT optimism-bias band is 10-200% on capex - 15% sits at the optimistic end) | 0.15 | ASSUMPTION | Uplift applied to build-phase totals
Annual indexation % on run costs | 0.03 | ASSUMPTION | Annual uplift applied to run-cost years 2-5
Schedule slip (weeks) | 0 | ASSUMPTION | Extends build-phase duration (and people cost) by N weeks; HM Treasury ICT duration optimism-bias is +10% to +54% (programme_benchmarks.json) as sensitivity anchors
Phase overlap (weeks) | 0 | ASSUMPTION | Weeks the HCL install runs PARALLEL to the SEGRO build. Models a COST saving only — nets off Azure environment double-running on the time-driven P1–P5 lines. It does NOT move the modelled go-live (the as-drawn Gantt draws HCL sequential — that is finding F2; the schedule benefit is shown on the Corr
Organisation headcount for per-user licences (brief assumed ~700; SEGRO ARA25 VERIFIED headcount is 463, average 454 - set to ~463 for ARA-anchored runs) | 700 | ASSUMPTION | Multiplies all per-user licence lines
Observability stack (Azure-native vs Datadog) | Azure | ASSUMPTION | Azure (default): Log Analytics + Azure Monitor (Azure-native). Datadog: APM + Infrastructure + LLM Observability metered SKUs (LLM spans) — a separate metered line Azure Monitor does not charge for. List prices are INDICATIVE ceilings; negotiated discount tier is RATE_MISSING.
Model vendor (Azure-served) | AzureOpenAI | ASSUMPTION | Azure-only serving plane family. Pair with ModelSKU.
Model SKU (GPT→5.6 / Claude→Fable / Grok→4.5 / Llama) | GPT-4o | ASSUMPTION | Foundation-model SKU. Default GPT-4o = headline continuity. Wrong-vendor SKUs evaluate to £0 via vendor_gate+model_gate. Llama uses GPU lines (not token mirrors).
Agent stack (MCP + RAG + memory) | Exclude | ASSUMPTION | Exclude (default): no MCP/RAG/memory/agent-intensity cost — headline-neutral. Include: ACA MCP × McpServerCount, APIM, embeddings, RAG shape, Cosmos memory × AgentCount.
RAG + memory store shape | AISearch_Cosmos | ASSUMPTION | AISearch_Cosmos: Azure AI Search + Cosmos Mongo memory. CosmosOnly: Cosmos for memory and vectors (AI Search £0).
Agent count (intensity calculator) | 1 | ASSUMPTION | Scales per-agent tokens/memory/embeddings when AgentStack=Include (1–100 guidance).
MCP server count (application plugs) | 2 | ASSUMPTION | Scales MCP Container Apps + APIM when AgentStack=Include (1–50 application plugs).
SCOPE NOTES
▪ HCL FLOOR caveat: all HCL licence/subscription/AMS lines (UnO, Unica+, CDP, DX, AMS) are RATE_MISSING at GBP 0 because HCL has not shared contract pricing. Any total that includes them is therefore a FLOOR, not an estimate - never present it as the expected HCL cost.
▪ INDICATIVE and VERIFIED prices are vendor LIST prices with no EA/MACC discount applied. Azure PAYG list is the ceiling: SEGRO's EA discount, 1-yr/3-yr reservations (typically 30-60% off VMs and databases) and savings plans would all reduce the infra figures. Microsoft GBP licence prices are paid-yea
▪ Headcount: SEGRO ARA25 (VERIFIED) reports 463 employees (average 454, of which 168 indirect/administration). The brief's ~700 figure is retained as the OrgSize toggle default per instruction, but per-user licence maths should be sanity-checked at ~463; the delta overstates per-user costs by ~50%.
▪ Contingency: the default 15% is an ASSUMPTION. HM Treasury Green Book optimism-bias guidance (programme_benchmarks.json, VERIFIED) puts Equipment/ICT-development capex uplift at 10% (lower bound, achievable at contract award with evidenced risk mitigation) to 200% (upper bound, the mandated starting
▪ FX: all USD-quoted sources convert at 0.74015 GBP/USD (ECB reference rate via Frankfurter API, 16 Jul 2026, VERIFIED in both people_rates.json and org_it_benchmarks.json). Converted lines are status INDICATIVE and show the arithmetic in notes - nothing converted silently.
▪ ServiceNow: no published list prices exist; the GBP 74.02/user/mo line is aggregator-sourced INDICATIVE, the adversarial verdict confirmed the source says per USER not per fulfiller, and ServiceNow moved to Foundation/Advanced/Prime packaging with a consumption meter in April 2026 - treat as an adju
▪ M365/Copilot baseline: SEGRO already licenses M365 and rolled Copilot out to all employees in 2025 (ARA25 p21). These lines are in the spec for completeness and marginal-cost modelling - treat core M365 + Copilot as existing baseline, not incremental POAP cost.
▪ Azure scope exclusions (will appear on a real bill but are not priced in the fact files): managed disks for node pools, bandwidth/egress, Azure Firewall, Private Link endpoints, backup storage. Defender for Cloud is carried explicitly as RATE_MISSING. Log Analytics ingestion is the most under-estima
▪ Training: no authoritative per-rollout per-employee figure exists (RATE_MISSING, GBP 0 adjustable). The Training Magazine USD 774/learner/yr (~GBP 573) enterprise average is INDICATIVE context for annual all-training spend only - not a rollout unit cost.
▪ Maker/verifier provenance: all four source fact files carry APPROVE verdicts in workbook_build/poap/verdicts/ (17 Jul 2026). Every VERIFIED value_gbp in this spec is copied unchanged from its fact file; DERIVED/INDICATIVE lines state their arithmetic; nothing is invented at spec time.

## Rates
Rates — every figure on this tab is an editable input
Azure rates VERIFIED from the Azure Retail Prices API (GBP, uksouth); people rates VERIFIED from ITJobsWatch / G-Cloud 14 published rate cards; RATE_MISSING lines are £0 until a real rate is supplied. Sources cited per row.
AZURE — COMPUTE & PLATFORM
Rate | Unit | Value (£) | Status | Source | Notes
AKS cluster management - Standard tier (Uptime SLA) | per cluster per hour | 0.0758 | VERIFIED | azure_infra_rates.json: AKS cluster management - Standard tier (Uptime SLA), as-of 2026-07-16 | ~GBP 55.3/cluster/month at 730 hrs. Production default tier. Azure Retail Prices API, uksouth, PAYG.
AKS node - Standard_D4s_v5 (4 vCPU / 16 GiB) Linux | per node per hour | 0.1682 | VERIFIED | azure_infra_rates.json: VM Standard_D4s_v5 (4 vCPU / 16 GiB) Linux - AKS node pool, as-of 2026-07-16 | ~GBP 122.8/month at 730 hrs. OS disk billed separately. Candidate NodeSize=S/M mapping.
VM Standard_D4ds_v5 (4 vCPU / 16 GiB / local temp disk) Linux — ARO minimum worker family | per node per hour | 0.1985 | VERIFIED | facts/azure_infra_rates.json: 'VM Standard_D4ds_v5 (4 vCPU / 16 GiB / local temp disk) Linux', as_of 2026-07-1 | Ddsv5 (with local disk) is the ARO minimum-spec worker family per the fact file. Used for the ARO branch worker lines; AKS branch uses D4s_v5.
AKS node - Standard_D8s_v5 (8 vCPU / 32 GiB) Linux | per node per hour | 0.3364 | VERIFIED | azure_infra_rates.json: VM Standard_D8s_v5 (8 vCPU / 32 GiB) Linux - AKS node pool, as-of 2026-07-16 | ~GBP 245.6/month at 730 hrs. Candidate NodeSize=L mapping.
ARO OpenShift worker licence uplift (General Purpose) | per vCPU per hour | 0.0324 | VERIFIED | azure_infra_rates.json: Azure Red Hat OpenShift (ARO) - OpenShift worker licence uplift, General Purpose, as-o | Charged on top of base Linux VM rate per worker node: 4 vCPU = 0.1296/hr, 8 vCPU = 0.2591/hr. ARO also needs 3 control-plane nodes billed as plain VMs. Drives t
AZURE — DATA SERVICES
Rate | Unit | Value (£) | Status | Source | Notes
PostgreSQL Flexible Server - GP D4ds_v5 (4 vCore) compute | per hour | 0.3121 | VERIFIED | azure_infra_rates.json: Azure Database for PostgreSQL Flexible Server - General Purpose D4ds_v5 (4 vCore) comp | ~GBP 227.8/month at 730 hrs. Per-vCore rate 0.078/hr scales linearly. Storage extra (separate line).
PostgreSQL Flexible Server - provisioned storage | per GB per month | 0.1008 | VERIFIED | azure_infra_rates.json: Azure Database for PostgreSQL Flexible Server - storage, as-of 2026-07-16 | Backup storage up to 100% of provisioned is free; excess billed separately.
Azure SQL Database - General Purpose Gen5, 4 vCore (provisioned) | per hour | 0.5766 | VERIFIED | azure_infra_rates.json: Azure SQL Database - General Purpose Gen5, 4 vCore (provisioned, single DB), as-of 202 | ~GBP 421/month at 730 hrs. PAYG rate includes SQL licence; storage billed separately.
Cosmos DB - serverless request units | per 1 million RUs consumed | 0.225 | VERIFIED | azure_infra_rates.json: Cosmos DB - serverless request units, as-of 2026-07-16 | Best for spiky/low agent-state workloads; no minimum. Storage billed separately.
Event Hubs - Standard tier, Throughput Unit | per Throughput Unit per hour | 0.0227 | VERIFIED | azure_infra_rates.json: Event Hubs - Standard tier, Throughput Unit, as-of 2026-07-16 | ~GBP 16.6/TU/month; 1 TU = 1 MB/s ingress. Ingress events charged additionally at 0.0212 per 1M events (same source file).
Azure Cache for Redis - Standard C1 (1 GB, replicated) | per cache per hour | 0.1311 | VERIFIED | azure_infra_rates.json: Azure Cache for Redis - Standard C1 (1 GB, replicated), as-of 2026-07-16 | ~GBP 95.7/month.
AZURE — NETWORKING
Rate | Unit | Value (£) | Status | Source | Notes
Application Gateway WAF_v2 - fixed gateway cost | per gateway per hour | 0.3409 | VERIFIED | azure_infra_rates.json: Application Gateway WAF_v2 - fixed gateway cost, as-of 2026-07-16 | ~GBP 248.9/month fixed, plus capacity units. WAF policies included in v2 SKU.
Application Gateway WAF_v2 - capacity unit | per capacity unit per hour | 0.0109 | VERIFIED | azure_infra_rates.json: Application Gateway WAF_v2 - capacity unit, as-of 2026-07-16 | Typical small prod ~10 CU avg adds ~GBP 79.6/month.
API Management - Standard tier (classic) | per unit per hour | 0.7127 | VERIFIED | azure_infra_rates.json: API Management - Standard tier (classic), as-of 2026-07-16 | ~GBP 520.3/unit/month. SEGRO already runs APIM (all integration via APIM per architecture principles) - existing estate APIM may absorb this; treat as marginal-
VPN Gateway - VpnGw1 | per gateway per hour | 0.1439 | VERIFIED | azure_infra_rates.json: VPN Gateway - VpnGw1, as-of 2026-07-16 | ~GBP 105/month. SEGRO single-tenant Azure estate likely already has connectivity - marginal cost may be nil.
Azure Private DNS - hosted zone | per zone per month (first 25 zones) | 0.3788 | VERIFIED | azure_infra_rates.json: Azure Private DNS - hosted zone, as-of 2026-07-16 | Zones 26+ at 0.0758/zone/month. Billed globally, not per region.
AZURE — OBSERVABILITY
Rate | Unit | Value (£) | Status | Source | Notes
Log Analytics - PAYG data ingestion (Analytics Logs) | per GB ingested | 2.1819 | VERIFIED | azure_infra_rates.json: Log Analytics - Pay-As-You-Go data ingestion (Analytics Logs), as-of 2026-07-16 | First 5 GB/month free. Single biggest observability cost driver for agent platforms - budget by GB/day. Basic Logs alternative 0.4735/GB (same source file).
Azure Monitor - metric alert rule | per monitored metric timeseries per month | 0.0758 | VERIFIED | azure_infra_rates.json: Azure Monitor - metric alert rule (per monitored metric timeseries), as-of 2026-07-16 | First 10 metric timeseries free. Log alert at 5-min frequency 0.1136/rule/month.
OBSERVABILITY — DATADOG (Observability=Datadog branch)
Rate | Unit | Value (£) | Status | Source | Notes
Datadog LLM Observability (Agent Observability) - Pro tier, up to 100K LLM spans (annual/c | per month, includes up to 100,000 LLM spans | 118.42 | INDICATIVE | datadoghq.com/product/llm-observability - Pro tier USD 160/month, up to 100K LLM spans, 15-day retention (annu | USD 160 x 0.74015 = 118.424, rounded 118.42. Billing unit = LLM span, defined by Datadog as 'a single call to an LLM provider' - tool/workflow/agent/embedding/r
Datadog LLM Observability - on-demand, first 100K LLM spans | per month, for first 100,000 LLM spans | 177.64 | INDICATIVE | datadoghq.com/pricing/list - Agent Observability 'For first 100k LLM spans, per month' on-demand USD 240, fetc | USD 240 x 0.74015 = 177.636, rounded 177.64. On-demand (uncommitted) list price for the same 100K-span base tier that costs USD 160 committed - i.e. the committ
Datadog LLM Observability - overage per additional 10K LLM spans (on-demand) | per 10,000 additional LLM spans per month | 3.7 | INDICATIVE | datadoghq.com/pricing/list - Agent Observability 'Per 10K additional LLM spans, per month' on-demand USD 5, fe | USD 5 x 0.74015 = 3.70075, rounded 3.70. Charged for LLM spans beyond the 100K included in the base tier. This is the true volume driver for an agent platform:
Datadog APM (Application Performance Monitoring) - per host per month (annual, with Infras | per APM host per month, billed annually | 22.94 | INDICATIVE | datadoghq.com/pricing - APM 'Per host, per month' USD 31 billed annually (with Infrastructure Monitoring attac | USD 31 x 0.74015 = 22.94465, rounded 22.94. This is the INFRA-ATTACHED APM rate. Per Datadog's pricing page, the attached rate REQUIRES a paired Pro/Enterprise
Datadog APM (Application Performance Monitoring) - per host per month (annual, STANDALONE | per APM host per month, billed annually | 26.65 | INDICATIVE | datadoghq.com/pricing - APM standalone 'Per host, per month' USD 36 billed annually (rate quoted when Infrastr | USD 36 x 0.74015 = 26.6454, rounded 26.65. The STANDALONE APM rate — used ONLY when Infrastructure Monitoring is NOT bought at all on the host. It is HIGHER tha
Datadog Infrastructure Monitoring - Pro tier, per host per month (annual) | per infra host per month, billed annually | 11.1 | INDICATIVE | datadoghq.com/pricing - Infrastructure Monitoring Pro 'Per host, per month' USD 15 billed annually (or USD 18 | USD 15 x 0.74015 = 11.10225, rounded 11.10. The foundational per-host SKU; APM is typically attached to it (the USD 31 APM line above assumes Infra attached). V
Datadog enterprise committed-annual-spend discount tier (negotiated) | GBP per year (committed spend / EA discount) | 0 | RATE_MISSING | Not published - Datadog volume/multi-year discounts are quote-only ('Multi-Year/Volume discounts available', c | £0 until a rate is supplied. Adjustable input defaulting to 0. Datadog's public list prices above are the pre-negotiation CEILING; enterprise agreements with co
AZURE — SECURITY
Rate | Unit | Value (£) | Status | Source | Notes
Key Vault - operations (secrets/software keys) | per 10,000 operations | 0.0227 | VERIFIED | azure_infra_rates.json: Key Vault - operations (Standard and Premium, secrets/software keys), as-of 2026-07-16 | Negligible at platform scale (millions of ops = a few GBP).
Microsoft Defender for Cloud (workload protection plans) | per resource per month | 0 | RATE_MISSING | azure_infra_rates.json narrative_notes: explicitly listed under 'Excluded (not in scope of the request, but wi | £0 until a rate is supplied. Not priced in the fact files - adjustable input defaulting to 0. Defender plans are per-resource-type (servers, containers, databas
FOUNDATION MODEL — SELF-HOSTED SERVING (ModelVendor=Llama)
Rate | Unit | Value (£) | Status | Source | Notes
Azure GPU VM Standard_NC24ads_A100_v4 (1x NVIDIA A100 80GB / 24 vCPU / 220 GiB) Linux - si | per node per hour | 3.4782 | VERIFIED | Azure Retail Prices API, uksouth, Consumption (PAYG): armSkuName 'Standard_NC24ads_A100_v4', productName 'NCad | LLAMA branch (self-hosted). Modest, defensible single-GPU serving SKU for a single-model inference pool (1x A100 80GB serves a quantised ~70B or smaller Llama c
Azure GPU VM Standard_NC40ads_H100_v5 (1x NVIDIA H100 NVL 94GB / 40 vCPU) Linux - higher-t | per node per hour | 6.6101 | VERIFIED | Azure Retail Prices API, uksouth, Consumption (PAYG): armSkuName 'Standard_NC40ads_H100_v5', productName 'Virt | LLAMA branch alternative. Newer H100-class single-GPU node for larger models or higher throughput than the A100 line above. ~GBP 4825.37/node/month at 730 hrs.
Azure GPU capacity - quota request / reserved-capacity commitment (procurement act) | per procurement (one-off / annual commitment) | 0 | RATE_MISSING | No clean public unit price - Azure GPU (NC/ND-series) capacity requires a quota-increase request and, at scale | £0 until a rate is supplied. LLAMA branch. Adjustable input cell defaulting to GBP 0 - never a verified figure. Same RATE_MISSING procurement FAMILY as the exis
FOUNDATION MODEL — AZURE-SERVED TOKENS (ModelSKU ladder)
Rate | Unit | Value (£) | Status | Source | Notes
Anthropic Claude Sonnet (current production tier) - input tokens, standard list | GBP per 1M input tokens | 2.22 | INDICATIVE | Anthropic pricing (platform.claude.com/docs pricing table, fetched 2026-07-18): Claude Sonnet 5 base input USD | CLAUDE branch (hosted API) - token meters only, like the existing Azure OpenAI GPT-4o pattern (aoai_gpt4o_input_1m_tokens). NO GPU node and NO inference-ops FTE
Anthropic Claude Sonnet (current production tier) - output tokens, standard list | GBP per 1M output tokens | 11.1 | INDICATIVE | Anthropic pricing (platform.claude.com/docs pricing table, fetched 2026-07-18): Claude Sonnet 5 output USD 15. | CLAUDE branch. Standard list USD 15/MTok out. INTRODUCTORY USD 10/MTok out through 31 Aug 2026 (= GBP 7.40) then reverts to USD 15 - use the standard 11.10 as t
Azure OpenAI GPT-4.1 — input tokens, Global, uksouth | GBP per 1M input tokens | 1.5 | VERIFIED | Azure Retail API uksouth meter 'gpt 4.1 Inp glbl Tokens' £0.0015/1K, retrieved 2026-07-19 | Cheaper than GPT-4o; AzureOpenAI ladder.
Azure OpenAI GPT-4.1 — output tokens, Global, uksouth | GBP per 1M output tokens | 6.1 | VERIFIED | Azure Retail API uksouth meter 'gpt 4.1 Outp glbl Tokens' £0.0061/1K, retrieved 2026-07-19
Azure OpenAI / Foundry GPT-5.6 Terra — input (Azure-served list) | GBP per 1M input tokens | 1.8504 | INDICATIVE | OpenAI list USD 2.50/MTok × 0.74015; no Azure Retail meter yet 2026-07-19 | Balance tier of GPT-5.6 family. INDICATIVE until uksouth meter publishes.
Azure OpenAI / Foundry GPT-5.6 Terra — output (Azure-served list) | GBP per 1M output tokens | 11.1022 | INDICATIVE | OpenAI list USD 15.00/MTok × 0.74015
Azure OpenAI / Foundry GPT-5.6 Sol — input (Azure-served list) | GBP per 1M input tokens | 3.7007 | INDICATIVE | OpenAI list USD 5.00/MTok × 0.74015; no Azure Retail meter yet 2026-07-19 | Frontier tier. INDICATIVE until uksouth meter publishes.
Azure OpenAI / Foundry GPT-5.6 Sol — output (Azure-served list) | GBP per 1M output tokens | 22.2045 | INDICATIVE | OpenAI list USD 30.00/MTok × 0.74015
Claude Fable 5 on Azure — input tokens, standard list | GBP per 1M input tokens | 7.4015 | INDICATIVE | Anthropic Claude Fable 5 USD 10/MTok × 0.74015; Azure-served (Foundry/BYOK) | ClaudeOnAzure top of ladder.
Claude Fable 5 on Azure — output tokens, standard list | GBP per 1M output tokens | 37.0075 | INDICATIVE | Anthropic Claude Fable 5 USD 50/MTok × 0.74015
Grok 4.3 on Azure AI Foundry — input (<200k) | GBP per 1M input tokens | 0.9252 | INDICATIVE | xAI/Foundry list USD 1.25/MTok × 0.74015 | GrokOnAzure mid tier.
Grok 4.3 on Azure AI Foundry — output (<200k) | GBP per 1M output tokens | 1.8504 | INDICATIVE | xAI/Foundry list USD 2.50/MTok × 0.74015
Grok 4.5 on Azure AI Foundry — input (<200k) | GBP per 1M input tokens | 1.4803 | INDICATIVE | xAI docs grok-4.5 USD 2.00/MTok × 0.74015 | GrokOnAzure top of ladder.
Grok 4.5 on Azure AI Foundry — output (<200k) | GBP per 1M output tokens | 4.4409 | INDICATIVE | xAI docs grok-4.5 USD 6.00/MTok × 0.74015
Azure OpenAI text-embedding-ada — tokens, Global uksouth | GBP per 1M tokens | 0.1 | VERIFIED | Azure Retail API uksouth meter 'embedding-ada-glbl Tokens' £0.0001/1K, retrieved 2026-07-19 | RAG embedding meter.
FOUNDATION MODEL — INFERENCE-OPS (ModelVendor=Llama)
Rate | Unit | Value (£) | Status | Source | Notes
MLOps engineer contractor day rate (UK median) - basis for the inference-ops uplift | GBP per day | 575 | VERIFIED | ITJobsWatch - MLOps contracts UK, 6 months to 18 Jul 2026 (242 rate quotes): median GBP 575/day, 25th pct 500, | LLAMA branch. The day rate itself is VERIFIED (ITJobsWatch median, 242 quotes). It is the RATE basis for the inference-ops FTE uplift line below - self-hosting
Inference-ops run-team uplift for self-hosted model serving (FTE fraction of an MLOps engi | FTE fraction (of mlops_engineer_contractor_day) - | 0 | ASSUMPTION | No published per-platform headcount figure. Expressed as a basis: 0.2-0.5 FTE of an MLOps engineer at the VERI | LLAMA branch ONLY. Value shipped as 0 (adjustable) so a total never silently bakes in an invented headcount; the intended live cell = FTE_fraction x 575 x worki
AGENT STACK — MCP / RAG / MEMORY (AgentStack=Include)
Rate | Unit | Value (£) | Status | Source | Notes
Azure Container Apps — active vCPU-second (MCP hosting) | per vCPU-second | 2e-05 | INDICATIVE | tco/facts/azure_rates.json aca_vcpu_second (Retail API £0 free-grant; USD list converted) | Per MCP server scale via McpServerCount.
Azure Container Apps — active GiB-second (MCP hosting) | per GiB-second | 2.5e-06 | INDICATIVE | tco/facts/azure_rates.json aca_gib_second
APIM — marginal call unit (derived from Standard tier capacity ASSUMPTION) | GBP per 1K calls | 0.043 | ASSUMPTION | Derived: APIM Standard ~£520.27/mo (tco azure_rates VERIFIED-lineage INDICATIVE) / ~12M calls/mo capacity floo | SEGRO principle: all MCP behind APIM. Not a published per-call meter — ASSUMPTION unit for estate scaling.
Azure AI Search Basic — search unit hour | per unit-hour | 0.0842 | VERIFIED | Azure Retail API uksouth meter 'Basic CC Unit' product Azure AI Search £0.0842/hr, retrieved 2026-07-19 | Active when RagMemoryShape=AISearch_Cosmos.
Azure Cosmos DB autoscale — 100 RU/s hour (Mongo API memory/vector) | per 100 RU/s per hour | 0.0091 | VERIFIED | Azure Retail API uksouth Cosmos DB autoscale 100 RUs £0.0091/hr, retrieved 2026-07-19 | Agent memory always; vectors when CosmosOnly.
PEOPLE — SEGRO INTERNAL
Rate | Unit | Value (£) | Status | Source | Notes
SEGRO internal fully-loaded FTE cost (platform engineer) | GBP per FTE per year | 95000 | ASSUMPTION | Not in fact files - ASSUMPTION per brief | Rationale: UK fully-loaded platform engineer cost (salary + NI + pension + overheads), consistent with the existing TCO workbook input. Adjustable. Context only
PEOPLE — UK CONTRACTOR MARKET (ITJobsWatch medians)
Rate | Unit | Value (£) | Status | Source | Notes
Platform Engineer contractor day rate (UK median) | GBP per day | 525 | VERIFIED | people_rates.json: Platform Engineer contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026), as | Median of 362 rate quotes; 25th pct 481, 75th pct 624. London median 581.
DevOps Engineer contractor day rate (UK median) | GBP per day | 525 | VERIFIED | people_rates.json: DevOps Engineer contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026), as-o | 25th pct 449, 75th pct 613.
Kubernetes-skill contractor day rate (UK median) | GBP per day | 535 | VERIFIED | people_rates.json: Kubernetes (skill) contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026), a | Median of 1,819 rate quotes; 25th pct 459, 75th pct 624.
Cloud Security contractor day rate (UK median) | GBP per day | 550 | VERIFIED | people_rates.json: Cloud Security (skill) contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026 | Median of 687 rate quotes; 25th pct 481, 75th pct 650.
Solutions Architect contractor day rate (UK median) | GBP per day | 625 | VERIFIED | people_rates.json: Solutions Architect contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026), | Median of 1,120 rate quotes; 25th pct 525, 75th pct 725.
Project Manager contractor day rate (UK median) | GBP per day | 535 | VERIFIED | people_rates.json: Project Manager contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026), as-o | 25th pct 450, 75th pct 625. Delivery Manager median 533 (same source file) if that role label is preferred.
Test Engineer contractor day rate (UK median) | GBP per day | 431 | VERIFIED | people_rates.json: Test Engineer contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026), as-of | Median of 206 rate quotes; 25th pct 363, 75th pct 538. SDET median 453 (small sample, 49 quotes).
Test Manager contractor day rate (UK median) | GBP per day | 515 | VERIFIED | people_rates.json: Test Manager contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026), as-of 2 | 25th pct 450, 75th pct 600.
Data Engineer contractor day rate (UK median) | GBP per day | 500 | VERIFIED | people_rates.json: Data Engineer contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026), as-of | Median of 1,322 rate quotes; 25th pct 425, 75th pct 588.
Business Analyst contractor day rate (UK median) | GBP per day | 500 | VERIFIED | people_rates.json: Business Analyst contractor median day rate, UK (ITJobsWatch, 6 months to 16 Jul 2026), as- | Median of 1,430 rate quotes; 25th pct 413, 75th pct 588.
Blended delivery day rate (adjustable placeholder) | GBP per day | 850 | ASSUMPTION | people_rates.json: Tier-1 Indian SI blended onshore/offshore day rate = RATE_MISSING (no public analyst-publis | RATE_MISSING in sources; ships as a visible, user-adjustable GBP 850 placeholder per project convention (same treatment as the TCO workbook). Sits between ITJob
PEOPLE — HCL (G-Cloud 14 published rate card)
Rate | Unit | Value (£) | Status | Source | Notes
HCL G-Cloud 14 SFIA rate - Solution development & implementation, Level 3 (Apply) | GBP per day (8-hr day excl. travel/lunch) | 950 | VERIFIED | people_rates.json: HCLTech G-Cloud 14 SFIA rate card - Solution development & implementation, Level 3 (Apply), | HCL's own published UK public-sector ceiling rate (SFIA card, Oct 2024). Grid context: L1 750 / L2 850 / L3 950 / L4 1050 / L5 1150 / L6 1250 / L7 1850; Strateg
HCL G-Cloud 14 published day-rate range - floor | GBP per day | 550 | VERIFIED | people_rates.json: HCLTech G-Cloud 14 Cloud Application Services day-rate range (published) 550-1650, as-of 20 | Low end of HCL's published SFIA-graded band (UK Digital Marketplace service 613304395170242). Per HCL's pricing document the card includes offshore India delive
HCL G-Cloud 14 published day-rate range - ceiling | GBP per day | 1650 | VERIFIED | people_rates.json: HCLTech G-Cloud 14 Cloud Application Services day-rate range (published) 550-1650, as-of 20 | High end of HCL's published band. Note the SFIA card itself lists Strategy & architecture L7 at 2050 for that category (same source file); 1650 is the range pub
LICENCES & SUBSCRIPTIONS
Rate | Unit | Value (£) | Status | Source | Notes
Microsoft 365 E3 (with Teams) | GBP per user per month (paid yearly, annual commit | 33.5 | VERIFIED | org_it_benchmarks.json: Microsoft 365 E3 (with Teams), Microsoft UK pricing page fetched 16 Jul 2026 | E3 without Teams: 27.00. Monthly-billed annual-term subs carry +5% premium (since 1 Apr 2025). SEGRO baseline - treat as existing cost, not incremental.
Microsoft 365 E5 (with Teams) | GBP per user per month (paid yearly, annual commit | 51.6 | VERIFIED | org_it_benchmarks.json: Microsoft 365 E5 (with Teams), Microsoft UK pricing page fetched 16 Jul 2026 | E5 without Teams: 45.00.
Microsoft 365 Copilot add-on | GBP per user per month (annual subscription, ex VA | 23.1 | VERIFIED | org_it_benchmarks.json: Microsoft 365 Copilot add-on, Microsoft UK pricing page fetched 16 Jul 2026 | SEGRO already rolled Copilot out to all employees in 2025 (ARA25 p21) - existing baseline, not incremental to POAP.
Microsoft Entra ID P1 | GBP per user per month (paid yearly, annual commit | 5.4 | VERIFIED | org_it_benchmarks.json: Microsoft Entra ID P1, Microsoft Entra UK pricing page fetched 16 Jul 2026 | Included in M365 E3 - relevant only for standalone licensing (e.g. service identities).
Microsoft Entra ID P2 | GBP per user per month (paid yearly, annual commit | 7.7 | VERIFIED | org_it_benchmarks.json: Microsoft Entra ID P2, Microsoft Entra UK pricing page fetched 16 Jul 2026 | Included in M365 E5.
Power BI Pro | GBP per user per month (paid yearly, ex VAT) | 10.8 | VERIFIED | org_it_benchmarks.json: Power BI Pro, Microsoft Power BI UK pricing page fetched 16 Jul 2026 | Included in E5. Premium Per User 18.50 (same source file) if step-up needed.
ServiceNow ITSM Standard (indicative per-user) | GBP per user per month | 74.02 | INDICATIVE | org_it_benchmarks.json: ServiceNow ITSM Standard USD 100/user/mo (NowTribe aggregator, Feb 2026) converted at | USD 100 x 0.74015 = 74.015, rounded 74.02. Adversarial verdict (org_it_benchmarks.verdict.json MINOR): source says per USER, not per fulfiller - only the Pro US
HCL UnO (Universal Orchestrator) platform licence/subscription | GBP per year | 0 | RATE_MISSING | Not in any fact file - HCL contract/price list not shared with SEGRO | £0 until a rate is supplied. Adjustable input defaulting to 0. Any total excluding this line is a FLOOR, not an estimate.
HCL Unica+ licence/subscription | GBP per year | 0 | RATE_MISSING | Not in any fact file - HCL contract/price list not shared with SEGRO | £0 until a rate is supplied. Adjustable input defaulting to 0.
HCL CDP licence/subscription | GBP per year | 0 | RATE_MISSING | Not in any fact file - HCL contract/price list not shared with SEGRO | £0 until a rate is supplied. Adjustable input defaulting to 0. Note HCL's own compatibility matrix marks AKS x CDP = N (hcl_v1 evidence) - relevant to the Platf
HCL DX licence/subscription | GBP per year | 0 | RATE_MISSING | Not in any fact file - HCL contract/price list not shared with SEGRO | £0 until a rate is supplied. Adjustable input defaulting to 0.
SERVICES (pen test, training, tooling)
Rate | Unit | Value (£) | Status | Source | Notes
CREST penetration testing day rate (mid of published G-Cloud bands) | GBP per day | 950 | DERIVED | people_rates.json: CREST penetration testing day rate, UK - DigitalXRAID G-Cloud 14 range 800-1250 AND Stratia | GBP 950/day DERIVED as the midpoint of the combined CREST-accredited UK day-rate range GBP 650-1250 ((650+1250)/2 = 950), spanning the two published bands in pe
HCL AMS / ongoing support & maintenance | GBP per year | 0 | RATE_MISSING | Not in any fact file - HCL contract/price list not shared with SEGRO | £0 until a rate is supplied. Adjustable input defaulting to 0. HM Treasury outsourcing (ICT services) optimism-bias upper bound is +41% on opex (programme_bench
OTHER
Rate | Unit | Value (£) | Status | Source | Notes
Azure OpenAI GPT-4o (2024-11-20) - input tokens, Global deployment | GBP per 1M input tokens | 1.9 | VERIFIED | org_it_benchmarks.json: Azure OpenAI GPT-4o input tokens, Azure Retail Prices API uksouth meter 'gpt 4o 1120 I | Consumption meter, not a licence. Cached input 0.90/1M. Regional (UK data residency) deployments ~20% more. GPT-4.1 is cheaper (1.50 in / 6.10 out) and GPT-4o m
Azure OpenAI GPT-4o (2024-11-20) - output tokens, Global deployment | GBP per 1M output tokens | 7.6 | VERIFIED | org_it_benchmarks.json: Azure OpenAI GPT-4o output tokens, Azure Retail Prices API uksouth meter 'gpt 4o 1120 | Batch API halves this (3.80/1M).
Training cost per employee for this platform rollout (one-off) | GBP per employee per rollout | 0 | RATE_MISSING | people_rates.json: Training cost per employee for THIS platform rollout (per-user, one-off) = RATE_MISSING (no | £0 until a rate is supplied. Adjustable input defaulting to 0. INDICATIVE context only: Training Magazine 2024 enterprise average USD 774/learner/YEAR (~GBP 573

## POAP Build Cost
POAP Build Cost — phase by phase (aligned to POAP slide 3)
Scenario: effort = Likely · HCL = Include · platform = AKS · sku = GPT-4o · agents = Exclude · obs = Azure · envs = 4 · clusters = Single · node size = M · day rate £850 · slip = 0 wk · overlap = 0 wk
P1 — DESIGN & PLAN (5 wk, from 2026-07-13, Slide 3: Design & Plan bar '5 weeks' x=1.98-4.52; workshop chain (Arch kick-off, Sizing, Cyber, IAM, Data Mgmt); KDD + procurement lane)
Cost line | Side | Quantity model | Qty Low | Qty Likely | Qty High | Qty (live) | Rate/unit £ | Cost £ (live) | Status | Basis / source | Schedule
Solutions architect - workshop lead, HLD/LLD, target arch for EA, KDD papers (AKS v ARO, env count, cluster topology) | SEGRO | 1 FTE x 5 wk x 5 d = 25 days | 20 | 25 | 30 | 25 | 625 | 15625 | ASSUMPTION | Team size ASSUMPTION: slide 3 workshop chain + slide 5 doc list (HLD, LLD, TCO for options, KDDs) need a full-time architect for the 5-wk phase. Rate VERIFIED (ITJobsWatch median). | TD
Platform engineer - sizing workshop, physical infrastructure diagrams, physical sizing of infrastructure | SEGRO | 0.6 FTE x 5 wk x 5 d = 15 days | 10 | 15 | 25 | 15 | 525 | 7875 | ASSUMPTION | ASSUMPTION: slide 5 requires 'Physical sizing of infrastructure' + 'Physical Low Level Technical Arch Diagrams'. Rate VERIFIED. | TD
Cloud security - Cyber Sec Workshop, cyber security impact analysis + diagrams | SEGRO | 0.4 FTE x 5 wk x 5 d = 10 days | 5 | 10 | 15 | 10 | 550 | 5500 | ASSUMPTION | ASSUMPTION sized to slide 5 cyber deliverables (impact analysis, diagrams). Rate VERIFIED. | TD
Data engineer - Data Mgmt Workshop, data flow design, data governance principles input | SEGRO | 0.4 FTE x 5 wk x 5 d = 10 days | 5 | 10 | 15 | 10 | 500 | 5000 | ASSUMPTION | ASSUMPTION sized to slide 5 'Data flow design' + slide 3 Data Mgmt workshop. Rate VERIFIED. | TD
Business analyst - Use case scope for Release 1 Agreed, KDD documentation, DRG/ARG approval pack | SEGRO | 0.4 FTE x 5 wk x 5 d = 10 days | 5 | 10 | 15 | 10 | 500 | 5000 | ASSUMPTION | ASSUMPTION: slide 3 'Use case scope for Release 1 Agreed' milestone + 'Arch decisions for DRG / ARG'. Rate VERIFIED. | TD
Project manager - mobilisation, delivery plan, procurement specification and coordination | SEGRO | 1 FTE x 5 wk x 5 d = 25 days | 15 | 25 | 30 | 25 | 535 | 13375 | ASSUMPTION | ASSUMPTION: slide 5 'Delivery plan' + 'Procurement specification' deliverables. Rate VERIFIED. | TD
HCL architecture/product SME input to design workshops (UnO/TX/Unica/CDP sizing and prerequisites) | HCL | 0.6 FTE x 5 wk x 5 d = 15 days | 10 | 15 | 25 | 15 | 950 | 14250 | INDICATIVE | Rate = HCL's own published G-Cloud 14 SFIA card (Solution dev L3 950/day, VERIFIED); grade mix and attendance ASSUMPTION. HCL named team incl. product SMEs per HCL_V1 brief; Platform Architect still TBD. | TD
Oracle 19 licence (mandatory for Unica+ MaxAI CDM) - procurement item, price not shared | ThirdParty | 1 licence x rate GBP 0 until quoted | 1 | 1 | 1 | 1 | 0 | 0 | RATE_MISSING | HCL Support Matrix (HCL_V1 brief section 3.7): Oracle 19 mandatory for Unica+ MaxAI CDM; absent from POAP Decisions & procurement lane (F10). GBP 0 adjustable input - FLOOR until quoted. | FIXED
Aerospike edition/licence (CDP caching, V6.3.0.35 disclosed, edition/licence unstated) - procurement item | ThirdParty | 1 licence x rate GBP 0 until quoted | 1 | 1 | 1 | 1 | 0 | 0 | RATE_MISSING | HCL Support Matrix (HCL_V1 brief section 2 blocker 7): Aerospike version disclosed, edition/licence still unstated; absent from POAP procurement lane (F10). GBP 0 adjustable input. | FIXED
SUBTOTAL — Design & Plan | [7 empty] | 66625
P2 — BUILD - SEGRO (AZURE FOUNDATIONS, AKS, SHARED SERVICES) (10 wk, from 2026-08-17, Slide 3: 'SEGRO 10 weeks' bar x=4.55-8.86 (start DERIVED from bar geometry ~ late Aug); items 1-6 incl. cyber design + data governance; 'To be validated based on Arch workshop' annotation (F14))
Cost line | Side | Quantity model | Qty Low | Qty Likely | Qty High | Qty (live) | Rate/unit £ | Cost £ (live) | Status | Basis / source | Schedule
Azure foundations - env segregation, networking, subscriptions, Private DNS, VPN tunnel connectivity, workspaces | SEGRO | 2 FTE x 10 wk x 5 d = 100 days | 80 | 100 | 130 | 100 | 525 | 52500 | ASSUMPTION | Squad shape ASSUMPTION anchored to platform.json 5.5-effective-FTE squad convention (2 of 5.5 FTE on foundations). Scope = slide 3 build item 1. Rate VERIFIED. | TD
Build and harden AKS platform - cluster ops processes, node pools, RBAC, Entra ID integration, backup strategy | SEGRO | 1 FTE x 10 wk x 5 d = 50 days | 40 | 50 | 70 | 50 | 535 | 26750 | ASSUMPTION | Squad shape ASSUMPTION (1 of 5.5 FTE). Scope = slide 3 build item 2. Kubernetes-skill rate VERIFIED (ITJobsWatch median 535). | TD
Deploy shared platform services - PostgreSQL, SQL Server, MongoDB/Cosmos, Kafka, Redis, monitoring stack, ingress, cert mgmt | SEGRO | 1.5 FTE x 10 wk x 5 d = 75 days | 60 | 75 | 100 | 75 | 525 | 39375 | ASSUMPTION | Squad shape ASSUMPTION (1.5 of 5.5 FTE). Scope = slide 3 build item 3 (8 named services). Rate VERIFIED. | TD
Complete cyber security design - managed identities, Key Vault, secrets mgmt, network segmentation, WAF, API security, PAM | SEGRO | 0.5 FTE x 10 wk x 5 d = 25 days | 20 | 25 | 40 | 25 | 550 | 13750 | ASSUMPTION | Squad shape ASSUMPTION (0.5 of 5.5 FTE). Scope = slide 3 build item 4. Rate VERIFIED. | TD
Data mgmt & governance principles - classification, ownership, retention, lineage, master data, information architecture | SEGRO | 0.5 FTE x 10 wk x 5 d = 25 days | 15 | 25 | 35 | 25 | 500 | 12500 | ASSUMPTION | Squad shape ASSUMPTION (0.5 of 5.5 FTE). Scope = slide 3 build item 6. Rate VERIFIED. | TD
FND-4 Agent eval harness & observability - golden sets, scored promotion gates, run-trace logging, eval dashboard (absent from POAP, F13) | SEGRO | 20 pd (range 12-25) per platform.json FND-4 | 12 | 20 | 25 | 20 | 850 | 17000 | ASSUMPTION | Quantity traced to platform.json FND-4 (12/20/25 pd, 0.44 FTE/wk over 9 wks) - the source itself labels the task ASSUMPTION, so it is carried as ASSUMPTION here. F13: no eval workstream anywhere in the POAP. Rate = blended GBP 850 ASSUMPTION placeholder (RATE_MISSING in sources). | TD
Project/delivery management across SEGRO build | SEGRO | 1 FTE x 10 wk x 5 d = 50 days | 40 | 50 | 60 | 50 | 535 | 26750 | ASSUMPTION | ASSUMPTION: 1 PM on a 6-workstream build phase. Rate VERIFIED. PM-as-%-of-delivery benchmark is RATE_MISSING in programme_benchmarks - sized bottom-up instead. | TD
Book CREST pen test + hold remediation window (F7: 4-8 wk booking lead time, must start by ~Oct) | SEGRO | 2 days procurement admin | 1 | 2 | 4 | 2 | 535 | 1070 | ASSUMPTION | F7 recommendation: add a 'book pen test' task in October; POAP shows none. Trivial cost, scheduled-risk critical. | TD
AKS cluster management fee (Standard tier) - commissioning window | Azure | 1 cluster x 22 wk x 168 h x 50% ramp = 1,848 hrs | 1109 | 1848 | 2587 | 1848 | 0.0758 | 140.0784 | ASSUMPTION | Rate VERIFIED (Azure Retail Prices API uksouth). Ramp ASSUMPTION: envs commissioned progressively Sep 2026-Jan 2027 (~22 wk pre-go-live window), average 50% of full-estate hours (low 30%, high 70%). Dual-cluster KDD flexes via ClusterCount. | TD
AKS worker node pools - D4s_v5 class (M) - commissioning window | Azure | 12 nodes (3/env x 4 envs) x 3,696 h x 50% ramp = 22,176 node-hrs | 13306 | 22176 | 31046 | 22176 | 0.1682 | 3730.0032 | ASSUMPTION | Rate VERIFIED. Node count ASSUMPTION: 3 workers/env x 4 envs (SEGRO standard) - no sizing published; POAP itself defers to Arch workshop (F14). Same 50% ramp ASSUMPTION as P2-L9. NodeSize toggle flexes S/M/L. | TD
ARO worker node pools - D4ds_v5 class (ARO minimum worker family) - commissioning window | Azure | 12 nodes (3/env x 4 envs) x 3,696 h x 50% ramp = 22,176 node-hrs | 13306 | 22176 | 31046 | 22176 | 0.1985 | 0 | ASSUMPTION | Rate VERIFIED (azure_infra_rates: Ddsv5 with local disk is the ARO minimum-spec worker family). Node count/ramp ASSUMPTION as P2-L10; scales with EnvCount and NodeSize. Priced only when Platform=ARO. | TD
ARO OpenShift worker licence uplift (only if ARO wins KDD-1) | Azure | 48 vCPU (12 nodes x 4 vCPU) x 3,696 h x 50% ramp = 88,704 vCPU-hrs | 53222 | 88704 | 124186 | 88704 | 0.0324 | 0 | ASSUMPTION | Rate VERIFIED (0.0324/vCPU-hr on top of VM). Volume follows P2-L10 node ASSUMPTION. F3: KDD 'TCO AKS v ARO' open while build text pre-commits to AKS; this line prices the ARO branch. | TD
ARO control-plane nodes - 3x D8s_v5 (required by ARO, no licence uplift on masters) | Azure | 3 masters x 3,696 h x 50% ramp = 5,544 node-hrs | 3326 | 5544 | 7762 | 5544 | 0.3364 | 0 | ASSUMPTION | Rate VERIFIED. ARO requires 3 control-plane nodes billed as plain VMs (azure_infra_rates narrative). Ramp ASSUMPTION as P2-L9. | TD
PostgreSQL Flexible Server GP 4-vCore - one per environment - commissioning window | Azure | 4 envs x 3,696 h x 50% ramp = 7,392 hrs | 4435 | 7392 | 10349 | 7392 | 0.3121 | 2307.0432 | ASSUMPTION | Rate VERIFIED. 1 server/env ASSUMPTION (UnO auto-installs Percona PGVector vs Unica+ 'Percona not supported' - HCL_V1 brief 3.4 - may force 2 flavours; high band covers). Ramp ASSUMPTION as P2-L9. | TD
PostgreSQL provisioned storage - commissioning window | Azure | 128 GB/env x 4 envs x 5 mo x 50% ramp = 1,280 GB-months | 768 | 1280 | 1792 | 1280 | 0.1008 | 129.024 | ASSUMPTION | Rate VERIFIED. 128 GB/env sizing ASSUMPTION (no sizing published; F14). | TD
Azure SQL Database GP 4-vCore - one per environment - commissioning window | Azure | 4 envs x 3,696 h x 50% ramp = 7,392 hrs | 4435 | 7392 | 10349 | 7392 | 0.5766 | 4262.2272 | ASSUMPTION | Rate VERIFIED. 1 DB/env ASSUMPTION per slide 3 shared-services list. Ramp ASSUMPTION as P2-L9. | TD
Cosmos DB serverless (MongoDB-API workloads) - commissioning window | Azure | 50 M RU/env/mo x 4 envs x 5 mo x 50% ramp = 500 units of 1M RU | 250 | 500 | 1000 | 500 | 0.225 | 112.5 | ASSUMPTION | Rate VERIFIED. RU volume ASSUMPTION - serverless chosen for low/spiky pre-go-live load; no workload sizing published (F14). | TD
Event Hubs Standard (Kafka endpoint) - commissioning window | Azure | 1 TU/env x 4 envs x 3,696 h x 50% ramp = 7,392 TU-hrs | 4435 | 7392 | 10349 | 7392 | 0.0227 | 167.7984 | INDICATIVE | Rate VERIFIED but HCL's own matrix marks Event Hubs = N for UnO/CDP/Unica+ (HCL_V1 brief 3.3) - Kafka may be forced self-hosted on the cluster (cost then shifts into node pools). Carried as the Azure-native branch. | TD
Azure Cache for Redis Standard C1 - one per environment - commissioning window | Azure | 4 envs x 3,696 h x 50% ramp = 7,392 cache-hrs | 4435 | 7392 | 10349 | 7392 | 0.1311 | 969.0912 | ASSUMPTION | Rate VERIFIED. 1 cache/env ASSUMPTION per slide 3 shared-services list. Ramp ASSUMPTION as P2-L9. | TD
Application Gateway WAF_v2 - fixed gateway fee (prod + shared non-prod) - commissioning window | Azure | 2 gateways x 3,696 h x 50% ramp = 3,696 gw-hrs | 2218 | 3696 | 5174 | 3696 | 0.3409 | 1259.9664 | ASSUMPTION | Rate VERIFIED. 2 gateways ASSUMPTION (1 prod + 1 shared non-prod) at the 4-env baseline; scales with EnvCount. Slide 3 cyber item names WAF explicitly. | TD
Application Gateway WAF_v2 - capacity units - commissioning window | Azure | 2 gw x 5 CU avg x 3,696 h x 50% ramp = 18,480 CU-hrs | 11088 | 18480 | 25872 | 18480 | 0.0109 | 201.432 | ASSUMPTION | Rate VERIFIED. 5 CU avg per gateway during build ASSUMPTION (light pre-go-live traffic). | TD
API Management Standard unit (marginal - estate APIM may absorb) - commissioning window | Azure | 1 unit x 3,696 h x 50% ramp = 1,848 unit-hrs | 0 | 1848 | 3696 | 1848 | 0.7127 | 1317.0696 | INDICATIVE | Rate VERIFIED. SEGRO principle: all integration via APIM with OAuth; estate already runs APIM so marginal cost may be nil (low = 0). Carried so the toggle maths is complete. | TD
VPN Gateway VpnGw1 (tunnel connectivity per slide 3 item 1) - commissioning window | Azure | 1 gateway x 3,696 h x 50% ramp = 1,848 hrs | 0 | 1848 | 3696 | 1848 | 0.1439 | 265.9272 | INDICATIVE | Rate VERIFIED. SEGRO single-tenant estate likely already has connectivity - marginal cost may be nil (low = 0). Named in slide 3 build item 1. | TD
Azure Private DNS zones - commissioning window | Azure | 10 zones x 5 mo = 50 zone-months | 25 | 50 | 75 | 50 | 0.3788 | 18.94 | ASSUMPTION | Rate VERIFIED. 10 zones ASSUMPTION (privatelink zones for AKS, PG, SQL, KV, ACR etc). Named in slide 3 build item 1. Pennies - carried for completeness. | TD
Log Analytics ingestion during build (monitoring stack commissioning) | Azure | 5 GB/day x 150 days x 50% ramp = 375 GB | 150 | 375 | 750 | 375 | 2.1819 | 818.2125 | ASSUMPTION | Rate VERIFIED (2.1819/GB). Volume ASSUMPTION - pre-go-live estate at reduced telemetry; run-phase volume is the bigger driver (see run model). | TD
Key Vault operations - commissioning window | Azure | 1M ops = 100 units of 10k ops | 50 | 100 | 200 | 100 | 0.0227 | 2.27 | ASSUMPTION | Rate VERIFIED; negligible at platform scale (a few GBP) - carried for completeness per slide 3 cyber item (Key Vault integration). | TD
Microsoft Defender for Cloud workload protection - commissioning window | Azure | 40 resources x 5 mo = 200 resource-months x rate GBP 0 | 100 | 200 | 300 | 200 | 0 | 0 | RATE_MISSING | Rate not priced in fact files (explicitly excluded from azure_infra_rates scope) - GBP 0 adjustable until priced. Will appear on a real bill. | TD
DevSecOps automation - IaC pipelines, policy-as-code, image scanning, CI/CD for infra + agent deployment (absent from POAP, F19) | SEGRO | 0.6 FTE x 10 wk x 5 d = 30 days (range 0.4-0.8 FTE) | 20 | 30 | 40 | 30 | 525 | 15750 | ASSUMPTION | Quantity is an ASSUMPTION pending the Arch workshop: slide 7 names a 'CI/CD Configuration Document' deliverable but the POAP contains no build task behind it anywhere. Sized as a fraction of the 10-wk build for one DevOps engineer (20/30/40 pd = 0.4-0.8 FTE). Trigger: 'Lack of any DevSecOps automation for Infra, Systems or Agents' - senior architect review 18 Jul 2026 (F19). Rate VERIFIED. Boundary vs P5-L2: this line BUILDS the pipelines/policy gates during P2; P5-L2 EXECUTES the CI/CD cutover and release automation at deploy - no double count. | TD
Data integration to MRI / SAMA / Anaplan — NOT in the POAP (scope gap, F15/F5) | SEGRO | Integration build to the systems of record — absent from the POAP | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | VISIBLE ZERO — the HCL-floor discipline applied to scope. The POAP costs the platform but no integration to MRI (the critical backbone), SAMA or Anaplan; agents with no data path to the systems of record cannot deliver business value. A delivery prerequisite, not adoption time. £0 here means UN-COSTED, not free. Absent from POAP (F15). | FIXED
GPU pool commissioning for model bring-up & eval (ModelChoice=Llama; bounded window, not 24/7) | Azure | 1 A100 node x ~12h/day x 6 wk bring-up = ~500 node-hrs (low 250 / high 1000) | 250 | 500 | 1000 | 500 | 3.4782 | 0 | ASSUMPTION | LLAMA branch build cost: the same A100 meter (GBP 3.4782/hr VERIFIED) spun up for a BOUNDED commissioning/eval window during P2 bring-up (not the 24/7 prod serving in R-L34). Hours are an ASSUMPTION range. Fixes the reviewer gap that Llama moved run cost but left the build unchanged despite the fact fragment's stated dual use. Active only when ModelChoice=Llama. Fragment: model_serving_rates.json. | TD
GPU capacity procurement — quota / reserved-capacity commitment (ModelChoice=Llama) | Azure | 1 x GPU quota request / reserved-capacity commitment — Rates cell £0 until quoted | 1 | 1 | 1 | 1 | 0 | 0 | RATE_MISSING | LLAMA branch: Azure GPU (NC/ND) capacity needs a quota request and, at scale, a reserved-capacity commitment negotiated per subscription — no public unit price, so visible £0 adjustable, SAME family as Oracle 19 (P1-L8) / Aerospike (P1-L9). Also a schedule risk (lead time to grant). Any Llama total excluding it is a FLOOR. Active only when ModelChoice=Llama. Fragment: model_serving_rates.json (model_serving_gpu_quota_procurement). | FIXED
SUBTOTAL — Build - SEGRO (Azure foundations, AKS, shared services) | [7 empty] | 221146.5833
P3 — BUILD - HCL (UNO + TX INSTALL, UNICA+/CDP DEPLOY) (6 wk, from 2026-10-26, Slide 3: 'HCL 6 weeks' bar x=8.91-10.78, drawn strictly sequential after SEGRO bar (F2: 2-4 wk overlap realistic via OverlapWeeks toggle); gated on open KDD AKS v ARO (F3))
Cost line | Side | Quantity model | Qty Low | Qty Likely | Qty High | Qty (live) | Rate/unit £ | Cost £ (live) | Status | Basis / source | Schedule
HCL install & configure base UnO platform + TX components (DX, Foundry) onto AKS - platform validation, connectivity, observability integration | HCL | 3 FTE x 6 wk x 5 d = 90 days | 60 | 90 | 135 | 90 | 950 | 85500 | INDICATIVE | Rate = HCL published G-Cloud SFIA L3 (VERIFIED); team size & grade mix ASSUMPTION. Low anchored to HCL's own D-025 '20-30 day core-install' agreed-in-principle x 3-person team floor. F3: install pre-commits to AKS while KDD open and HCL's matrix says AKS x CDP = N. | TD
HCL deploy Unica+ & CDP services - routing, application gateways, certificates | HCL | 2 FTE x 6 wk x 5 d = 60 days | 40 | 60 | 90 | 60 | 950 | 57000 | INDICATIVE | Rate VERIFIED (HCL's own card); team size & grade mix ASSUMPTION. Slide 3 HCL bar second block. CDP 2-env exception (F9) reduces scope but weakens Dec testing. | TD
SEGRO platform/security engineers supporting HCL install (access, networking, reviews) | SEGRO | 1 FTE x 6 wk x 5 d = 30 days | 20 | 30 | 45 | 30 | 525 | 15750 | ASSUMPTION | ASSUMPTION: vendor installs on a SEGRO-run cluster always consume platform-team time (RBAC, network paths, secrets). Rate VERIFIED. | TD
HCL UnO platform licence/subscription - initial year | HCL | 1 year x rate GBP 0 until contract shared | 1 | 1 | 1 | 1 | 0 | 0 | RATE_MISSING | HCL contract pricing not shared with SEGRO. GBP 0 adjustable input - all HCL-side totals are a FLOOR while this holds. | FIXED
HCL Unica+ licence/subscription - initial year | HCL | 1 year x rate GBP 0 until contract shared | 1 | 1 | 1 | 1 | 0 | 0 | RATE_MISSING | As P3-L4. | FIXED
HCL CDP licence/subscription - initial year | HCL | 1 year x rate GBP 0 until contract shared | 1 | 1 | 1 | 1 | 0 | 0 | RATE_MISSING | As P3-L4. Note AKS x CDP = N in HCL's own matrix - CDP scope interacts with the Platform toggle (F3). | FIXED
HCL DX licence/subscription - initial year | HCL | 1 year x rate GBP 0 until contract shared | 1 | 1 | 1 | 1 | 0 | 0 | RATE_MISSING | As P3-L4. | FIXED
MinIO EOL remediation (community edition EOL Apr 2026; HCL: 'Do not assume replaceable') | HCL | 1 remediation package x rate GBP 0 until scoped | 1 | 1 | 1 | 1 | 0 | 0 | RATE_MISSING | HCL_V1 brief blocker 6: CDP mandates MinIO v5.0.15, community edition EOL upstream Apr 2026, Azure First tab walks back Blob substitution. Absent from POAP procurement lane (F10). GBP 0 adjustable. | FIXED
SUBTOTAL — Build - HCL (UnO + TX install, Unica+/CDP deploy) | [7 empty] | 158250
P4 — TESTING (SIT, PEN TEST, UAT, PERFORMANCE) (4 wk, from 2026-12-07, Slide 3: Testing bar x=11.19-12.9 (Dec 2026); 'Test phase complete' milestone adjacent to Christmas marker (F1: peak-leave compression risk))
Cost line | Side | Quantity model | Qty Low | Qty Likely | Qty High | Qty (live) | Rate/unit £ | Cost £ (live) | Status | Basis / source | Schedule
System Integration Testing - test engineers | SEGRO | 2 FTE x 4 wk x 5 d = 40 days | 30 | 40 | 60 | 40 | 431 | 17240 | ASSUMPTION | Team size ASSUMPTION; slide 9 requires SIT report + regression test report with evidence. Rate VERIFIED. High band covers F1 Christmas compression re-runs. | TD
Test management - plan, defect register, release readiness | SEGRO | 1 FTE x 4 wk x 5 d = 20 days | 15 | 20 | 30 | 20 | 515 | 10300 | ASSUMPTION | ASSUMPTION: slide 9 deliverables (defect register & resolution log, UAT plan & sign off). Rate VERIFIED. | TD
CREST penetration test engagement (cloud platform scope) | ThirdParty | ~10 tester-days (5-day light to 15-day deep scope) | 5 | 10 | 15 | 10 | 950 | 9500 | INDICATIVE | Rate = mid of two VERIFIED published G-Cloud CREST bands (650-1250/day); 10-day scope typical for a new cloud platform per people_rates derivation (GBP 7k-12.5k engagement). F7: needs booking by ~Oct + named Jan remediation window. | FIXED
UAT coordination & business-readiness liaison (BA) | SEGRO | 1 FTE x 4 wk x 5 d = 20 days | 10 | 20 | 25 | 20 | 500 | 10000 | ASSUMPTION | ASSUMPTION: UAT & release readiness item on slide 3. SEGRO business-user UAT time itself is NOT costed (see notes). Rate VERIFIED. | TD
Performance & resilience testing (incl. DR test execution - DR Test Report is a named deliverable) | SEGRO | 0.75 FTE x 4 wk x 5 d = 15 days | 10 | 15 | 25 | 15 | 525 | 7875 | ASSUMPTION | ASSUMPTION: slide 9 'Performance resilience test report' + 'Disaster Recovery Test Report'. DR infrastructure itself remains uncosted (sizing_updates_missed) - see notes. Rate VERIFIED. | TD
HCL defect-fix & SIT/UAT support (their stack, their fixes) | HCL | 1 FTE x 4 wk x 5 d = 20 days | 10 | 20 | 40 | 20 | 950 | 19000 | INDICATIVE | Rate VERIFIED (HCL card); allocation ASSUMPTION - vendor stack defects during SIT need vendor fixes; high band covers the F1 compressed-December scenario. | TD
SEGRO platform team support during test phase (env fixes, redeploys) | SEGRO | 1 FTE x 4 wk x 5 d = 20 days | 15 | 20 | 30 | 20 | 525 | 10500 | ASSUMPTION | ASSUMPTION: standard test-phase platform support. Azure consumption for Dec is inside the P2 commissioning-window ramp lines. Rate VERIFIED. | TD
AI red-team exercise + audit dry-run before go-live - prompt injection, tool-abuse/data-exfiltration, jailbreak testing on agent surfaces (absent from POAP, F26) | ThirdParty | 3/5/13 days — one-off at Likely; the HIGH case is a two-touch lifecycle red-team (a pre-UAT touch + the pre-go-live exercise) | 3 | 5 | 13 | 5 | 950 | 4750 | INDICATIVE | Engagement size is an ASSUMPTION range (3/5/13 days). Rate: the DERIVED CREST pen-test day rate (950) is used as an INDICATIVE proxy for a specialist AI red-team rate - no published AI-red-team rate exists in the fact files. Trigger: 'Red Teaming or Audit Dry runs for AI not in plan' - senior architect review 18 Jul 2026 (F26). Fixed engagement like P4-L3 - does not stretch with schedule slip. WIDENED (18 Jul 2026 review): Microsoft/industry guidance treats AI red-teaming as lifecycle-iterative, not one-shot — the HIGH effort case (13 d) prices a second, pre-UAT touch on top of the pre-go-live exercise; the annual cadence line R-L31 carries the ongoing lifecycle. Likely unchanged (5 d) so the default headline holds. | FIXED
Eval golden-set labelling by business SMEs — EXCLUDED (scope gap, F13) | SEGRO | SME weeks to label the eval golden sets FND-4 consumes — not costed | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | VISIBLE ZERO. FND-4 costs the eval-harness MACHINERY; nobody has costed the business-SME weeks that label the golden sets it scores against. Without labelled goldens the promotion gates are hollow. A delivery prerequisite. £0 = un-costed, not free. Absent from POAP (F13). | FIXED
SUBTOTAL — Testing (SIT, pen test, UAT, performance) | [7 empty] | 89165
P5 — DEPLOY (PROD READINESS, MIGRATION, GO-LIVE) (4 wk, from 2027-01-04, Slide 3: Deploy bar x=13.23-14.9 (Jan 2027); production readiness review, smoke test/stage gates, go/no-go x=13.99, migration execution, go-live ~end Jan/Feb 2027)
Cost line | Side | Quantity model | Qty Low | Qty Likely | Qty High | Qty (live) | Rate/unit £ | Cost £ (live) | Status | Basis / source | Schedule
Production readiness, smoke tests, stage gates, migration execution, go-live | SEGRO | 2 FTE x 4 wk x 5 d = 40 days | 30 | 40 | 55 | 40 | 525 | 21000 | ASSUMPTION | Team size ASSUMPTION; scope = slide 3 Deploy items 1-5 + slide 10 deploy docs (release plan, cutover, rollback, smoke report). Rate VERIFIED. | TD
CI/CD cutover, release automation, operational handover pack | SEGRO | 1 FTE x 4 wk x 5 d = 20 days | 15 | 20 | 30 | 20 | 525 | 10500 | ASSUMPTION | ASSUMPTION: slide 10 'Operational handover pack' + CI/CD configuration doc (slide 7). Rate VERIFIED. Boundary vs P2-L27: that line builds the DevSecOps pipelines in P2; this line is the deploy-phase cutover/release execution only - no double count. | TD
Release/project management - go/no-go pack, cutover comms | SEGRO | 1 FTE x 4 wk x 5 d = 20 days | 15 | 20 | 25 | 20 | 535 | 10700 | ASSUMPTION | ASSUMPTION: go/no-go decision milestone (slide 3, x=13.99). Rate VERIFIED. | TD
Pen-test remediation + retest sign-off before go/no-go (F7) | SEGRO | 0.5 FTE x 4 wk x 5 d = 10 days | 5 | 10 | 20 | 10 | 550 | 5500 | ASSUMPTION | F7: remediation + retest must land before the January go/no-go; POAP holds no named window. High band = material findings. Rate VERIFIED. | TD
HCL go-live support (their components through cutover) | HCL | 1 FTE x 4 wk x 5 d = 20 days | 10 | 20 | 30 | 20 | 950 | 19000 | INDICATIVE | Rate VERIFIED (HCL card); allocation ASSUMPTION. | TD
R1 use-case delivery lane — ABSENT from the POAP (scope gap, F5) | SEGRO | Building the first business-facing use cases against the platform — no lane in the POAP | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | VISIBLE ZERO. A101: £830k buys a platform with zero business-facing capability at go-live. There is no R1 use-case delivery lane in the POAP (F5) — the £37k supervised September pilot (see the R1 Pilot block) is the costed alternative. £0 = un-costed, not free. | FIXED
SUBTOTAL — Deploy (prod readiness, migration, go-live) | [7 empty] | 66700
P6 — HYPERCARE / PGLS + BUSINESS READINESS CLOSE-OUT (6 wk, from 2027-02-01, Slide 3: 'PGLS + Hypercare' bar from go-live (x=15.41, Feb 2027); duration 6 wk ASSUMPTION from the 4-8 wk hypercare norm (programme_benchmarks, Microsoft guidance: short fixed-end-date, criteria-based exit))
Cost line | Side | Quantity model | Qty Low | Qty Likely | Qty High | Qty (live) | Rate/unit £ | Cost £ (live) | Status | Basis / source | Schedule
Hypercare squad - declining coverage, average 1.5 FTE across 6 weeks | SEGRO | avg 1.5 FTE x 6 wk x 5 d = 45 days | 30 | 45 | 60 | 45 | 525 | 23625 | ASSUMPTION | Duration ASSUMPTION per programme_benchmarks hypercare norm (4-8 wk, criteria-exited fixed window); average 1.5 FTE across the window is a coverage ASSUMPTION (not a % of the build squad). Rate VERIFIED. | TD
HCL PGLS / hypercare support on HCL components | HCL | 1 FTE x 6 wk x 5 d = 30 days | 15 | 30 | 45 | 30 | 950 | 28500 | INDICATIVE | Rate VERIFIED (HCL card); allocation ASSUMPTION. If PGLS is inside a fixed-price contract this double-counts - flexes to 0 via qty or HCL_Toggle. | TD
Change management, comms, training delivery & business readiness (spread P2-P6, booked here) | SEGRO | 10% of ~GBP 600k delivery floor / BA rate 500 = ~120 days | 80 | 120 | 160 | 120 | 500 | 60000 | ASSUMPTION | Sized from the VERIFIED Prosci benchmark: most common change-mgmt allocation = 10% of project budget (programme_benchmarks). Covers slide 3 Business readiness lane (change mgmt, training, comms, stakeholder engagement). Effort spans P2-P6; booked in one line here. | TD
End-user training materials/licence cost per employee (per-rollout unit cost unpublished) | SEGRO | OrgSize employees x per-rollout rate GBP 0 (live headcount = the single OrgSize input; ARA25 VERIFIED = 463, brief = 700) | 463 | 463 | 463 | 700 | 0 | 0 | RATE_MISSING | Headcount now follows the single OrgSize input (default 700 per brief; SEGRO ARA25 VERIFIED = 463 — set OrgSize to 463 for the ARA-anchored run). Reconciles the previous two-headcounts issue (this line hardcoded 463 while TCO/employee used OrgSize). Per-rollout training unit cost is RATE_MISSING (£0 adjustable), so the live cost is unchanged. Trainer delivery days already inside P6-L3. | FIXED
Service transition & application support model into ITIL/ServiceNow (transition pack, RACI, ownership matrix) | SEGRO | 0.5 FTE x 6 wk x 5 d = 15 days | 10 | 15 | 25 | 15 | 535 | 8025 | ASSUMPTION | ASSUMPTION: slide 3 Business readiness item 1 + slide 8 docs (Support RACI, Service ownership matrix); SEGRO principle - ITIL/ServiceNow service transition for everything. Rate VERIFIED. | TD
SUBTOTAL — Hypercare / PGLS + business readiness close-out | [7 empty] | 120150
LOADINGS & SENSITIVITY (formula-driven)
Build subtotal (all phases) | [7 empty] | 722036.5833
Contingency on build | [7 empty] | 108305.4875 | DERIVED | ContingencyPct applied once to the build subtotal (default 15% ASSUMPTION; Green Book ICT capex optimism-bias starting range is 10-200%).
Weekly time-driven burn (P1–P5 average) | [7 empty] | 20263.3305 | DERIVED | Average weekly run-rate of time-driven P1–P5 work; drives slip cost.
Slip cost (SlipWeeks × weekly time-driven P1–P5 burn) | [7 empty] | 0 | DERIVED | SlipWeeks x (time-driven P1-P5 cost / 29 wks). Time-driven = lines flagged time_driven (SEGRO/HCL people + Azure commissioning); RATE_MISSING licences
Overlap saving — F2 (Azure double-running only, per parallel week) | [7 empty] | 0 | DERIVED | OverlapWeeks x (P1-P5 Azure time-driven lines / 29 wks). Parallel SEGRO/HCL working saves Azure environment DOUBLE-RUNNING cost only; it is a COST lev
TOTAL BUILD (phases + contingency + slip − overlap) | [7 empty] | 830342.0708
▪ HCL FLOOR: every HCL licence/subscription/AMS line is RATE_MISSING at GBP 0 (contract not shared) - any total including the HCL side is a FLOOR, not an estimate.
▪ Run cost excludes SEGRO business-user time (UAT, adoption, process change) throughout.
▪ Build durations are the POAP's own, marked 'To be validated based on Arch workshop' on the plan itself (F14) - price slips via SlipWeeks; go-live is better presented as a range (Feb-Apr 2027).
▪ F5 value gap: ~30 weeks and the full build spend deliver zero business-facing capability at go-live - no R1 use-case delivery lane exists in the POAP; run-model token lines are placeholders until R1 lands.
▪ Azure quantities are list-price PAYG ceilings at stated volume ASSUMPTIONS; EA/MACC discounts and reservations (30-60% off) reduce them. Managed disks, egress, Azure Firewall, Private Link and backup storage are not priced (fact-file scope) and will appear on a real bill.
▪ DR: 'Disaster Recovery Test Report' is a named POAP deliverable and its test execution is costed (P4-L5), but DR infrastructure itself is not costed anywhere in the POAP or this model (sizing_updates_missed) - a named gap.
▪ Kafka: HCL's matrix marks Event Hubs = N for UnO/CDP/Unica+ - the Event Hubs lines are the Azure-native branch; self-hosted Kafka on the cluster is the fallback and shifts that cost into node pools.
▪ Phase start dates are a strictly-sequential reconstruction from the POAP's own week labels (5/10/6/4/4 + 6 wk hypercare from 13 Jul 2026, go-live ~end Jan/Feb 2027). The drawn bar geometry does NOT reconcile with these labels (HCL bar drawn ~3.8 wk vs labelled 6; 'Test phase comp

## 5yr Run Cost
5-Year Run Cost — recurring lines, indexed from Y2
Scenario: envs = 4 · platform = AKS · sku = GPT-4o · agents = Exclude/1 · mcp = 2 · obs = Azure · HCL = Include · indexation = 3.0%
Run line | Side | Quantity model | Qty / yr | Rate/unit £ | Y1 | Y2 | Y3 | Y4 | Y5 | 5-yr total | Status | Basis / source
AKS cluster management fee (Standard tier) - 24/7 | Azure | 1 cluster x 8,760 h/yr | 8760 | 0.0758 | 664.008 | 683.9282 | 704.4461 | 725.5795 | 747.3469 | 3525.3087 | ASSUMPTION | Rate VERIFIED. Single cluster ASSUMPTION - dual (CDP forced split) flexes via ClusterCount.
Worker node pools - prod 24/7 + non-prod reduced hours | Azure | 3 prod x 8,760 h + 9 non-prod x 3,120 h = 54,360 node-hrs/yr | 54360 | 0.1682 | 9143.352 | 9417.6526 | 9700.1821 | 9991.1876 | 10290.9232 | 48543.2975 | ASSUMPTION | Rate VERIFIED. Node counts ASSUMPTION (3/env x 4 envs); non-prod at 12h weekdays (3,120 h/yr) ASSUMPTION - auto-shutdown saves ~64% vs 24/7. NodeSize toggle flexes S/M/L.
ARO worker node pools - D4ds_v5 (ARO minimum family) - prod 24/7 + non-prod reduced | Azure | 3 prod x 8,760 h + 9 non-prod x 3,120 h = 54,360 node-hrs/yr | 54360 | 0.1985 | 0 | 0 | 0 | 0 | 0 | 0 | ASSUMPTION | Rate VERIFIED (ARO minimum worker family D4ds_v5). Volumes as R-L2; scales with EnvCount and NodeSize. Priced only when Platform=ARO.
ARO OpenShift worker licence uplift (ARO branch only) | Azure | 12 prod vCPU x 8,760 + 36 non-prod vCPU x 3,120 = 217,440 vCPU-hrs/yr | 217440 | 0.0324 | 0 | 0 | 0 | 0 | 0 | 0 | ASSUMPTION | Rate VERIFIED. Volume follows R-L2 node assumptions. Prices the open KDD-1 ARO branch (F3).
ARO control-plane nodes 3x D8s_v5 - 24/7 (ARO branch only) | Azure | 3 masters x 8,760 h = 26,280 node-hrs/yr | 26280 | 0.3364 | 0 | 0 | 0 | 0 | 0 | 0 | ASSUMPTION | Rate VERIFIED; ARO requires 3 always-on control-plane nodes (azure_infra_rates narrative).
PostgreSQL Flexible Server GP 4-vCore - prod 24/7 + non-prod reduced | Azure | 1 prod x 8,760 + 3 non-prod x 3,120 = 18,120 hrs/yr | 18120 | 0.3121 | 5655.252 | 5824.9096 | 5999.6568 | 6179.6466 | 6365.0359 | 30024.5009 | ASSUMPTION | Rate VERIFIED. 1 server/env at 4-env baseline; non-prod 12h weekdays ASSUMPTION.
PostgreSQL provisioned storage | Azure | 128 GB x 4 envs x 12 mo = 6,144 GB-months/yr | 6144 | 0.1008 | 619.3152 | 637.8947 | 657.0315 | 676.7424 | 697.0447 | 3288.0285 | ASSUMPTION | Rate VERIFIED; sizing ASSUMPTION (no published sizing, F14).
Azure SQL Database GP 4-vCore - prod 24/7 + non-prod reduced | Azure | 1 prod x 8,760 + 3 non-prod x 3,120 = 18,120 hrs/yr | 18120 | 0.5766 | 10447.992 | 10761.4318 | 11084.2747 | 11416.803 | 11759.307 | 55469.8085 | ASSUMPTION | Rate VERIFIED; env pattern ASSUMPTION as R-L5.
Cosmos DB serverless (MongoDB-API workloads) | Azure | 100 M RU/mo x 12 = 1,200 units of 1M RU/yr | 1200 | 0.225 | 270 | 278.1 | 286.443 | 295.0363 | 303.8874 | 1433.4667 | ASSUMPTION | Rate VERIFIED; volume ASSUMPTION - true volume unknowable until R1 use cases land (F5).
Event Hubs Standard (Kafka endpoint) - prod 24/7 + non-prod reduced | Azure | 1 TU prod x 8,760 + 3 non-prod x 3,120 = 18,120 TU-hrs/yr | 18120 | 0.0227 | 411.324 | 423.6637 | 436.3736 | 449.4648 | 462.9488 | 2183.775 | INDICATIVE | Rate VERIFIED but HCL matrix marks Event Hubs = N for UnO/CDP/Unica+ - self-hosted Kafka on cluster is the fallback (cost shifts to node pools).
Azure Cache for Redis Standard C1 - prod 24/7 + non-prod reduced | Azure | 1 prod x 8,760 + 3 non-prod x 3,120 = 18,120 cache-hrs/yr | 18120 | 0.1311 | 2375.532 | 2446.798 | 2520.2019 | 2595.808 | 2673.6822 | 12612.022 | ASSUMPTION | Rate VERIFIED; env pattern ASSUMPTION as R-L5.
Application Gateway WAF_v2 - prod 24/7 + shared non-prod reduced | Azure | 1 prod x 8,760 + 1 non-prod x 3,120 = 11,880 gw-hrs/yr | 11880 | 0.3409 | 4049.892 | 4171.3888 | 4296.5304 | 4425.4263 | 4558.1891 | 21501.4266 | ASSUMPTION | Rate VERIFIED; 2-gateway topology ASSUMPTION as P2-L19.
Application Gateway WAF_v2 - capacity units (prod) | Azure | 10 CU avg x 8,760 h = 87,600 CU-hrs/yr | 87600 | 0.0109 | 954.84 | 983.4852 | 1012.9898 | 1043.3794 | 1074.6808 | 5069.3752 | ASSUMPTION | Rate VERIFIED; 10 CU average ASSUMPTION (azure_infra_rates 'typical small prod ~10 CU').
API Management Standard unit - 24/7 (marginal; estate APIM may absorb) | Azure | 1 unit x 8,760 h/yr | 8760 | 0.7127 | 6243.252 | 6430.5496 | 6623.466 | 6822.17 | 7026.8351 | 33146.2728 | INDICATIVE | Rate VERIFIED. Set qty 0 if absorbed by existing estate APIM (SEGRO already runs APIM per architecture principles).
VPN Gateway VpnGw1 - 24/7 (marginal; estate may already carry) | Azure | 1 gateway x 8,760 h/yr | 8760 | 0.1439 | 1260.564 | 1298.3809 | 1337.3323 | 1377.4523 | 1418.7759 | 6692.5055 | INDICATIVE | Rate VERIFIED; marginal cost may be nil on the existing single-tenant estate - set qty 0 if absorbed.
Azure Private DNS zones | Azure | 10 zones x 12 mo = 120 zone-months/yr | 120 | 0.3788 | 45.456 | 46.8197 | 48.2243 | 49.671 | 51.1611 | 241.3321 | ASSUMPTION | Rate VERIFIED; zone count ASSUMPTION as P2-L23. Pennies - completeness.
Log Analytics ingestion - platform + agent observability (the biggest observability driver) | Azure | 10 GB/day x 365 = 3,650 GB/yr | 3650 | 2.1819 | 7963.935 | 8202.8531 | 8448.9386 | 8702.4068 | 8963.479 | 42281.6125 | ASSUMPTION | Rate VERIFIED (2.1819/GB PAYG). 10 GB/day ASSUMPTION - agent platforms are log-heavy (azure_infra_rates narrative: budget by GB/day); commitment tiers discount 15-30% at 100 GB/day+.
Azure Monitor metric alert rules | Azure | 100 metric timeseries x 12 mo = 1,200 metric-months/yr | 1200 | 0.0758 | 90.96 | 93.6888 | 96.4995 | 99.3944 | 102.3763 | 482.919 | ASSUMPTION | Rate VERIFIED; alert-rule count ASSUMPTION for a multi-service platform (first 10 free).
Key Vault operations | Azure | 5M ops/yr = 500 units of 10k ops | 500 | 0.0227 | 11.35 | 11.6905 | 12.0412 | 12.4025 | 12.7745 | 60.2587 | ASSUMPTION | Rate VERIFIED; negligible (a few GBP/yr) - completeness.
Microsoft Defender for Cloud workload protection | Azure | 40 resources x 12 mo = 480 resource-months x rate GBP 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | Rate not priced in fact files - GBP 0 adjustable until priced; will appear on a real bill.
Azure OpenAI - input tokens (placeholder until R1 use cases land) | Azure | 50M tokens/mo x 12 = 600 units of 1M/yr | 600 | 1.9 | 1140 | 1174.2 | 1209.426 | 1245.7088 | 1283.08 | 6052.4148 | ASSUMPTION | Rate VERIFIED (uksouth meter). Volume is a placeholder ASSUMPTION: F5 - the POAP delivers zero business-facing use cases at go-live, so token spend is near-zero until R1; adjust when R1 scope lands. GPT-4.1/4.1-mini are cheaper per the same fact file.
Azure OpenAI - output tokens (placeholder until R1 use cases land) | Azure | 10M tokens/mo x 12 = 120 units of 1M/yr | 120 | 7.6 | 912 | 939.36 | 967.5408 | 996.567 | 1026.464 | 4841.9319 | ASSUMPTION | As R-L20; Batch API halves the rate.
SEGRO platform run team - support & maintain, patching, upgrades, evals | SEGRO | 2 FTE x 220 working d/yr = 440 days/yr | 440 | 525 | 231000 | 237930 | 245067.9 | 252419.937 | 259992.5351 | 1226410.3721 | ASSUMPTION | 2 FTE ongoing ASSUMPTION (~GBP 231k/yr at the VERIFIED 525/day median). Context: the 15-22%-of-build annual S&M benchmark implies GBP 125-183k/yr on the default GBP 830k build - the 2-FTE line sits above that band because it also covers evals/upgrades, and full Y1 run (~GBP 312k incl. Azure) is 37.6% of build. Adjust the qty to taste. Rate VERIFIED. The run team also owns the agent-learning-to-rules feedback loop the architect flagged (F24, 18 Jul 2026) - evals/golden-set refresh is already within this line's scope.
ServiceNow ITSM - platform support fulfilers | SEGRO | 20 fulfilers x 12 mo = 240 user-months/yr | 240 | 74.02 | 17764.8 | 18297.744 | 18846.6763 | 19412.0766 | 19994.4389 | 94315.7358 | INDICATIVE | Rate INDICATIVE (aggregator USD 100/user/mo converted at 0.74015; ServiceNow publishes no list prices; packaging moved Apr 2026). 20 fulfilers fixed ASSUMPTION (OrgSize-agnostic). SEGRO already runs ServiceNow - marginal seats only.
HCL AMS / ongoing support & maintenance contract | HCL | 1 year x rate GBP 0 until contract shared | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | HCL contract pricing not shared. GBP 0 adjustable - HCL run totals are a FLOOR. Green Book outsourcing opex optimism bias +41% upper bound applies once a real figure lands.
HCL UnO platform licence renewal | HCL | 1 year x rate GBP 0 until contract shared | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | As R-L24.
HCL Unica+ licence renewal | HCL | 1 year x rate GBP 0 until contract shared | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | As R-L24.
HCL CDP licence renewal | HCL | 1 year x rate GBP 0 until contract shared | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | As R-L24.
HCL DX licence renewal | HCL | 1 year x rate GBP 0 until contract shared | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | As R-L24.
Third-party licence renewals - Oracle 19 + Aerospike (+ any MinIO successor) | ThirdParty | 1 bundle/yr x rate GBP 0 until quoted | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RATE_MISSING | F10 procurement items (HCL_V1 brief): prices not shared/published. GBP 0 adjustable.
FinOps / cost optimisation review cadence | SEGRO | 1 day/mo x 12 = 12 days/yr | 12 | 525 | 6300 | 6489 | 6683.67 | 6884.1801 | 7090.7055 | 33447.5556 | ASSUMPTION | ASSUMPTION per sizing_updates_missed 'post go-live run-rate FinOps review cadence' - POAP shows none. Rate VERIFIED. Typically self-funding against PAYG list prices (reservations save 30-60%).
Recurring AI red-team / audit dry-run cadence (annual refresh as agent surfaces and edge cases grow - F24/F26) | ThirdParty | 1 engagement/yr x ~5 tester-days = 5 days/yr | 5 | 950 | 4750 | 4892.5 | 5039.275 | 5190.4532 | 5346.1668 | 25218.3951 | INDICATIVE | Annual cadence is an ASSUMPTION. Rate: DERIVED CREST pen-test day rate (950) used as an INDICATIVE proxy for a specialist AI red-team rate - no published AI-red-team rate exists in the fact files. Ties to the architect's point that agent learning / edge-case transfer is ongoing, so red-team scope grows with the agent surface (F24; senior architect review 18 Jul 2026, F26). Lifecycle framing reinforced 18 Jul 2026: red-team scope grows with the agent surface, so this is a standing annual cadence, not a one-off — pairs with the widened pre-go-live two-touch range on P4-L8.
Claude Sonnet — input tokens (ModelSKU=Claude-Sonnet-5; mirrors R-L20 volume) | Azure | 50M tokens/mo x 12 = 600 units of 1M/yr (same volume, Claude list rate) | 600 | 2.22 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | CLAUDE branch of the ModelChoice toggle: same token VOLUME as the GPT-4o line it mirrors, priced at the Anthropic Claude Sonnet LIST rate (INDICATIVE, no committed-use discount; durable standard rate, not the intro rate that expires 31 Aug 2026). Active only when ModelChoice=Claude. Verified fragment: model_serving_rates.json (APPROVE). v3: ClaudeOnAzure / ModelSKU=Claude-Sonnet-5 (was ModelChoice=Claude).
Claude Sonnet — output tokens (ModelSKU=Claude-Sonnet-5; mirrors R-L21 volume) | Azure | 10M tokens/mo x 12 = 120 units of 1M/yr (same volume, Claude list rate) | 120 | 11.1 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | CLAUDE branch of the ModelChoice toggle: same token VOLUME as the GPT-4o line it mirrors, priced at the Anthropic Claude Sonnet LIST rate (INDICATIVE, no committed-use discount; durable standard rate, not the intro rate that expires 31 Aug 2026). Active only when ModelChoice=Claude. Verified fragment: model_serving_rates.json (APPROVE). v3: ClaudeOnAzure / ModelSKU=Claude-Sonnet-5 (was ModelChoice=Claude).
Self-hosted model serving — GPU node 24/7 (ModelChoice=Llama; A100 single-model pool) | Azure | 1 x NC24ads_A100_v4 node x 8,760 hr/yr (24/7 prod serving) | 8760 | 3.4782 | 0 | 0 | 0 | 0 | 0 | 0 | ASSUMPTION | LLAMA branch: 24/7 production inference serving on a single A100 80GB node (GBP 3.4782/hr VERIFIED, Azure Retail API uksouth). PAYG list is the ceiling — 1yr/3yr reservations and spot cut it materially. This is the run-time cost the self-host argument must show: unlike a hosted API, you pay for the GPU whether or not tokens flow. Active only when ModelChoice=Llama. Fragment: model_serving_rates.json.
Inference-ops run-team uplift for self-hosted serving (ModelChoice=Llama) | SEGRO | FTE fraction x 231 billable d/yr — ships at 0 (adjustable): 0.2–0.5 FTE illustrative | 0 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | ASSUMPTION | LLAMA branch ONLY. Ships at qty 0 so no invented headcount enters a total; the MLOps day rate (GBP 575, VERIFIED ITJobsWatch median) is the basis, the 0.2–0.5 FTE fraction is the ASSUMPTION (set the qty to fraction x 231). INCREMENTAL to the R-L22 platform run team — do not double-count. Self-hosting adds GPU/driver/CUDA lifecycle, quantisation & throughput tuning, 24/7 serving health that a hosted API removes. Active only when ModelChoice=Llama. Fragment: model_serving_rates.json.
Datadog Infrastructure Monitoring — per-host, ADDITIVE on top of Azure-native (Observability=Datadog) | Azure | 12 worker hosts (3/env x 4 envs, matching R-L2) x 12 mo = 144 host-months/yr; scales with EnvCount | 144 | 11.1 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | DATADOG branch: Infrastructure Monitoring Pro GBP 11.10/host/mo (committed annual, INDICATIVE list). Host count is DERIVED from the same worker-node estate as the run compute line R-L2 (3 nodes/env x 4 envs = 12 hosts) x 12 months = 144 host-months, and scales with EnvCount (env_scaling) so it tracks the node model rather than a static guess (fact file: 'size against the AKS/ARO node count'). APM is priced SEPARATELY on the same hosts (R-L39) — not conflated here. List price is a CEILING; the negotiated discount tier is RATE_MISSING (datadog_committed_annual_spend_tier). Active only when Observability=Datadog. Fragment: observability_datadog_rates.json.
Datadog APM — per traced host, ADDITIVE (Observability=Datadog; attached rate, pairs with R-L36 Infra) | Azure | Same 12-host estate as R-L36 (3/env x 4 envs) x 12 mo = 144 host-months/yr; scales with EnvCount | 144 | 22.94 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | DATADOG branch: APM GBP 22.94/host/mo (committed annual, INFRA-ATTACHED rate, INDICATIVE list). Datadog's attached APM rate REQUIRES a paired Infra Pro subscription on the same host — so R-L36 Infra (GBP 11.10) + R-L39 APM (GBP 22.94) = GBP 34.04/host is the CORRECT additive total (USD 15 + USD 31), NOT a double-count (verified against datadoghq.com/pricing: attached APM USD 31 is cheaper than standalone USD 36 precisely because it mandates the separate Infra line). Same host count as R-L36 (144 host-months, scales with EnvCount). List price is a CEILING; negotiated tier RATE_MISSING. Active only when Observability=Datadog. Fragment: observability_datadog_rates.json.
Datadog LLM Observability — base 100K LLM spans/mo (Observability=Datadog; committed) | Azure | 12 months of the committed 100K-span base tier | 12 | 118.42 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | ADDITIVE on top of the Azure-native lines (which stay on): LLM Observability Pro base tier GBP 118.42/mo committed (up to 100K LLM spans, INDICATIVE). The metered SKU Azure Monitor does NOT charge for — this is exactly why the Azure-only run floor understated observability, so selecting Datadog RAISES the floor. Overage (GBP 3.70 per 10K additional LLM spans) is the volume driver at agent scale, carried as the adjustable overage line R-L38. Active only when Observability=Datadog. Fragment: observability_datadog_rates.json.
Datadog LLM Observability — span overage (Observability=Datadog; ships at 0, adjustable) | Azure | 10K-span overage blocks/yr beyond the 100K base — ships at 0 (volume unknown until R1) | 0 | 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | ASSUMPTION | DATADOG branch: the true volume driver. GBP 3.70 per 10K LLM spans over the 100K base (INDICATIVE). Ships at 0 because agent call volume is unknown until R1 use cases land (F5) — the same reason the Azure token lines are placeholders. Illustrative: 1M LLM calls/mo ~= 90 blocks x 12 = ~GBP 4,000/yr. Adjustable. Active only when Observability=Datadog. Fragment: observability_datadog_rates.json.
GPT-4.1 — input tokens (ModelSKU=GPT-4.1; mirrors R-L20) | Azure | 50M tokens/mo x 12 = 600 units of 1M/yr (same volume, GPT-4.1 rate) | 600 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | GPT-4.1 branch (ModelVendor=AzureOpenAI, ModelSKU=GPT-4.1): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=GPT-4.1. Fragment: azure_model_sku_rates.json.
GPT-4.1 — output tokens (ModelSKU=GPT-4.1; mirrors R-L21) | Azure | 10M tokens/mo x 12 = 120 units of 1M/yr (same volume, GPT-4.1 rate) | 120 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | GPT-4.1 branch (ModelVendor=AzureOpenAI, ModelSKU=GPT-4.1): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=GPT-4.1. Fragment: azure_model_sku_rates.json.
GPT-5.6-Terra — input tokens (ModelSKU=GPT-5.6-Terra; mirrors R-L20) | Azure | 50M tokens/mo x 12 = 600 units of 1M/yr (same volume, GPT-5.6-Terra rate) | 600 | 1.8504 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | GPT-5.6-Terra branch (ModelVendor=AzureOpenAI, ModelSKU=GPT-5.6-Terra): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=GPT-5.6-Terra. Fragment: azure_model_sku_rates.json.
GPT-5.6-Terra — output tokens (ModelSKU=GPT-5.6-Terra; mirrors R-L21) | Azure | 10M tokens/mo x 12 = 120 units of 1M/yr (same volume, GPT-5.6-Terra rate) | 120 | 11.1022 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | GPT-5.6-Terra branch (ModelVendor=AzureOpenAI, ModelSKU=GPT-5.6-Terra): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=GPT-5.6-Terra. Fragment: azure_model_sku_rates.json.
GPT-5.6-Sol — input tokens (ModelSKU=GPT-5.6-Sol; mirrors R-L20) | Azure | 50M tokens/mo x 12 = 600 units of 1M/yr (same volume, GPT-5.6-Sol rate) | 600 | 3.7007 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | GPT-5.6-Sol branch (ModelVendor=AzureOpenAI, ModelSKU=GPT-5.6-Sol): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=GPT-5.6-Sol. Fragment: azure_model_sku_rates.json.
GPT-5.6-Sol — output tokens (ModelSKU=GPT-5.6-Sol; mirrors R-L21) | Azure | 10M tokens/mo x 12 = 120 units of 1M/yr (same volume, GPT-5.6-Sol rate) | 120 | 22.2045 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | GPT-5.6-Sol branch (ModelVendor=AzureOpenAI, ModelSKU=GPT-5.6-Sol): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=GPT-5.6-Sol. Fragment: azure_model_sku_rates.json.
Claude-Fable-5 — input tokens (ModelSKU=Claude-Fable-5; mirrors R-L20) | Azure | 50M tokens/mo x 12 = 600 units of 1M/yr (same volume, Claude-Fable-5 rate) | 600 | 7.4015 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | Claude-Fable-5 branch (ModelVendor=ClaudeOnAzure, ModelSKU=Claude-Fable-5): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=Claude-Fable-5. Fragment: azure_model_sku_rates.json.
Claude-Fable-5 — output tokens (ModelSKU=Claude-Fable-5; mirrors R-L21) | Azure | 10M tokens/mo x 12 = 120 units of 1M/yr (same volume, Claude-Fable-5 rate) | 120 | 37.0075 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | Claude-Fable-5 branch (ModelVendor=ClaudeOnAzure, ModelSKU=Claude-Fable-5): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=Claude-Fable-5. Fragment: azure_model_sku_rates.json.
Grok-4.3 — input tokens (ModelSKU=Grok-4.3; mirrors R-L20) | Azure | 50M tokens/mo x 12 = 600 units of 1M/yr (same volume, Grok-4.3 rate) | 600 | 0.9252 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | Grok-4.3 branch (ModelVendor=GrokOnAzure, ModelSKU=Grok-4.3): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=Grok-4.3. Fragment: azure_model_sku_rates.json.
Grok-4.3 — output tokens (ModelSKU=Grok-4.3; mirrors R-L21) | Azure | 10M tokens/mo x 12 = 120 units of 1M/yr (same volume, Grok-4.3 rate) | 120 | 1.8504 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | Grok-4.3 branch (ModelVendor=GrokOnAzure, ModelSKU=Grok-4.3): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=Grok-4.3. Fragment: azure_model_sku_rates.json.
Grok-4.5 — input tokens (ModelSKU=Grok-4.5; mirrors R-L20) | Azure | 50M tokens/mo x 12 = 600 units of 1M/yr (same volume, Grok-4.5 rate) | 600 | 1.4803 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | Grok-4.5 branch (ModelVendor=GrokOnAzure, ModelSKU=Grok-4.5): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=Grok-4.5. Fragment: azure_model_sku_rates.json.
Grok-4.5 — output tokens (ModelSKU=Grok-4.5; mirrors R-L21) | Azure | 10M tokens/mo x 12 = 120 units of 1M/yr (same volume, Grok-4.5 rate) | 120 | 4.4409 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | Grok-4.5 branch (ModelVendor=GrokOnAzure, ModelSKU=Grok-4.5): same token VOLUME as the GPT-4o line it mirrors; Azure-served meter. Active only when ModelSKU=Grok-4.5. Fragment: azure_model_sku_rates.json.
MCP hosting — Container Apps vCPU-seconds × McpServerCount | Azure | McpServerCount × always-on 0.5 vCPU floor (ASSUMPTION) | 15768000 | 2e-05 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | AGENT STACK MCP on ACA. Fragment: agent_runtime_azure_rates.json.
MCP hosting — Container Apps GiB-seconds × McpServerCount | Azure | McpServerCount × 1 GiB floor (ASSUMPTION) | 31536000 | 2.5e-06 | 0 | 0 | 0 | 0 | 0 | 0 | INDICATIVE | Paired memory with R-L40.
APIM fronting MCP tool calls × McpServerCount | Azure | McpServerCount × calls/server/yr / 1000 (ASSUMPTION unit) | 120 | 0.043 | 0 | 0 | 0 | 0 | 0 | 0 | ASSUMPTION | All MCP behind APIM (SEGRO principle). apim_call_unit is ASSUMPTION.
RAG embeddings — Ada tokens × AgentCount | Azure | AgentCount × embedding placeholder/yr | 50 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | ASSUMPTION | RAG embedding meter (VERIFIED). Active when AgentStack=Include.
Azure AI Search Basic unit (RagMemoryShape=AISearch_Cosmos) | Azure | 1× Basic search unit × 8760h (floor) | 8760 | 0.0842 | 0 | 0 | 0 | 0 | 0 | 0 | VERIFIED | VERIFIED AI Search Basic. Zero when CosmosOnly.
Cosmos Mongo agent memory — 100 RU/s × AgentCount | Azure | AgentCount × 8760h × 100 RU/s unit | 8760 | 0.0091 | 0 | 0 | 0 | 0 | 0 | 0 | ASSUMPTION | VERIFIED Cosmos autoscale meter. Memory always when Include; also vectors if CosmosOnly.
TOTAL RUN (per year / 5-yr) |  |  |  |  | 312073.8242 | 321436.0389 | 331079.1201 | 341011.4937 | 351241.8385 | 1656842.3154
Agent-stack run Y1 (MCP+RAG+memory subset) |  |  |  |  | 0
· of which MCP-driven (scales with McpServerCount) |  |  |  |  | 0
· of which agent-driven (scales with AgentCount) |  |  |  |  | 0
· of which fixed (AI Search — flat with 1 stack) |  |  |  |  | 0
▪ Run totals EXCLUDE SEGRO business-user time (UAT, agent adoption, process change) throughout - consistent with the TCO workbook convention.
▪ HCL-side run cost is a FLOOR: AMS + all four licence renewals are RATE_MISSING at GBP 0 because HCL has not shared contract pricing. Never present the run total as the expected HCL cost.
▪ Support & maintain context: R-L22 (2 FTE platform run team ~GBP 231k/yr) is ABOVE the 15-22%-of-build annual S&M band (GBP 125-183k/yr on the default GBP 830k build) because it also covers evals and upgrades; the band itself is an ASSUMPTION anchored to SAP's VERIFIED 22% list ra
▪ Azure figures are PAYG list-price ceilings (uksouth, GBP, Retail Prices API): EA/MACC discounts, 1-3 yr reservations (30-60% off VMs/DBs) and Log Analytics commitment tiers all reduce them.
▪ Excluded Azure meters that will appear on a real bill: managed disks, bandwidth/egress, Azure Firewall, Private Link endpoints, backup storage (azure_infra_rates narrative). Defender for Cloud is carried explicitly as RATE_MISSING.
▪ Azure OpenAI token lines are placeholders: the POAP delivers no business-facing use case at go-live (F5), so real token volumes await R1 scope.
▪ Non-prod reduced-hours pattern (12h weekdays = 3,120 h/yr) is an ASSUMPTION; running non-prod 24/7 roughly triples those components.
▪ M365/Copilot are existing SEGRO baseline (ARA25: Copilot rolled out to all employees 2025) - deliberately NOT carried as incremental run lines.

## R1 Pilot
R1 September Pilot — one supervised Content Agent (the costed alternative)
Basis: effort = Likely · OUT OF TOTAL (not in TotalBuild / TotalRun5yr) · interim infra, ~6 weeks, September
▪ OUT OF TOTAL — this is the costed ALTERNATIVE to the full HCL mobilisation: one supervised Content Agent on interim infra, ~6 weeks, September. It is NOT added to TotalBuild or TotalRun5yr (those are the POAP-as-drawn figures). Every rate is VERIFIED and inherited from the Rates tab; every quantity is an ASSUMPTION low/likely/high range. ~£37k at Likely — a rounding error against the £830k build FLOOR, which is the whole point of the offer. Fragment: r1_pilot_scope.json (APPROVE).
Pilot line | Side | Quantity model | Qty Low | Qty Likely | Qty High | Qty (live) | Rate/unit £ | Cost £ (live) | Status | Basis / source
A couple of agent/AI engineers - build & supervise ONE Content Agent (prompt/tooling, content-source connectors, guardrails, eval harness for the single agent) on interim infra | SEGRO | 2 agent/AI engineers x 30 days each = 60 person-days over ~6 wk; low 40 (2 x 20 d, tighter scope/ramp) / high 80 (2 x 40 d, overrun or a 3rd pair of hands) | 40 | 60 | 80 | 60 | 525 | 31500 | ASSUMPTION | RATE VERIFIED: contractor_devops_engineer_day = GBP 525/day (spec_rates_control.json, ITJobsWatch UK median). No dedicated 'agent-engineer' or ML-engineer rate exists in the fact files; the DevOps-engineer median is the nearest AI/dev build rate and is already the basis used elsewhere for agent-adjacent build/deploy work (spec_cost_model P2-L27 DevSecOps-for-agents, P5-L2 CI/CD-for-agents). Nearest alternative = contractor_data_engineer_day (GBP 500, VERIFIED) if an ML/data slant is preferred. QUANTITY ASSUMPTION: 2 engineers x ~6 wk; a single supervised Content Agent is a small build, so 60 person-days is the likely, 40-80 the range.
Fractional supervising lead - human-in-the-loop oversight, guardrail/eval sign-off, go/no-go on agent outputs (the 'supervised' in the offer) | SEGRO | 0.25 FTE x 6 wk x 5 d = ~8 person-days; low 5 / high 12 | 5 | 8 | 12 | 8 | 625 | 5000 | ASSUMPTION | RATE VERIFIED: contractor_solutions_architect_day = GBP 625/day (spec_rates_control.json, ITJobsWatch UK median) used as the senior supervising-lead rate. QUANTITY ASSUMPTION: deliberately small fractional oversight (0.25 FTE) - this line embodies the human-in-the-loop supervision that makes the single-agent pilot a controlled release. Optional; set to 0 if the two engineers self-supervise.
Sandbox worker nodes - a couple of D4s_v5 D-series nodes on an interim AKS Free-tier cluster (cluster-mgmt fee = GBP 0 on Free tier, so only node compute is costed) | Azure | 2 x D4s_v5 nodes x 6 wk; likely 1008 node-hrs (2 nodes x 84 h/wk = 12h x 7d), low 720 (12h x 5 weekdays), high 2016 (24/7) | 720 | 1008 | 2016 | 1008 | 0.1682 | 169.5456 | ASSUMPTION | RATE VERIFIED: vm_d4s_v5_node_hr = GBP 0.1682/node-hr (spec_rates_control.json, Azure Retail Prices API uksouth PAYG). INTERIM infra: sandbox cluster uses AKS Free tier (azure_infra_rates.json Free tier = GBP 0.0, dev/test) so no aks_standard_mgmt_hr fee applies. QUANTITY ASSUMPTION: 2 small nodes is the minimal footprint for one low-throughput agent; running-hours range spans weekday-only to 24/7. ~GBP 170 at likely - trivially small vs people cost.
Minimal PaaS - one small PostgreSQL Flexible Server (4 vCore) for agent state / content metadata store | Azure | 1 server x 6 wk; likely 504 server-hrs (84 h/wk), low 360 (12h weekdays), high 1008 (24/7) | 360 | 504 | 1008 | 504 | 0.3121 | 157.2984 | ASSUMPTION | RATE VERIFIED: pg_flexible_d4ds_compute_hr = GBP 0.3121/hr (spec_rates_control.json). QUANTITY ASSUMPTION: a single small state store for one agent, on interim infra, same 6-wk window and hours pattern as PILOT-L3. The smallest published SKU in the fact files; storage priced separately (PILOT-L5).
Minimal PaaS - PostgreSQL provisioned storage for the sandbox state store | Azure | 32 GB x ~1.5 months = 48 GB-months; low 32 / high 96 | 32 | 48 | 96 | 48 | 0.1008 | 4.8384 | ASSUMPTION | RATE VERIFIED: pg_flexible_storage_gb_mo = GBP 0.1008/GB/mo (spec_rates_control.json). QUANTITY ASSUMPTION: 32 GB is a minimal pilot allocation; ~1.5 months covers the 6-wk window. Pennies - carried for completeness.
Supervision observability - Log Analytics ingestion of agent run-traces (so a human can watch/audit every action; low volume for a single supervised agent) | Azure | ~0.7 GB/day x 42 days ~= 30 GB over 6 wk; low 10 / high 60 (first 5 GB/mo is free per the meter) | 10 | 30 | 60 | 30 | 2.1819 | 65.457 | ASSUMPTION | RATE VERIFIED: log_analytics_gb_ingested = GBP 2.1819/GB (spec_rates_control.json). QUANTITY ASSUMPTION: a single low-throughput supervised agent generates modest run-trace volume; this line makes 'supervised' concrete (human-in-the-loop needs the traces). Gross of the 5 GB/month free allowance.
LLM tokens - Azure OpenAI GPT-4o INPUT tokens for the Content Agent (low pilot throughput, supervised single agent) | Azure | ~10M input tokens/mo x ~1.5 mo = 15 units of 1M; low 5 / high 40 | 5 | 15 | 40 | 15 | 1.9 | 28.5 | ASSUMPTION | RATE VERIFIED: aoai_gpt4o_input_1m_tokens = GBP 1.90 per 1M input tokens (spec_rates_control.json, Azure Retail Prices API uksouth meter 'gpt 4o 1120 Inp glbl'). QUANTITY ASSUMPTION: deliberately low - one supervised content agent at low throughput. GPT-4o-mini (GBP 0.10/1M in same fact file) would cut this ~19x if used; carried on GPT-4o as the conservative anchor.
LLM tokens - Azure OpenAI GPT-4o OUTPUT tokens for the Content Agent (generated content, low pilot volume) | Azure | ~3.3M output tokens/mo x ~1.5 mo = 5 units of 1M; low 2 / high 12 | 2 | 5 | 12 | 5 | 7.6 | 38 | ASSUMPTION | RATE VERIFIED: aoai_gpt4o_output_1m_tokens = GBP 7.60 per 1M output tokens (spec_rates_control.json, meter 'gpt 4o 1120 Outp glbl'). QUANTITY ASSUMPTION: low single-agent output volume; Batch API halves the rate (GBP 3.80/1M) per the fact file if throughput allows.
PILOT TOTAL (out of the POAP total) | [7 empty] | 36963.6394
Pilot total £36,964 vs POAP build FLOOR £830,342 — the price of saying yes to one supervised agent in September.

## Agents
Named agents — which to build (catalogue; Gantt ASSUMPTION lanes)
AgentStack = Exclude · AgentCount intensity = 1 · Include flags mark which agents are in the delivery programme (Gantt rows always visible as ASSUMPTION gaps when Exclude).
Agent id | Name | Use case | MCP apps | RAG? | Include | Notes
AGT-OPEX | OpEx categorisation agent | opex | MRI | Y | Exclude
AGT-CAPEX | CapEx assist agent | capex | MRI, Anaplan | Y | Exclude
AGT-GROWTH | Growth / Research Pack agent | growth | SAMA | Y | Exclude
AGT-METER | Meter exception agent | meter | UL360 | N | Exclude
AGT-RECON | Recon discrepancy agent | recon | MRI, UL360 | N | Exclude
AGT-R1-CONTENT | R1 Content Agent (supervised September pilot) | r1_pilot |  | N | Exclude | Costed on R1 Pilot tab OUT OF TOTAL
AGT-ORCH | Platform orchestrator / supervisor agent | platform |  | N | Exclude | Not a named UC agent — catalogue ASSUMPTION for multi-agent supervision
▪ Include column is formula-driven from AgentStack + catalogue defaults (amber). Overtype with a fixed Include/Exclude if you need a custom mix — replacing the formula is intentional. AgentCount still scales run intensity.

## Team Model
Team Model — FTE by phase (reference; build lines carry the priced quantities)
Phase | Role | Side | FTE | Status | Basis
P1 | Solutions architect (workshops, HLD/LLD, KDDs) | SEGRO | 1 | ASSUMPTION | Slide 3 workshop chain + slide 5 doc list; full-time for 5 wk.
P1 | Platform engineer (sizing, physical diagrams) | SEGRO | 0.6 | ASSUMPTION | Slide 5 physical sizing + LLD diagrams.
P1 | Cloud security (cyber workshop, impact analysis) | SEGRO | 0.4 | ASSUMPTION | Slide 5 cyber deliverables.
P1 | Data engineer (data mgmt workshop, data flow design) | SEGRO | 0.4 | ASSUMPTION | Slide 5 data flow design.
P1 | Business analyst (R1 scope, DRG/ARG pack) | SEGRO | 0.4 | ASSUMPTION | Slide 3 R1-scope milestone.
P1 | Project manager (mobilisation, procurement) | SEGRO | 1 | ASSUMPTION | Slide 5 delivery plan + procurement spec.
P1 | HCL architecture/product SMEs | HCL | 0.6 | ASSUMPTION | HCL named team (HCL_V1 brief); Platform Architect still TBD - a named risk.
P2 | Platform engineers (Azure foundations) | SEGRO | 2 | ASSUMPTION | Squad shape mirrors platform.json 5.5-effective-FTE convention: 2.0 + 1.0 + 1.5 + 0.5 + 0.5 = 5.5 FTE build squad.
P2 | Kubernetes engineer (AKS hardening) | SEGRO | 1 | ASSUMPTION | Part of the 5.5-FTE squad shape.
P2 | DevOps engineers (shared services) | SEGRO | 1.5 | ASSUMPTION | Part of the 5.5-FTE squad shape; 8 named services on slide 3.
P2 | Cloud security engineer (cyber design) | SEGRO | 0.5 | ASSUMPTION | Part of the 5.5-FTE squad shape.
P2 | Data engineer (governance principles) | SEGRO | 0.5 | ASSUMPTION | Part of the 5.5-FTE squad shape.
P2 | Eval harness build (FND-4) | SEGRO | 0.44 | ASSUMPTION | platform.json FND-4: 20 pd over 9 wk = 0.44 FTE add-on (source labels the task ASSUMPTION); absent from POAP (F13).
P2 | Project manager | SEGRO | 1 | ASSUMPTION | 1 PM across 6 workstreams; PM-as-% benchmark RATE_MISSING so sized bottom-up.
P2 | DevSecOps engineer (IaC, policy-as-code, CI/CD) | SEGRO | 0.6 | ASSUMPTION | P2-L27: 30 pd likely over 10 wk x 5 d = 0.6 FTE. F19 - no DevSecOps automation anywhere in the POAP; senior architect review 18 Jul 2026.
P3 | HCL UnO/TX install team | HCL | 3 | ASSUMPTION | Grade mix ASSUMPTION on HCL SFIA L3 rate; low band anchored to HCL D-025 20-30 day core install.
P3 | HCL Unica+/CDP deploy team | HCL | 2 | ASSUMPTION | Slide 3 HCL bar second block.
P3 | SEGRO platform support to HCL install | SEGRO | 1 | ASSUMPTION | Vendor install on SEGRO-run cluster consumes platform-team time.
P4 | Test engineers (SIT + performance/DR) | SEGRO | 2.75 | ASSUMPTION | 2 SIT + 0.75 perf/DR; slide 9 test-report deliverables.
P4 | Test manager | SEGRO | 1 | ASSUMPTION | Defect register, UAT plan/sign-off.
P4 | UAT coordination BA | SEGRO | 1 | ASSUMPTION | Business-user UAT time itself not costed (see notes).
P4 | CREST pen testers | ThirdParty | 0.5 | INDICATIVE | ~10 tester-days in a 4-wk window; F7 booking lead time.
P4 | HCL defect-fix support | HCL | 1 | ASSUMPTION | Vendor-stack defects need vendor fixes.
P4 | SEGRO platform support | SEGRO | 1 | ASSUMPTION | Env fixes and redeploys during test.
P5 | Platform engineers (readiness, migration, go-live) | SEGRO | 2 | ASSUMPTION | Slide 3 Deploy items 1-5.
P5 | DevOps engineer (cutover, handover pack) | SEGRO | 1 | ASSUMPTION | Slide 10 deploy docs.
P5 | Release/project manager (go/no-go) | SEGRO | 1 | ASSUMPTION | Go/no-go decision milestone.
P5 | Cloud security (pen-test remediation + retest) | SEGRO | 0.5 | ASSUMPTION | F7: remediation window before go/no-go.
P5 | HCL go-live support | HCL | 1 | ASSUMPTION | HCL components through cutover.
P6 | Hypercare squad (avg 1.5 FTE coverage) | SEGRO | 1.5 | ASSUMPTION | Average 1.5 FTE coverage across the 6-wk hypercare window (coverage ASSUMPTION; duration from the 4-8 wk programme_benchmarks norm).
P6 | HCL PGLS support | HCL | 1 | ASSUMPTION | Flex to 0 if inside fixed-price contract.
P6 | Change mgmt & training (spread P2-P6, booked P6) | SEGRO | 0.8 | ASSUMPTION | 120 pd over ~30 wk = 0.8 FTE; sized from Prosci 10%-of-budget benchmark (VERIFIED).
P6 | Service transition PM (ITIL/ServiceNow) | SEGRO | 0.5 | ASSUMPTION | SEGRO principle: ServiceNow service transition for everything.
ENVIRONMENT & SCALING MODEL (drives the EnvCount / Cluster / NodeSize toggles)
Env-count scaling | EnvCount toggle 2/3/4 scales every env_count-tagged line linearly as EnvCount/4. Baseline quantities are stated at 4 environments = SEGRO Dev/Test/Pre-Prod/Prod standard. The env count is an OPEN KDD on the POAP ('KDD: Vol of Environments', F9) - this toggle prices both answers.
CDP 2-env exception (F9) | HCL proposes 4 envs for UnO/TX/Commerce but only 2 for Unica/CDP (mobilisation doc line 76; Track Workbook 'Unica+ Test/Prod exception - Decision required'). Below SEGRO's 4-env standard and it weakens the December test phase - no true pre-prod for CDP (F9). Model at EnvCount=4 for the SEGRO standard; EnvCount=2 approximates HCL's CDP exception. Carry the exception as an explicit accepted-risk lin
Single vs dual cluster (F3) | ClusterCount Single/Dual doubles cluster-tagged lines (AKS mgmt fee, ARO masters). HCL's own support matrix marks AKS x CDP = N - if CDP stays in scope on AKS, a second cluster (or ARO) may be forced (F3), so Dual is a live branch, not a stress test.
Node-size S/M/L multipliers | NodeSize S=0.5x, M=1x, L=2x - applied as the NodeSize component of node_env-tagged lines (worker pools scale with EnvCount/4 x NodeSize composed; no line uses a bare node_size tag). Basis: M = D4s_v5 (4 vCPU/16 GiB, GBP 0.1682/hr VERIFIED) or D4ds_v5 (GBP 0.1985/hr VERIFIED) on the ARO branch; L = the 8-vCPU sibling at exactly 2x (linear per-vCPU Azure pricing, VERIFIED); S = half the M node-hours

## Benchmarks
Benchmarks — web-verified market data vs this plan (comparisons recalc live)
Grounding for a ~700-person UK/EU organisation (adjustable OrgSize input; note SEGRO ARA 2025 reports 463 direct employees — SEGRO runs lean with an outsourced supply chain, so per-employee ratios are conservative). All items adversarially verified against live sources 16-17 Jul 2026.
Benchmark | Value | Unit | Status | Source | This plan (live)
SEGRO plc headcount (Group, year-end basis per governance report) | 463 | employees | VERIFIED | SEGRO Annual Report and Accounts 2025, Corporate Governance (p86): 'a non-unionised business with a headcount | 700
SEGRO plc total revenue FY2025 | 726 | GBP million per year (2024: 675) | VERIFIED | SEGRO ARA 2025, financial statements (p150). Comparison shows total 5-yr programme cost as a share of one year | 0.3426%
IT spend as % of revenue — UK cross-industry typical range (property firms typically 1.5-3 | 3-6 | % of annual revenue | INDICATIVE | Start Tech, citing Computer Economics benchmarking (2025; page names Computer Economics only, an Avasant compa | 0.06852%
IT operational spend per user per year — cross-industry average (this-plan column = 5-yr T | 7614 | USD per user per year (~GBP 5,635 at ECB | INDICATIVE | Avasant IT Spending and Staffing Benchmarks (via VC3 summary). Comparison shows this plan's annualised 5-yr TC | 710.6241
HM Treasury optimism-bias uplift — Equipment/Development (ICT) capex, lower-to-upper bound | 10-200 | % uplift on estimated capex (start at UP | VERIFIED | HM Treasury, Supplementary Green Book Guidance: Optimism Bias, Table 1 (Mott MacDonald 2002). Current asset UR | 15%
HM Treasury optimism-bias uplift — Equipment/Development (ICT) works duration | 10-54 | % uplift on estimated duration | VERIFIED | HM Treasury Green Book Optimism Bias, Table 1 (same asset URL as capex row). | Applied to the POAP's ~29-week Design-to-Deploy window: +3 weeks (lower) to +16 weeks (upper), pushing Feb 2027 go-live
Average overrun on large IT projects (>$15M) | 45 cost / 7 schedule | % over budget / % over time (average; an | VERIFIED | McKinsey & Company with University of Oxford, 'Delivering large-scale IT projects on time, on budget, and on v | 15%
IT project fat-tail risk (Flyvbjerg & Budzier, 1,471 projects) | 27 average; 1-in-6 projects are black swans averaging +200 cost / +70 schedule | % overrun | VERIFIED | Flyvbjerg & Budzier, 'Why Your IT Project May Be Riskier Than You Think', HBR 89(9), 2011 (arXiv:1304.0265). C | 2491026.2124
Change management budget as % of total project budget (most common allocation) | 10 | % of project budget | VERIFIED | Prosci, 'How to Budget for Change Management' (pub. 24 May 2023, upd. 17 Oct 2025; Prosci Best Practices resea | 83034.2071
Annual support & maintenance as % of initial build cost (custom software, commercial rule | 15-22 | % of build cost per year | ASSUMPTION | Reasoned from SAP 22% vendor list rate (VERIFIED) and 80-90%-of-lifecycle maintenance literature — no single a | 37.58%
Enterprise software vendor annual support & maintenance — SAP Enterprise Support list rate | 22 | % of licence fee per year | VERIFIED | SAP Support Portal: list price 'remains fixed at 22 percent until 2025' (verifier note: quote carries the 'unt | Verified vendor anchor for the 15-22%/yr S&M assumption above — no separate live comparison.
Hypercare duration norm for an implementation of this size | 4-8 | weeks | ASSUMPTION | Reasoned from Microsoft Dynamics 365 implementation guidance (VERIFIED: short, fixed-end-date, criteria-based | This plan carries 6 wk (within the 4-8 wk norm) at an average 1.5 FTE coverage assumption (build line P6-L1)
Enterprise GenAI value realisation | 74% of companies struggle to achieve and scale value from AI; only 26% move beyond PoC to generate value | % of surveyed companies (1,000 surveyed) | VERIFIED | BCG press release, 'AI Adoption in 2024', 24 Oct 2024 (verifier: bcg.com bot-blocked on re-fetch; URL slug con | Benefits-realisation caveat: majority of AI programmes do not scale value — supports F5 (no R1 delivery lane = zero busi
Microsoft 365 Copilot add-on | 23.1 | GBP per user per month, annual subscript | VERIFIED | Microsoft UK enterprise plans & pricing page, fetched 16 Jul 2026. SEGRO already rolled Copilot out to all emp | 194040
ServiceNow ITSM Standard — indicative per-user price | 100 | USD per user per month (indicative; larg | INDICATIVE | NowTribe 2026 cost breakdown (per USER per the source page — verifier MINOR corrected from 'per fulfiller'). S | USD — do not silently convert; if costed, add an explicit FX input cell (ECB ref 0.74015 GBP/USD, 16 Jul 2026).
AKS Standard tier cluster management fee, UK South | 0.0758 | GBP per cluster per hour (~GBP 664/clust | VERIFIED | Azure Retail Prices API, currencyCode=GBP, uksouth, queried 2026-07-17 (verifier re-queried: exact). | Feeds the Platform=AKS branch; scales with ClusterCount toggle (dual cluster doubles the management fee).
Azure Red Hat OpenShift worker licence fee (General Purpose), UK South list | 0.0324 | GBP per vCPU per hour (~GBP 284/vCPU/yea | VERIFIED | Azure Retail Prices API, GBP, queried 2026-07-17 (verifier re-queried: all scale points exact). The auditable | Feeds the Platform=ARO branch (per-vCPU licence uplift line); the published IDC/Forrester OpenShift studies were unverif